## project import
Project Number | Job Sequence | Job Number | Old Job Number | Agreement type / Stage | stage | Street Number | Street | Suburb | City | Site Address | Weekly Review, Forecast Commencment Date | Adjusted Forecast Date (QBE or load adjusted) by management | Actual Release date to (Scheduling , purchase orders) for ACC | Client Type - Retail , Lofty , Developer | With | Notes | CMA | Sales Consultant | Site Manager | OTR - Community Title | Number of Dwellings Number of Single Stories | Number of Dwellings Number of Double Stories | Number of Dwellings Number of Total Dwellings | STAGE 1 PWA & Invoice Issued | STAGE 1 PWA & Invoice Signed | STAGE 1 PWA & Invoice Paid (7 Days) | STAGE 1 PWA & Invoice $ Amount Paid | STAGE 1 (1 Day) Sales Documents (Incl. Site Inspection) Complete | STAGE 1 Added to Trello Trello | STAGE 1 Concept Plan Ordered | STAGE 1 Concept Plan Received | STAGE 1 Concept Plan Amendment Ordered | STAGE 1 Concept Plan Amendment Received | STAGE 1 Concept Plan Signed Off (7 Days) | STAGE 1 Site Survey Ordered | STAGE 1 Site Survey Received (14 Days) | STAGE 1 Soil - Bore Logs Ordered | STAGE 1 Soil - Bore Logs Received (14 Days) | STAGE 1 Planning Drawings Ordered | STAGE 1 Planning Drawings Received | STAGE 1 Planning Drawings Amendment Ordered | STAGE 1 Planning Drawings Amendment Received | STAGE 1 Planning Drawings Signed off (14 Days) | STAGE 1 Prelim EER Ordered | STAGE 1 Prelim EER Received (2 Days) | STAGE 1 Prelim EER Confirm EER option with Scheduling | STAGE 1 Prelim EER Log on Sales Estimating Trello | STAGE 1 Prelim EER Confirm EER Option with Scheduling | STAGE 1 Prelim EER Received back from Estimating | STAGE 1 Civil Plan Ordered | STAGE 1 Civil Plan Received (10 Days) | STAGE 1 Civil Plan Gavin Check Ordered | STAGE 1 Civil Plan Gavin Check Returned (2 Days) | STAGE 1 Civil Plan Amended Ordered | STAGE 1 Civil Plan Amended Received (10 Days) | STAGE 1 Prelim Footings Ordered | STAGE 1 Prelim Footings Received (2 Days) | STAGE 1 Lodged for Planning Approval Lodged | STAGE 1 Lodged for Planning Approval Approved (28 Days) | STAGE 1 Lodged for Planning Approval RFI Received | STAGE 1 Lodged for Planning Approval RFI Responded (14 Days) | STAGE 1 Final Quote Check Issued to Estimator | STAGE 1 Final Quote Check Sent to S/C | STAGE 1 Final Quote Check Contract Sent to Ryan | STAGE 1 Final Quote Check Contract Approved by Ryan | STAGE 1 Contracts/Send Finalised Quote Issued | STAGE 1 Contracts/Send Finalised Quote Received (7 Days) | STAGE 1 Contracts/Send Finalised Quote Sale Contact Client to Confirm No more Changes | STAGE 1 2nd Deposit - contract deposit Issued | STAGE 1 3rd Deposit - contract deposit Received (7 Days) | STAGE 1 Contract Value $ | STAGE 1 Stage 1 Complete | STAGE 2 DNF Conditions Check Completed | STAGE 2 Working Drawings Ordered | STAGE 2 Working Drawings Received (14 Days) | STAGE 2 Working Drawings Plan Check complete | STAGE 2 Working Drawings Logged for Amends | STAGE 2 Working Drawings Amends received | STAGE 2 Working Drawings Amended Plans Checked | STAGE 2 Working Drawings Finalised and signed (10 Days) | STAGE 2 Pegging Plan/Encroachment Plan Ordered | STAGE 2 Pegging Plan/Encroachment Plan Received (7 Days) | STAGE 2 Finalised EER Ordered | STAGE 2 Finalised EER Received (7 Days) | STAGE 2 Finalised EER Sent to Scheduling | STAGE 2 Finalised EER Received back from Scheduling (1 Day) | STAGE 16 Finalised EER Stage 2 Complete | CA Sheet Added to Pre-construction Trello + Move to Stage 3 on LMWF | Attached lightweight Verandah Engineering Ordered | Received (14 Days) | FCR Ordered | Received (14 Days) | Amendment Ordered | Amendment Received | Sent to Gavin | Received back from Gavin (7 Days) | Electrical/NBN Undergrounds Plan Ordered | Plan Received (10 Days) | Permit Application Lodged to Council | Permit received | NBN layout sent to CMA's | Section 221 - Stormwater/Crossover Permits Ordered | Received (14 Days) | Timber Frame / Steel Frame | Framing and Trusses Ordererd | Received (21 Days) | Amendment Ordered | Amendment Received | Beam Design Ordered | Receieved (21 Days) | Amendment Ordered | Amendment Received | Construction/Timber/Beam Jordan Check Sent to Management | Approved (7 Days) | Selections Selections Consultant | Selection Type Scheme / Client | Email Request to selections to contact client | Gallery Appointment Date (21 Days) | Selection Variation signed | Selections booklet signed (10 Days) | 1st Site Inspection Ordered | Back (14 Days) | Items Actioned (5 Days) | Retaining, Fencing & BOB Retaining In Contract? | Retaining Required Before Or During Build | Fencing In Contract? | BOB Sent | BOB Signed + Contact Details (30 Days) | Fencing Notices Issued to client | Fencing Sent Via Registered Mail | Registered Mail Collected | 30 day overdue letter | Cross Notice Received / Notes | Cross notice responded to (7 Days) | Fencing Notices Completed + Saved in folder (14 Days) | SA Water SA Water Docs proposed location Plan ordered | Received (7 Days) | Cross check SA Water Locations against Working Drawings | Invoice Received | Invoice paid (2 Days) | Confirmation of SA Water Meters & Sewer Connection on Site | Construction Price Check (CPC) Sheet requested Log on trello | received (14 Days) | sent to Gary | Gary communicate to client /meeting (3 Days) | Variation issued? | Variation Signed / Approved (14 Days) | Check contract Vegetation Site Scrape | Variation Required Yes/No | Issued | Received (5 Days) | BRC/KBS Lodged | Approved (28 Days) | RFI Received | RFI Responded (14 Days) | CITB Paid (Admin - CC) | DA DA Requested | DA Approved (7 Days) | Final Site Inspection, confirmation of Services Ordered | Back (7 Days) | Actioned | Finance Updated Progress Payment Schedule issued for VO's over $40K | Total of Variations Incl. CPC | Revised Progress Claim amount/Total Build Amount - Approved by Accounts | Loan Approval Requested | Loan Approval Received (14 Days) | Further Proof of Finance | Commencement Letter requested | Commencement Letter received | Settlement on Land - Titles | HOW Discuss amount with Craig | HOW Insurance Requested | Received | Invoiced Paid | Construction Release Request Released to Construction Template CRAIG | Pre Release to Scheduling and PO's | released to construction (HOW Complete) | CANCELLATIONS PWA Cancellation Letter Issued (also update col B to 'cancelling') | Signed Returned | Followed Up (Unsigned) | Advised Departments Job Closed | Contract Cancellation Refund Y/N | Agreed Amount $ | Release of Documents Y/N | Letter Issued | Followed up Unsigned | Signed Returned | Payment Made | Documents Released | Advised Departments Job Closed | Column K (unnamed in CERTIFICATION) | Estimator | Link
1001 | 01 | 1001-01 | 1200 | PWA | Cancelling | #61 | Nelson Avenue | Flinders Park | Lot 611 | #61 Nelson Avenue, Flinders Park (Lot 611) |  |  |  | Retail | Vincent Iannazzone & Lisa Marie Iannazzone | clients saving money- pick up again 2024 |  | Brenton G | Daniel |  | 0 | 1 | 1 | 2022-02-22 | 2022-02-24 | 2022-02-25 | 5000 |  | Yes | 2022-03-23 | 2022-03-30 |  |  | 2022-04-03 | 2022-04-04 | 2022-04-21 | 2022-04-04 | 2022-06-01 | 2022-05-26 | 2022-06-01 |  |  | 2022-06-03 | 2022-05-23 | 2022-05-25 |  | 2022-05-25 |  | 2022-05-25 | 2022-05-23 | 2022-06-01 | 2022-06-03 | 2022-06-03 | 2022-07-11 |  | 2022-05-23 | 2022-06-01 | 2022-06-03 | 2022-08-10 | 2022-06-22 | 2022-07-12 | 2022-08-22 | 2022-09-05 |  |  | 2022-09-15 |  |  | 2022-02-22 | N/A |  | No | [14 empty] | No | [69 empty] | - | [7 empty] | - | [25 empty] | Vicki
1002 | 01 | 1002-01 | 1230 | Contract | Cancelling | #28 | Primmer Avenue | Modbury North |  | #28 Primmer Avenue, Modbury North |  |  |  | Retail | Mukhtar Jawidi & Kousar Mirzaei | non responsive |  | Paul | Tom Sando |  | 0 | 1 | 1 | 2022-04-04 | 2022-05-02 | 2022-04-27 | 3000 |  | Yes | 2022-06-07 | 2022-06-09 |  |  | 2022-06-28 | 2022-05-19 | 2022-06-06 | 2022-05-19 | 2022-07-26 | 2022-09-14 | 2022-09-20 |  |  | 2022-08-16 | 2022-07-20 | 2022-07-22 |  | 2022-07-22 |  | 2022-07-25 | 2022-07-20 | 2022-07-26 | 2022-08-22 | 2022-08-22 | 2022-09-14 |  | 2022-07-20 | 2022-07-26 | 2022-08-22 | 2022-10-05 | 2022-09-13 | 2022-09-23 | 2022-10-17 | 2022-10-25 |  |  | 2022-11-07 | 2022-11-08 |  | 2022-10-25 |  | 445639 | No |  | 2022-11-14 | 2022-11-30 | 2022-12-08 | [10 empty] | No | [69 empty] | - | [7 empty] | - | [12 empty] | Form has been commenced |  |  |  | No | N/A | No | 2023-08-17 | [5 empty] | Vicki
1003 | 01 | 1003-01 | 1339 - D1 | PWA | On Hold | #72 | Birdwood Terrace | North Plympton | Lot 1 | #72 Birdwood Terrace, North Plympton (Lot 1) | 2024-01-31 | 2024-03-15 |  | Developer | Amirreza Jourabchi |  |  | Brenton G | Paul C | Yes | 0 | 1 | 1 | 2022-12-07 | 2022-12-13 | 2022-12-13 | 1000 |  | Yes | 2022-12-20 | 2022-12-21 | 2023-04-05 |  |  | 2023-04-24 | 2023-05-19 | 2023-04-24 | 2023-06-08 | 2023-05-09 | 2023-05-11 | 2023-08-11 | 2023-08-15 |  | 2023-06-09 | 2023-06-13 |  |  |  |  | 2023-04-21 | 2023-06-08 | 2023-08-15 | 2023-05-16 | 2023-08-11 | 2023-08-15 | 2023-04-21 | 2023-06-08 | 2023-06-09 | 2023-09-01 | 2023-06-29 | 2023-08-31 | 2023-11-13 | 2023-11-20 | [8 empty] | No | [14 empty] | No | [69 empty] | - | [7 empty] | - | [25 empty] | Elise
1004 | 01 | 1004-01 | 1288 | PWA | - | #13 | Perserverance Road | Tea Tree Gully | Lot 1 | #13 Perserverance Road, Tea Tree Gully (Lot 1) | 2024-12-31 | 2024-03-30 |  | Retail | Jarrad Martin Hawkins | 22/06 - To be logged for PA | Marie | Brenton G | TBC | No | 1 | 0 | 1 | 2022-06-01 | 2022-07-25 | 2022-07-07 | 3000 |  | Yes | 2022-07-25 | 2022-07-25 |  |  | 2024-01-16 | 2022-07-25 | 2022-08-04 | 2024-11-04 | 2024-12-20 | 2023-01-16 | 2023-01-17 | 2024-08-28 | 2024-06-06 | 2024-09-19 | 2025-07-14 | [5 empty] | 2024-09-24 | 2024-10-31 | n/a | n/a | 2025-05-02 | 2025-05-28 | 2024-09-20 | 2024-12-20 | 2024-09-30 |  | 2024-10-17 | 2024-11-05 | [10 empty] | No | [14 empty] | No | [21 empty] | 2023-12-20 | [47 empty] | - | [7 empty] | - | [25 empty] | Elise
1004 | 02 | 1004-02 | 1288 | PWA | - | #13 | Perserverance Road | Tea Tree Gully | Lot 2 | #13 Perserverance Road, Tea Tree Gully (Lot 2) | 2024-12-31 | 2024-03-30 |  | Retail | Jarrad Martin Hawkins | 22/06 - To be logged for PA | Marie | Brenton G | TBC | No | 1 | 0 | 1 | 2022-06-01 | 2022-07-25 | 2022-07-07 | 3000 |  | Yes | 2022-07-25 | 2022-07-25 |  |  | 2024-01-16 | 2022-07-25 | 2022-08-04 | 2024-11-04 | 2024-12-20 | 2023-01-16 | 2023-01-17 | 2024-08-28 | 2024-06-06 | 2024-09-19 | 2025-07-14 | [5 empty] | 2024-09-24 | 2024-10-31 | n/a | n/a | 2025-05-02 | 2025-05-28 | 2024-09-20 | 2024-12-20 | 2024-09-30 |  | 2024-10-17 | 2024-11-05 | [10 empty] | No | [14 empty] | No | [21 empty] | 2023-12-20 | [47 empty] | - | [7 empty] | - | [25 empty] | Elise
1004 | 03 | 1004-03 | 1288 | PWA | - | #13 | Perserverance Road | Tea Tree Gully | Lot 3 | #13 Perserverance Road, Tea Tree Gully (Lot 3) | 2024-12-31 | 2024-03-30 |  | Retail | Jarrad Martin Hawkins | 22/06 - To be logged for PA | Marie | Brenton G | TBC | No | 1 | 0 | 1 | 2022-06-01 | 2022-07-25 | 2022-07-07 | 3000 |  | Yes | 2022-07-25 | 2022-07-25 |  |  | 2024-01-16 | 2022-07-25 | 2022-08-04 | 2024-11-04 | 2024-12-20 | 2023-01-16 | 2023-01-17 | 2024-08-28 | 2024-06-06 | 2024-09-12 | 2025-07-14 | [5 empty] | 2024-09-24 | 2024-10-31 | n/a | n/a | 2025-05-02 | 2025-05-28 | 2024-09-20 | 2024-12-20 | 2024-09-30 |  | 2024-10-17 | 2024-11-05 | [10 empty] | No | [14 empty] | No | [21 empty] | 2023-12-20 | [47 empty] | - | [7 empty] | - | [25 empty] | Elise
1005 | 01 | 1005-01 | 1216 - D3 | PWA | Cancelling | #30 | Luprena Avenue | Ingle Farm | Lot 3 | #30 Luprena Avenue, Ingle Farm (Lot 3) | 2024-03-31 | 2024-05-01 |  | Developer | Michelle & Peter Macfarlane |  |  | Brenton G | Teo | No | 1 | 0 | 1 | 2022-03-08 | 2022-03-09 | 2022-03-09 | 3000 |  | Yes | 2022-03-21 | 2022-03-25 |  |  |  | 2022-03-28 | 2022-05-11 |  |  | 2022-04-14 | 2022-07-19 | [9 empty] | 2022-07-08 | 2022-07-30 | [6 empty] | 2022-08-04 | 2022-12-13 | 2022-09-30 | 2022-12-06 | 2023-02-13 | 2023-02-23 | [8 empty] | No | [14 empty] | No | [69 empty] | - | [7 empty] | - | [12 empty] | W/ GB 2nd Round | [12 empty] | Elise
1005 | 02 | 1005-02 | 1216 - D2 | PWA | Cancelling | #30 | Luprena Avenue | Ingle Farm | Lot 2 | #30 Luprena Avenue, Ingle Farm (Lot 2) | 2024-03-31 | 2024-05-01 |  | Developer | Michelle & Peter Macfarlane |  |  | Brenton G | Teo | No | 1 | 0 | 1 | 2022-03-08 | 2022-03-09 | 2022-03-09 | 3000 |  | Yes | 2022-03-21 | 2022-03-25 |  |  |  | 2022-03-28 | 2022-05-11 |  |  | 2022-04-14 | 2022-07-19 | [9 empty] | 2022-07-08 | 2022-07-30 | [6 empty] | 2022-08-04 | 2022-12-13 | 2022-09-30 | 2022-12-06 | 2023-02-13 | 2023-02-23 | [8 empty] | No | [14 empty] | No | [69 empty] | - | [7 empty] | - | [12 empty] | W/ GB 2nd Round | [12 empty] | Elise
1005 | 03 | 1005-03 | 1216 - D1 | PWA | Cancelling | #30 | Luprena Avenue | Ingle Farm | Lot 1 | #30 Luprena Avenue, Ingle Farm (Lot 1) | 2024-03-31 | 2024-05-01 |  | Developer | Michelle & Peter Macfarlane |  |  | Brenton G | Teo | No | 1 | 0 | 1 | 2022-03-08 | 2022-03-09 | 2022-03-09 | 3000 |  | Yes | 2022-03-21 | 2022-03-25 |  |  |  | 2022-03-28 | 2022-05-11 |  |  | 2022-04-14 | 2022-07-19 | [9 empty] | 2022-07-08 | 2022-07-30 | [6 empty] | 2022-08-04 | 2022-12-13 | 2022-09-30 | 2022-12-06 | 2023-02-13 | 2023-02-23 | [8 empty] | No | [14 empty] | No | [69 empty] | - | [7 empty] | - | [12 empty] | W/ GB 2nd Round | [12 empty] | Elise
1006 | 01 | 1006-01 | 1197 - D3 | PWA | Cancelling | #1 | Waninga Drive | Holden Hill |  | #1 Waninga Drive, Holden Hill SA 5088 | 2023-06-30 |  |  | Developer | Pavitar Dhillon |  |  | Michael B | Tom Sando | No | 1 |  | 1 | 2022-02-16 | 2022-03-24 | 2022-02-21 | 3000 |  | Yes | 2022-02-22 | 2022-03-04 |  |  |  | 2022-02-22 | 2022-02-22 | 2022-03-01 | 2022-03-31 | 2022-03-07 | 2022-06-01 |  |  |  | 2022-10-17 | 2022-10-19 |  |  |  |  | 2022-03-25 | 2022-04-05 |  |  |  |  | 2022-06-22 | 2022-06-29 | 2022-04-13 | 2022-10-27 | 2022-05-18 | 2022-06-14 | 2022-10-20 | 2023-11-20 | [8 empty] | No | [14 empty] | No | [90 empty] | waiting on GB first round | [12 empty] | Elise
1006 | 02 | 1006-02 | 1197 - D2 | PWA | Cancelling | #1 | Waninga Drive | Holden Hill |  | #1 Waninga Drive, Holden Hill SA 5088 |  |  |  | Developer | [14 empty] | Yes | 2022-02-22 | 2022-03-04 |  |  |  | 2022-02-22 | 2022-02-22 | 2022-03-01 | 2022-03-31 | 2022-03-07 | 2022-06-01 |  |  |  | 2002-10-17 | 2022-10-19 |  |  |  |  | 2022-03-25 | 2022-04-05 |  |  |  |  | 2022-06-22 | 2022-06-29 | 2022-04-13 | 2022-10-27 | 2022-05-18 | 2022-06-14 | 2022-10-20 | 2023-11-20 | [8 empty] | No | [14 empty] | No | [90 empty] | waiting on GB first round | [12 empty] | Elise
1006 | 03 | 1006-03 | 1197 - D1 | PWA | Cancelling | #1 | Waninga Drive | Holden Hill |  | #1 Waninga Drive, Holden Hill SA 5088 |  |  |  | Developer | [14 empty] | Yes | 2022-02-22 | 2022-03-04 |  |  |  | 2022-02-22 | 2022-02-22 | 2022-03-01 | 2022-03-31 | 2022-03-07 | 2022-06-01 |  |  |  | 2022-10-17 | 2022-10-19 |  |  |  |  | 2022-03-25 | 2022-04-05 |  |  |  |  | 2022-06-22 | 2022-06-29 | 2022-04-13 | 2022-10-27 | 2022-05-18 | 2022-06-14 | 2022-10-20 | 2023-11-20 | [8 empty] | No | [14 empty] | No | [38 empty] | Yes | [51 empty] | waiting on GB first round | [12 empty] | Elise
1007 | 01 | 1007-01 | 1126 - D9 | PWA | Cancelling | #13 | Hunt Crescent | Christies Beach | Lot 9 | #13 Hunt Crescent, Christies Beach (Lot 9) | 2024-03-31 | 2024-05-01 |  | Developer | 13-15 Hunt Crescent Pty Ltd |  |  | Brenton G | Steve Hall | Yes | 0 | 1 | 1 | 2022-12-02 | 2021-12-07 | 2021-12-23 | 2083.33 |  | Yes | 2021-11-08 | 2022-09-13 |  |  |  | 2022-01-10 | 2022-01-20 | 2022-01-18 | 2022-02-09 | 2021-12-02 | 2022-12-13 |  |  |  | 2023-09-25 | [5 empty] | 2022-01-20 | 2022-02-24 | 2023-09-25 |  | 2022-10-20 | 2022-11-18 | 2023-09-12 | 2023-09-25 | 2022-03-01 | 2023-07-06 | 2023-05-05 | 2023-07-29 | 2023-05-29 | 2023-07-07 | [8 empty] | No | [14 empty] | No | [69 empty] | - | [7 empty] | - | [25 empty] | Elise
1007 | 02 | 1007-02 | 1126 - D8 | PWA | Cancelling | #13 | Hunt Crescent | Christies Beach | Lot 8 | #13 Hunt Crescent, Christies Beach (Lot 8) | 2024-03-31 | 2024-05-01 |  | Developer | 13-15 Hunt Crescent Pty Ltd |  |  | Brenton G | Steve Hall | Yes | 0 | 1 | 1 | 2022-12-02 | 2021-12-07 | 2021-12-23 | 2083.33 |  | Yes | 2021-11-08 | 2022-09-13 |  |  |  | 2022-01-10 | 2022-01-20 | 2022-01-18 | 2022-02-09 | 2021-12-02 | 2022-12-13 |  |  |  | 2023-09-25 | [5 empty] | 2022-01-20 | 2022-02-24 | 2023-09-25 |  | 2022-10-20 | 2022-11-18 | 2023-09-12 | 2023-09-25 | 2022-03-01 | 2023-07-06 | 2023-05-05 | 2023-07-29 | 2023-05-29 | 2023-07-07 | [8 empty] | No | [14 empty] | No | [69 empty] | - | [7 empty] | - | [25 empty] | Elise
1007 | 03 | 1007-03 | 1126 - D7 | PWA | Cancelling | #13 | Hunt Crescent | Christies Beach | Lot 7 | #13 Hunt Crescent, Christies Beach (Lot 7) | 2024-03-31 | 2024-05-01 |  | Developer | 13-15 Hunt Crescent Pty Ltd |  |  | Brenton G | Steve Hall | Yes | 0 | 1 | 1 | 2022-12-02 | 2021-12-07 | 2021-12-23 | 2083.33 |  | Yes | 2021-11-08 | 2022-09-13 |  |  |  | 2022-01-10 | 2022-01-20 | 2022-01-18 | 2022-02-09 | 2021-12-02 | 2022-12-13 |  |  |  | 2023-09-25 | [5 empty] | 2022-01-20 | 2022-02-24 | 2023-09-25 | 2023-10-04 | 2022-10-20 | 2022-11-18 | 2023-09-12 | 2023-09-25 | 2022-03-01 | 2023-07-06 | 2023-05-05 | 2023-07-29 | 2023-05-29 | 2023-07-07 | [8 empty] | No | [14 empty] | No | [69 empty] | - | [7 empty] | - | [25 empty] | Elise
1007 | 04 | 1007-04 | 1126 - D6 | PWA | Cancelling | #13 | Hunt Crescent | Christies Beach | Lot 6 | #13 Hunt Crescent, Christies Beach (Lot 6) | 2024-03-31 | 2024-05-01 |  | Developer | 13-15 Hunt Crescent Pty Ltd |  |  | Brenton G | Steve Hall | Yes | 0 | 1 | 1 | 2022-12-02 | 2021-12-07 | 2021-12-23 | 2083.33 |  | Yes | 2021-11-08 | 2022-09-13 |  |  |  | 2022-01-10 | 2022-01-20 | 2022-01-18 | 2022-02-09 | 2021-12-02 | 2022-12-13 |  |  |  | 2023-09-25 | [5 empty] | 2022-01-20 | 2022-02-24 | 2023-09-25 | 2023-10-04 | 2022-10-20 | 2022-11-18 | 2023-09-12 | 2023-09-25 | 2022-03-01 | 2023-07-06 | 2023-05-05 | 2023-07-29 | 2023-05-29 | 2023-07-07 | [8 empty] | No | [14 empty] | No | [69 empty] | - | [7 empty] | - | [25 empty] | Elise
1007 | 05 | 1007-05 | 1126 - D5 | PWA | Cancelling | #13 | Hunt Crescent | Christies Beach | Lot 5 | #13 Hunt Crescent, Christies Beach (Lot 5) | 2024-03-31 | 2024-05-01 |  | Developer | 13-15 Hunt Crescent Pty Ltd |  |  | Brenton G | Steve Hall | Yes | 0 | 1 | 1 | 2022-12-02 | 2021-12-07 | 2021-12-23 | 2083.33 |  | Yes | 2021-11-08 | 2022-09-13 |  |  |  | 2022-01-10 | 2022-01-20 | 2022-01-18 | 2022-02-09 | 2021-12-02 | 2022-12-13 |  |  |  | 2023-09-25 | [5 empty] | 2022-01-20 | 2022-02-24 | 2023-09-25 | 2023-10-04 | 2022-10-20 | 2022-11-18 | 2023-09-12 | 2023-09-25 | 2022-03-01 | 2023-07-06 | 2023-05-05 | 2023-07-29 | 2023-05-29 | 2023-07-07 | [8 empty] | No | [14 empty] | No | [69 empty] | - | [7 empty] | - | [25 empty] | Elise
1007 | 06 | 1007-06 | 1126 - D4 | PWA | Cancelling | #13 | Hunt Crescent | Christies Beach | Lot 4 | #13 Hunt Crescent, Christies Beach (Lot 4) | 2024-03-31 | 2024-05-01 |  | Developer | 13-15 Hunt Crescent Pty Ltd |  |  | Brenton G | Steve Hall | Yes | 0 | 1 | 1 | 2022-12-02 | 2021-12-07 | 2021-12-23 | 2083.33 |  | Yes | 2021-11-08 | 2022-09-13 |  |  |  | 2022-01-10 | 2022-01-20 | 2022-01-18 | 2022-02-09 | 2021-12-02 | 2022-12-13 |  |  |  | 2023-09-25 | [5 empty] | 2022-01-20 | 2022-02-24 | 2023-09-25 | 2023-10-04 | 2022-10-20 | 2022-11-18 | 2023-09-12 | 2023-09-25 | 2022-03-01 | 2023-07-06 | 2023-05-05 | 2023-07-29 | 2023-05-29 | 2023-07-07 | [8 empty] | No | [14 empty] | No | [69 empty] | - | [7 empty] | - | [25 empty] | Elise
1007 | 07 | 1007-07 | 1126 - D3 | PWA | Cancelling | #13 | Hunt Crescent | Christies Beach | Lot 3 | #13 Hunt Crescent, Christies Beach (Lot 3) | 2024-03-31 | 2024-05-01 |  | Developer | 13-15 Hunt Crescent Pty Ltd |  |  | Brenton G | Steve Hall | Yes | 0 | 1 | 1 | 2022-12-02 | 2021-12-07 | 2021-12-23 | 2083.33 |  | Yes | 2021-11-08 | 2022-09-13 |  |  |  | 2022-01-10 | 2022-01-20 | 2022-01-18 | 2022-02-09 | 2021-12-02 | 2022-12-13 |  |  |  | 2023-09-25 | [5 empty] | 2022-01-20 | 2022-02-24 | 2023-09-25 | 2023-10-04 | 2022-10-20 | 2022-11-18 | 2023-09-12 | 2023-09-25 | 2022-03-01 | 2023-07-06 | 2023-05-05 | 2023-07-29 | 2023-05-29 | 2023-07-07 | [8 empty] | No | [14 empty] | No | [69 empty] | - | [7 empty] | - | [25 empty] | Elise
1007 | 08 | 1007-08 | 1126 - D2 | PWA | Cancelling | #13 | Hunt Crescent | Christies Beach | Lot 2 | #13 Hunt Crescent, Christies Beach (Lot 2) | 2024-03-31 | 2024-05-01 |  | Developer | 13-15 Hunt Crescent Pty Ltd |  |  | Brenton G | Steve Hall | Yes | 0 | 1 | 1 | 2022-12-02 | 2021-12-07 | 2021-12-23 | 2083.33 |  | Yes | 2021-11-08 | 2022-09-13 |  |  |  | 2022-01-10 | 2022-01-20 | 2022-01-18 | 2022-02-09 | 2021-12-02 | 2022-12-13 |  |  |  | 2023-09-25 | [5 empty] | 2022-01-20 | 2022-02-24 | 2023-09-25 | 2023-10-04 | 2022-10-20 | 2022-11-18 | 2023-09-12 | 2023-09-25 | 2022-03-01 | 2023-07-06 | 2023-05-05 | 2023-07-29 | 2023-05-29 | 2023-07-07 | [8 empty] | No | [14 empty] | No | [69 empty] | - | [7 empty] | - | [25 empty] | Elise
1007 | 09 | 1007-09 | 1126 - D12 | PWA | Cancelling | #13 | Hunt Crescent | Christies Beach | Lot 12 | #13 Hunt Crescent, Christies Beach (Lot 12) | 2024-03-31 | 2024-05-01 |  | Developer | 13-15 Hunt Crescent Pty Ltd |  |  | Brenton G | Steve Hall | Yes | 0 | 1 | 1 | 2022-12-02 | 2021-12-07 | 2021-12-23 | 2083.33 |  | Yes | 2021-11-08 | 2022-09-13 |  |  |  | 2022-01-10 | 2022-01-20 | 2022-01-18 | 2022-02-09 | 2021-12-02 | 2022-12-13 |  |  |  | 2023-09-25 | [5 empty] | 2022-01-20 | 2022-02-24 | 2023-09-25 | 2023-10-04 | 2022-10-20 | 2022-11-18 | 2023-09-12 | 2023-09-25 | 2022-03-01 | 2023-07-06 | 2023-05-05 | 2023-07-29 | 2023-05-29 | 2023-07-07 | [8 empty] | No | [14 empty] | No | [69 empty] | - | [7 empty] | - | [25 empty] | Elise
1007 | 10 | 1007-10 | 1126 - D11 | PWA | Cancelling | #13 | Hunt Crescent | Christies Beach | Lot 11 | #13 Hunt Crescent, Christies Beach (Lot 11) | 2024-03-31 | 2024-05-01 |  | Developer | 13-15 Hunt Crescent Pty Ltd |  |  | Brenton G | Steve Hall | Yes | 0 | 1 | 1 | 2022-12-02 | 2021-12-07 | 2021-12-23 | 2083.33 |  | Yes | 2021-11-08 | 2022-09-13 |  |  |  | 2022-01-10 | 2022-01-20 | 2022-01-18 | 2022-02-09 | 2021-12-02 | 2022-12-13 |  |  |  | 2023-09-25 | [5 empty] | 2022-01-20 | 2022-02-24 | 2023-09-25 | 2023-10-04 | 2022-10-20 | 2022-11-18 | 2023-09-12 | 2023-09-25 | 2022-03-01 | 2023-07-06 | 2023-05-05 | 2023-07-29 | 2023-05-29 | 2023-07-07 | [8 empty] | No | [14 empty] | No | [69 empty] | - | [7 empty] | - | [25 empty] | Elise
1007 | 11 | 1007-11 | 1126 - D10 | PWA | Cancelling | #13 | Hunt Crescent | Christies Beach | Lot 10 | #13 Hunt Crescent, Christies Beach (Lot 10) | 2024-03-31 | 2024-05-01 |  | Developer | 13-15 Hunt Crescent Pty Ltd |  |  | Brenton G | Steve Hall | Yes | 0 | 1 | 1 | 2022-12-02 | 2021-12-07 | 2021-12-23 | 2083.33 |  | Yes | 2021-11-08 | 2022-09-13 |  |  |  | 2022-01-10 | 2022-01-20 | 2022-01-18 | 2022-02-09 | 2021-12-02 | 2022-12-13 |  |  |  | 2023-09-25 | [5 empty] | 2022-01-20 | 2022-02-24 | 2023-09-25 | 2023-10-04 | 2022-10-20 | 2022-11-18 | 2023-09-12 | 2023-09-25 | 2022-03-01 | 2023-07-06 | 2023-05-05 | 2023-07-29 | 2023-05-29 | 2023-07-07 | [8 empty] | No | [14 empty] | No | [69 empty] | - | [7 empty] | - | [25 empty] | Elise
1007 | 12 | 1007-12 | 1126 - D1 | PWA | Cancelling | #13 | Hunt Crescent | Christies Beach | Lot 1 | #13 Hunt Crescent, Christies Beach (Lot 1) | 2024-03-31 | 2024-05-01 |  | Developer | 13-15 Hunt Crescent Pty Ltd |  |  | Brenton G | Steve Hall | Yes | 0 | 1 | 1 | 2022-12-02 | 2021-12-07 | 2021-12-23 | 2083.33 |  | Yes | 2021-11-08 | 2022-09-13 |  |  |  | 2022-01-10 | 2022-01-20 | 2022-01-18 | 2022-02-09 | 2021-12-02 | 2022-12-13 |  |  |  | 2023-09-25 | [5 empty] | 2022-01-20 | 2022-02-24 | 2023-09-25 | 2023-10-04 | 2022-10-20 | 2022-11-18 | 2023-09-12 | 2023-09-25 | 2022-03-01 | 2023-07-06 | 2023-05-05 | 2023-07-29 | 2023-05-29 | 2023-07-07 | [8 empty] | No | [14 empty] | No | [69 empty] | - | [7 empty] | - | [25 empty] | Elise
1008 | 01 | 1008-01 | 1426 | PWA | Cancelling | 5 | A Dennis Crescent | Para Hills |  | 5A Dennis Crescent, Para Hills | 2024-04-30 | 2024-05-01 |  | Retail | Mirza Ali | 3/4/24 - no response | Amy | Paul | TBC | No | 0 | 1 | 1 | 2023-06-01 | 2023-06-05 | 2023-06-07 | 3000 |  | Yes | 2023-06-13 | 2023-06-22 | 2023-07-19 | 2023-07-21 | 2023-07-31 | 2023-06-13 | 2023-07-05 | 2023-06-13 |  | 2023-07-31 | 2023-08-04 | 2023-09-07 | 2023-09-14 | 2023-10-16 | 2023-10-16 | 2023-10-17 |  | 2023-10-17 |  | 2023-10-19 | 2023-10-16 | 2023-11-02 |  |  |  |  | 2023-10-16 | 2023-11-02 | 2023-11-02 | 2023-11-10 |  |  | 2023-11-13 | 2023-11-22 | 2023-12-12 | [7 empty] | No | 2023-03-29 | [13 empty] | No | [16 empty] | Timber | [52 empty] | - | [7 empty] | - | [25 empty] | Vicki
1009 | 01 | 1009-01 | 1399 | PWA | In Doubt | #78 | Queen Street | Norwood |  | #78 Queen Street, Norwood | 2024-02-29 | 2024-04-01 |  | Developer | Annemarie & Premjeet Dhillon | Technical Arugment re Tree | Masha | Brenton G |  |  | 0 | 1 | 1 | 2023-03-24 | 2023-04-21 | 45041 | 1908-03-18 |  | Yes | 2023-04-24 | 2023-04-27 |  |  | 2023-04-28 | 2023-04-27 | 2023-05-11 | 2023-04-27 | 2023-05-11 | 2023-06-02 | 2023-06-07 | 2023-07-19 | 2023-07-26 |  | 2023-07-18 | 2023-07-25 | 2023-07-25 | 2023-07-25 |  |  | 2023-05-11 | 2023-05-29 | 2023-07-18 | 2023-07-19 | 2023-07-19 | 2023-07-24 | 2023-05-11 | 2023-05-29 | 2023-07-18 |  | 2023-07-19 | [43 empty] | Timber | [8 empty] | N/A | N/A | [42 empty] | - | [7 empty] | - | [25 empty] | Elise
1009 | 02 | 1009-02 | 1399 | PWA | In Doubt | #78 | Queen Street | Norwood |  | #78 Queen Street, Norwood | 2024-02-29 | 2024-04-01 |  | Developer | Annemarie & Premjeet Dhillon | Arborist report back for review and amend | Masha | Brenton G |  |  | 0 | 1 | 1 | 2023-03-24 | 2023-04-21 | 45041 | 1908-03-18 |  | Yes | 2023-04-24 | 2023-04-27 |  |  | 2023-04-28 | 2023-04-27 | 2023-05-11 | 2023-04-27 | 2023-05-11 | 2023-06-02 | 2023-06-07 | 2023-07-19 | 2023-07-26 |  | 2023-07-18 | 2023-07-25 | 2023-07-25 | 2023-07-25 |  |  | 2023-05-11 | 2023-05-29 | 2023-07-18 | 2023-07-19 | 2023-07-19 | 2023-07-24 | 2023-05-11 | 2023-05-29 | 2023-07-18 |  | 2023-07-19 | [43 empty] | Timber | [8 empty] | N/A | N/A | [42 empty] | - | [7 empty] | - | [25 empty] | Elise
1009 | 03 | 1009-03 | 1399 | PWA | In Doubt | 78 | Queen Street | Norwood |  | 78 Queen Street, Norwood | 2024-02-29 | 2024-04-30 |  | Developer | Annemarie & Premjeet Dhillon |  | Masha | Brenton G |  |  | 0 | 1 | 1 | 2023-03-24 | 2023-04-21 | 45041 | 1900-10-26 |  | Yes | 2023-04-24 | 2023-04-27 |  |  | 2023-04-28 | 2023-04-27 | 2023-05-11 | 2023-04-27 | 2023-05-11 | 2023-06-02 | 2023-06-07 | 2023-07-19 | 2023-07-26 |  | 2023-07-18 | 2023-07-25 | 2023-07-25 | 2023-07-25 | [24 empty] | No | [14 empty] | No | [16 empty] | Timber | [8 empty] | N/A | N/A | [42 empty] | - | [7 empty] | - | [25 empty] | Elise
1010 | 01 | 1010-01 | 1382 | PWA | On Hold | 124 | Nelson Road | Valley View | Lot 1 | 124 Nelson Road, Valley View (Lot 1) | 2023-12-31 | 2024-01-30 |  | Developer | Daniel Giles and Mitchelle Trezise | 30/6 - Awaiting approval on concepts from client. ON HOLD | Marie | Brenton G |  |  | 1 | 0 | 1 | 2023-02-15 | 2023-02-16 | 2023-02-16 | 3000 |  | Yes | 2023-02-17 | 2023-02-20 | n/a | n/a | 2023-02-22 | 2023-02-16 | 2023-03-10 | 2023-09-24 | 2024-03-14 | 2023-03-14 | 2023-03-15 | 2023-08-11 | 2023-08-11 |  | 2023-05-05 | 2023-05-10 | 2023-05-10 | 2023-05-12 | 2023-05-12 | 2023-05-18 | 2023-03-21 | 2023-05-02 |  |  |  |  | 2023-04-21 | 2024-06-26 | 2023-05-04 | 2024-08-29 | 2023-06-06 | 2023-08-23 | 2024-06-05 | 2024-08-15 | [8 empty] | No | [14 empty] | No | [25 empty] | N/A | N/A | Phoebe | [41 empty] | - | [7 empty] | - | [25 empty] | Elise
1011 | 01 | 1011-01 | 1380 | PWA | In Doubt | 1a | Cootra Avenue | Parkside |  | 1a Cootra Avenue , Parkside | 2024-02-29 | 2024-04-01 |  | Retail | Mein Douglas | Client undecided if they wish to proced working with Brenton |  | Brenton G |  |  | 1 | 0 | 1 | 2023-02-07 | 2023-02-08 | 2023-02-09 | 3000 |  | Yes | 2023-03-03 | 2023-03-15 | 2023-04-28 |  | 2023-09-01 | 2023-03-03 | 2023-03-22 | 2023-03-03 | 2023-10-23 | 2023-09-05 | 2023-09-15 | 2023-09-21 | 2023-09-26 | 2023-09-28 | 2023-09-28 | 2023-10-03 |  |  |  |  | 2023-09-28 | 2023-10-23 |  |  |  |  | 2023-09-28 | 2023-10-23 | 2023-11-09 | 2024-04-26 | 2023-11-20 | 2024-04-26 | 2024-09-19 | [9 empty] | no | [40 empty] | N/A | N/A | [42 empty] | - | [7 empty] | - | [12 empty] | W/ GB 2nd Round | [12 empty] | Elise
1012 | 01 | 1012-01 | 1379 | PWA | In Doubt | 3 | Wallis Street | Parkside |  | 3 Wallis Street, Parkside | 2024-02-29 | 2024-04-01 |  | Retail | Mein Douglas | Going through Probate and Will be contested Client meeting 30/10 |  | Brenton G |  |  | 1 | 0 | 1 | 2023-02-07 | 2023-02-08 | 2023-02-09 | 3000 |  | Yes | 2023-03-03 | 2023-03-15 | 2023-04-28 |  | 2023-09-01 | 2023-03-03 | 2023-03-20 | 2023-03-03 | 2023-10-23 | 2023-09-05 | 2023-09-15 | 2023-09-21 | 2023-09-26 | 2023-09-28 | 2023-09-28 | 2023-10-03 |  |  |  |  | 2023-09-28 | 2023-10-23 |  |  |  |  | 2023-09-28 | 2023-10-23 | 2023-11-09 | 2024-04-26 | 2023-11-20 | 2024-04-26 | 2024-09-19 | [9 empty] | no | [40 empty] | N/A | N/A | [42 empty] | - | [7 empty] | - | [12 empty] | W/ GB 2nd Round | [12 empty] | Elise
1010 | 02 | 1010-02 | 1382 | PWA | On Hold | 124 | Nelson Road | Valley View | Lot 2 | 124 Nelson Road, Valley View (Lot 2) | 2023-12-31 | 2024-01-30 |  | Developer | Daniel Giles and Mitchelle Trezise | 17/6 - Awaiting approval on concepts from client | Marie | Brenton G |  |  | 1 | 0 | 1 | 2023-02-15 | 2023-02-16 | 2023-02-16 | 3000 |  | Yes | 2023-02-17 | 2023-02-20 | n/a | n/a | 2023-02-22 | 2023-02-16 | 2023-03-10 | 2023-09-24 | 2024-03-14 | 2023-03-14 | 2023-03-15 | 2023-08-11 | 2023-08-11 |  | 2023-05-05 | 2023-05-10 | 2023-05-10 | 2023-05-12 | 2023-05-12 | 2023-05-18 | 2023-03-21 | 2023-05-02 |  |  |  |  | 2023-04-21 | 2024-06-26 | 2023-05-04 | 2024-08-29 | 2023-06-06 | 2023-08-23 | 2024-06-05 | 2024-08-15 | [8 empty] | No | [14 empty] | No | [25 empty] | N/A | N/A | Phoebe | [41 empty] | - | [7 empty] | - | [25 empty] | Elise
1013 | 01 | 1013-01 | 1325 | PWA | Cancelling | #137 | Bradley Grove | Mitchell Park | Lot 300 | #137 Bradley Grove, Mitchell Park 5043 (Lot 300) | 2024-01-31 | 2024-03-01 |  | Retail | Christopher Edwards & Jennifer Edwards | *address update!! |  |  | Steve Hall | No | 0 | 1 | 1 | 2022-10-20 | 2022-10-20 | 2022-10-20 | 5000 |  | Yes | 2022-12-16 | 2022-12-16 | 2023-08-15 | 2023-08-16 |  | 2023-01-23 | 2023-02-09 | 2023-01-23 | 2023-04-17 | 2023-01-13 | 2023-02-14 | 2023-05-11 | 2023-05-17 | 2023-07-07 | 2023-04-17 | 2023-04-19 |  | 2023-06-08 |  | 2023-06-09 | 2023-04-11 | 2023-04-17 | 2023-04-17 | 2023-04-18 | 2023-05-17 |  | 2023-04-17 | 2023-04-28 | 2023-04-28 | 2023-06-05 | 2023-05-04 | 2023-05-29 | 2023-06-13 | 2023-06-15 | [8 empty] | No | [14 empty] | No | [103 empty] | Elise
1014 | 01 | 1014-01 | 1324 | PWA | Cancelling | #4a | Gangara Avenue | Warradale |  | #4a Gangara Avenue, Warradale | 2023-12-31 | 2024-01-30 |  | Retail | Barbara Puzio & Barry Pilkington | Travis to advise when to send contract |  | Paul | Paul C |  | 0 | 1 | 1 | 2022-10-19 | 2022-11-22 | 2022-11-22 | 5000 |  | Yes | 2022-12-21 | 2023-01-18 | 2023-02-23 | 2023-02-24 | 2023-03-30 | 2022-12-01 | 2022-12-16 | 2022-12-01 | 2023-06-22 | 2023-03-31 | 2023-04-14 | 2023-08-23 | 2023-08-28 | 2023-06-07 | 2023-06-07 | 2023-06-09 |  | 2023-06-09 |  | 2023-06-13 | 2023-06-07 | 2023-06-22 | 2023-06-22 | 2023-06-23 |  |  | 2023-06-07 | 2023-06-22 | 2023-06-23 | 2023-07-03 |  |  | 2023-07-28 | 2023-08-03 | [5 empty] | 2022-10-19 | N/A |  | No | [14 empty] | No | [69 empty] | - | [7 empty] | - | [25 empty] | Elise
1010 | 03 | 1010-03 | 1382 | PWA | On Hold | 124 | Nelson Road | Valley View | Lot 3 | 124 Nelson Road, Valley View (Lot 3) | 2023-12-31 | 2024-01-30 |  | Developer | Daniel Giles and Mitchelle Trezise | 17/6 - Awaiting approval on concepts from client | Marie | Brenton G |  |  | 1 | 0 | 1 | 2023-02-15 | 2023-02-16 | 2023-02-16 | 3000 |  | Yes | 2023-02-17 | 2023-02-20 | n/a | n/a | 2023-02-22 | 2023-02-16 | 2023-03-10 | 2023-09-24 | 2024-03-14 | 2023-03-14 | 2023-03-15 | 2023-08-11 | 2023-08-11 |  | 2023-05-05 | 2023-05-10 | 2023-05-10 | 2023-05-12 | 2023-05-12 | 2023-05-18 | 2023-03-21 | 2023-05-02 |  |  |  |  | 2023-04-21 | 2024-06-26 | 2023-05-04 | 2024-08-29 | 2023-06-06 | 2023-08-23 | 2024-06-05 | 2024-08-15 | [8 empty] | No | [14 empty] | No | [25 empty] | N/A | N/A | Phoebe | [41 empty] | - | [7 empty] | - | [25 empty] | Elise
1013 | 02 | 1013-02 | 1265 | PWA | Cancelling | #137 | Bradley Grove | Mitchell Park | Lot 301 | #137 Bradley Grove, Mitchell Park SA 5043 (Lot 301) | 2024-01-31 | 2024-03-01 |  | Retail | Yuki Akita | *06/10- logged for price re-check before proceeding |  | Paul | Steve Hall | No | 0 | 1 | 1 | 2022-06-08 | 2022-06-09 | 2022-06-09 | 5000 |  | Yes | 2022-09-29 | 2022-09-29 |  |  | 2022-09-29 | 2022-08-19 | 2022-09-07 | 2022-08-19 |  | 2022-12-20 | 2022-12-20 | 2023-09-06 | 2023-09-14 |  | 2023-01-13 | 2023-01-18 |  | 2023-01-18 |  | 2023-01-20 | 2023-01-12 | 2023-01-24 | 2023-02-06 | 2023-02-10 |  |  | 2023-01-12 | 2023-01-24 | 2023-02-13 | 2023-05-17 | 2023-03-01 | 2023-03-22 | 2023-05-26 | 2023-10-11 | [8 empty] | No | [14 empty] | No | [103 empty] | Vicki
1015 | 01 | 1015-01 | 1217 | PWA | Cancelling | #6 | Kareda Drive | Campbelltown | Lot 101 | #6 Kareda Drive, Campbelltown (Lot 101) | 2024-01-31 | 2024-03-01 |  | Retail | Emma Louise Frewin | *04/07 PD sent to client to sign |  |  | Teo |  | 0 | 1 | 1 | 2022-03-16 | 2022-03-17 | 2022-03-17 | 5000 |  | Yes | 2022-05-09 | 2022-05-16 |  |  | 2022-06-07 | 2022-05-09 | 2022-06-03 | 2022-05-09 |  | 2022-06-07 | 2022-06-20 | 2023-06-28 | 2023-07-04 | [26 empty] | 2022-03-16 | N/A |  | No | [14 empty] | No | [69 empty] | - | [7 empty] | - | [25 empty] | Elise
1016 | 01 | 1016-01 |  | PWA | Cancelling | #12 | Foster Avenue | Paradise | Lot 1 | #12 Foster Avenue, Paradise (Lot 1) |  |  |  | Developer | Sarah McInerney |  |  | Gary P | Tom Sando |  | 1 | 0 | 1 | 2020-03-15 | 2020-03-16 | 2020-03-16 | 2500 |  | Yes | [9 empty] | 2020-04-07 | 2020-04-07 | [9 empty] | 2020-04-15 | [7 empty] | 2020-04-17 | 2020-04-20 | [12 empty] | No | 2021-09-06 | [13 empty] | No | [69 empty] | - | [7 empty] | - | [25 empty] | Vicki
1016 | 02 | 1016-02 |  | PWA | Cancelling | #12 | Foster Avenue | Paradise | Lot 2 | #12 Foster Avenue, Paradise (Lot 2) |  |  |  | Developer | Sarah McInerney |  |  | Gary P | Tom Sando |  | 1 | 0 | 1 | 2020-03-15 | 2020-03-16 | 2020-03-16 | 2500 |  | Yes | [9 empty] | 2020-04-07 | 2020-04-07 | [9 empty] | 2020-04-15 | [7 empty] | 2020-04-17 | 2020-04-20 | [12 empty] | No | 2021-09-06 | [13 empty] | No | [69 empty] | - | [7 empty] | - | [25 empty] | Vicki
1007 | 13 | 1007-13 | 1126 | PWA | Cancelling | #13 | Hunt Crescent | Christies Beach | CA | #13 Hunt Crescent, Christies Beach (CA) | 2024-03-31 | 2024-05-01 |  | Developer | 13-15 Hunt Crescent Pty Ltd |  |  | Brenton G | Steve Hall | Yes | 0 | 0 | 0 | 2022-12-02 | 2021-12-07 | 2021-12-23 | 0 |  | Yes | 2021-11-08 | 2022-09-13 |  |  |  | 2022-01-10 | 2022-01-20 | 2022-01-18 | 2022-02-09 | 2021-12-02 | 2022-12-13 | [9 empty] | 2022-01-20 | 2022-02-24 |  |  | 2022-10-20 | 2022-11-18 |  |  | 2022-03-01 | 2023-07-06 | 2023-05-05 | 2023-07-29 | 2023-05-29 | 2023-07-07 | [8 empty] | No | [14 empty] | No | [69 empty] | - | [7 empty] | - | [25 empty] | Elise
1017 | 01 | 1017-01 | 1005 | PWA | Cancelling | #187 | Portrush Road | Maylands | CA | #187 Portrush Road, Maylands (CA) | 2024-02-29 | 2024-04-01 |  | Developer | George Isaac |  |  | Brenton G |  | Yes | 0 | 0 | 0 | 2021-07-01 | 2021-07-01 | 2021-07-01 | 0 |  | Yes | 2021-08-24 | 2021-09-03 |  |  |  | 2021-07-06 | 2021-07-21 | 2021-07-21 | 2021-08-17 | 2021-09-14 | 2022-07-18 |  |  |  | 2022-02-07 | 2022-02-10 |  |  |  |  | 2021-09-30 | 2021-10-19 |  |  | 2022-06-10 | 2022-06-21 | 2022-02-07 | 2022-02-21 | 2021-10-19 | 2023-05-05 | 2021-11-29 | 2022-11-29 | 2023-12-15 | 2023-12-21 | 2024-03-13 | 2024-04-13 | 2024-04-13 | [5 empty] | No | [14 empty] | No | [69 empty] | - | [7 empty] | - | [12 empty] | W/ GB 2nd Round | [12 empty] | Elise
1018 | 01 | 1018-01 | 1455 | PWA | - | 200 | Oakden Avenue | Oakden |  | 200 Oakden Avenue, Oakden |  |  |  | Retail | Vedprakash Patel, Shruti Patel | 06/07 - Client in selections. stage 1 DA achieved**Sustainable Asset Property** Variation to Encumbrance and Planning achieved. Released to footings only. Received frames- Awaiting Stage 2 DA | Marie | Paul | TBC | No | 0 | 1 | 1 | 2024-05-13 | 2024-05-17 | 2024-05-27 | 5000 |  | Yes | 2024-03-18 | 2024-03-27 | 2024-07-09 | 2024-08-10 | 2024-09-24 | 2024-06-14 | 2024-10-22 | 2024-06-14 | 2025-01-15 | 2024-09-24 | 2024-10-03 |  |  | 2024-10-18 | 2024-10-03 | 2024-10-07 | 2024-10-09 | 2024-10-09 | 2024-10-09 | 2024-10-22 | 2024-10-03 | 2024-10-31 | n/a | n/a |  |  | 2024-10-03 | 2024-10-31 | 2024-09-16 | 2024-11-29 | 2024-09-29 | 2022-11-22 | 2024-12-18 |  |  |  | 2025-04-08 | [37 empty] | Steel | [10 empty] | Phoebe | Full Selections | [74 empty] | Elise
1019 | 01 | 1019-01 | 1457 | PWA | On Hold | 3 | Cannes Avenue | Grange | Single Storey | 3 Cannes Avenue, Grange - Single Storey |  |  |  | Developer | Mario Monteleone | 21/8 - Concepts sent to Brenton | Masha | Brenton G | TBC | No | 0 | 1 | 1899-12-31 | [5 empty] | Yes | 2024-05-21 | 2024-06-14 | 2024-07-17 | 2024-08-21 | [9 empty] | 1901-03-23 | [8 empty] | n/a | n/a | [50 empty] | Timber | [10 empty] | Phoebe | [75 empty] | Vicki
1019 | 02 | 1019-02 | 1458 | PWA | On Hold | 3 | Cannes Avenue | Grange | Double Storey | 3 Cannes Avenue, Grange - Double Storey |  |  |  | Developer | Mario Monteleone | 21/8 - Concepts sent to Brenton | Masha | Brenton G | TBC | No | 1 | 0:00 | 1899-12-31 | [5 empty] | Yes | 2024-05-21 | 2024-06-14 | 2024-07-17 | 2024-08-21 | [18 empty] | n/a | n/a | [61 empty] | Phoebe | [75 empty] | Vicki
1020 | 01 | 1020-01 | 1470 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot 10 | 84 -88 Greentree Blvd Paralowie - Lot 10 |  |  |  | Developer | Lofty Building Group | 16/06 - In for BRC/DA application. In selections | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [12 empty] | 2026-03-12 | 2026-04-07 | [7 empty] | 2026-04-14 | 2026-04-15 | [6 empty] | 2025-04-24 | 2026-05-21 | [11 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 02 | 1020-02 | 1471 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot 11 | 84 -88 Greentree Blvd Paralowie - Lot 11 |  |  |  | Developer | Lofty Building Group | 16/06 - In for BRC/DA application. Selections completed | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [13 empty] | 2026-02-20 | [7 empty] | 2026-03-13 | 2026-03-18 | [6 empty] | 2025-04-24 | 2026-05-21 | [11 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 03 | 1020-03 | 1472 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot 12 | 84 -88 Greentree Blvd Paralowie - Lot 12 |  |  |  | Developer | Lofty Building Group | 16/06 - In for BRC/DA application. Selections completed | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [12 empty] | 2026-03-12 | 2016-03-19 | [7 empty] | 2026-04-14 | 2026-04-15 | [6 empty] | 2025-04-24 | 2026-05-21 | [11 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 04 | 1020-04 | 1473 | PWA | on Hold | 84-88 | Greentree Blvd | Paralowie | Lot 13 | 84 -88 Greentree Blvd Paralowie - Lot 13 |  |  |  | Developer | Lofty Building Group | On market | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [42 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 05 | 1020-05 | 1474 | PWA | on Hold | 84-88 | Greentree Blvd | Paralowie | Lot 14 | 84 -88 Greentree Blvd Paralowie - Lot 14 |  |  |  | Developer | Lofty Building Group | On market | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [42 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 06 | 1020-06 | 1475 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot 15 | 84 -88 Greentree Blvd Paralowie - Lot 15 |  |  |  | Developer | Lofty Building Group | 16/06 - Awaiting Frames for BRC/DA application. In selections | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [13 empty] | 2026-02-25 | [7 empty] | 2026-03-13 | 2026-03-18 | [6 empty] | 2025-04-24 | 2026-06-02 | [11 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 07 | 1020-07 | 1476 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot 16 | 84 -88 Greentree Blvd Paralowie - Lot 16 |  |  |  | Developer | Usman Ahmed and Samia Sumbal | 16/06 - Awaiting Frames for BRC/DA application. Selections completed | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [13 empty] | 2026-02-25 | [7 empty] | 2026-03-13 | 2026-03-18 | [6 empty] | 2025-04-24 | 2026-06-02 | [11 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 08 | 1020-08 | 1477 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot 17 | 84 -88 Greentree Blvd Paralowie - Lot 17 |  |  |  | Developer | Lofty Building Group | 16/06 - Awaiting Frames for BRC/DA application. In selections | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [12 empty] | 2026-03-12 | 2026-03-19 | [7 empty] | 2026-06-04 | [7 empty] | 2025-04-24 | 2026-06-02 | [11 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 09 | 1020-09 | 1478 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot 18 | 84 -88 Greentree Blvd Paralowie - Lot 18 |  |  |  | Developer | Lofty Building Group | 16/06 - Awaiting Frames and FCR for BRC/DA application. In Selections | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [12 empty] | 2026-04-17 | 2026-05-27 | [7 empty] | 2026-06-04 | [7 empty] | 2026-05-27 | 2026-06-03 | [11 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 10 | 1020-10 | 1479 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot 19 | 84 -88 Greentree Blvd Paralowie - Lot 19 |  |  |  | Developer | Lofty Building Group | 16/06 - Awaiting Frames for BRC/DA application. selections completed | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [12 empty] | 2026-04-01 | 2026-04-07 | [7 empty] | 2026-04-14 | 2026-04-15 | [6 empty] | 2025-04-24 | 2026-06-02 | [11 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 11 | 1020-11 | 1480 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot 20 | 84 -88 Greentree Blvd Paralowie - Lot 20 |  |  |  | Developer | Lofty Building Group | 16/06 - Awaiting Frames for BRC/DA application. selections completed | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [12 empty] | 2026-03-03 | 2026-03-04 | [7 empty] | 2026-03-13 | 2026-03-18 | [6 empty] | 2025-04-24 | 2026-06-02 | [11 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 12 | 1020-12 | 1481 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot 21 | 84 -88 Greentree Blvd Paralowie - Lot 21 |  |  |  | Developer | Lofty Building Group | 16/06 - Awaiting Frames for BRC/DA application. In selections | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [12 empty] | 2026-03-23 | 2026-04-10 | [7 empty] | 2026-04-14 | 2026-04-15 | [6 empty] | 2025-04-24 | 2026-05-25 | [11 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 13 | 1020-13 | 1482 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot 22 | 84 -88 Greentree Blvd Paralowie - Lot 22 |  |  |  | Developer | Lofty Building Group | 16/06 - Awaiting Frames for BRC/DA application. selections completed | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [12 empty] | 2026-03-13 | 2026-04-13 | [7 empty] | 2026-04-14 | 2026-04-15 | [6 empty] | 2025-04-24 | 2026-05-25 | [11 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 14 | 1020-14 | 1483 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot23 | 84 -88 Greentree Blvd Paralowie - Lot23 |  |  |  | Developer | Lofty Building Group | 16/06 - Awaiting Frames for BRC/DA application. selections completed | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [12 empty] | 2026-03-18 | 2026-04-13 | [7 empty] | 2026-04-14 | 2026-04-15 | [6 empty] | 2025-04-24 | 2026-05-25 | [11 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 15 | 1020-15 | 1484 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot24 | 84 -88 Greentree Blvd Paralowie - Lot24 |  |  |  | Developer | Lofty Building Group | 16/06 - In for WDs | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [42 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 16 | 1020-16 | 1485 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot25 | 84 -88 Greentree Blvd Paralowie - Lot25 |  |  |  | Developer | Lofty Building Group | 16/06 - Awaiting Frames for BRC/DA application. selections completed | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [12 empty] | 2026-03-12 | 2026-03-25 | [7 empty] | 2026-04-14 | 2026-04-15 | [6 empty] | 2026-05-13 | 2026-06-03 | [11 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 17 | 1020-17 | 1486 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot26 | 84 -88 Greentree Blvd Paralowie - Lot26 |  |  |  | Developer | Lofty Building Group | 16/06 - Awaiting Frames for BRC/DA application. In selections | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [42 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 18 | 1020-18 | 1487 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot27 | 84 -88 Greentree Blvd Paralowie - Lot27 |  |  |  | Developer | Lofty Building Group | 16/06 - Awaiting Frames and FCR for BRC/DA application. In Selections | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [12 empty] | 2026-04-17 | 2026-06-02 | [7 empty] | 2026-06-04 | [7 empty] | 2026-06-03 | [12 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 19 | 1020-19 | 1488 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot28 | 84 -88 Greentree Blvd Paralowie - Lot28 |  |  |  | Developer |  | 16/06 - WDs requested | Marie | Brenton G | TBC | [54 empty] | 2026-04-13 | [8 empty] | 2026-06-04 | [107 empty] | Elise
1020 | 20 | 1020-20 | 1489 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot29 | 84 -88 Greentree Blvd Paralowie - Lot29 |  |  |  | Developer | Lofty Building Group | 16/06 - WDs requested | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [42 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 21 | 1020-21 | 1490 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot30 | 84 -88 Greentree Blvd Paralowie - Lot30 |  |  |  | Developer | Lofty Building Group | 16/06 - Awaiting Frames and FCR for BRC/DA application. In Selections | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [13 empty] | 2026-05-29 | [7 empty] | 2026-06-04 | [7 empty] | 2026-06-03 | [12 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 22 | 1020-22 | 1491 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot31 | 84 -88 Greentree Blvd Paralowie - Lot31 |  |  |  | Developer | Lofty Building Group | 16/06 - Awaiting Frames and FCR for BRC/DA application. Selections completed | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [12 empty] | 2026-03-12 | 2026-03-17 | [7 empty] | 2026-04-14 | 2026-04-15 | [19 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 23 | 1020-23 | 1492 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot32 | 84 -88 Greentree Blvd Paralowie - Lot32 |  |  |  | Developer | Lofty Building Group | 16/06 - Awaiting Frames and FCR for BRC/DA application. Selections completed | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [12 empty] | 2026-03-12 | 2026-04-21 | [7 empty] | 2026-04-24 | 2026-04-28 | [19 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 24 | 1020-24 | 1493 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot33 | 84 -88 Greentree Blvd Paralowie - Lot33 |  |  |  | Developer | Lofty Building Group | 16/06 - Awaiting Frames and FCR for BRC/DA application. In Selections | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [12 empty] | 2026-05-19 | 2026-06-04 | [7 empty] | 2026-06-04 | [20 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 25 | 1020-25 | 1494 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot34 | 84 -88 Greentree Blvd Paralowie - Lot34 |  |  |  | Developer | Lofty Building Group | 16/06 - Awaiting Frames and FCR for BRC/DA application. In Selections | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [12 empty] | 2026-03-12 | 2026-04-21 | [7 empty] | 2026-04-24 | 2026-04-28 | [19 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 26 | 1020-26 | 1495 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot35 | 84 -88 Greentree Blvd Paralowie - Lot35 |  |  |  | Developer | Lofty Building Group | 16/06 - Awaiting Frames and FCR for BRC/DA application. In Selections | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [12 empty] | 2026-05-25 | [8 empty] | 2026-06-04 | [20 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 27 | 1020-27 | 1496 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot36 | 84 -88 Greentree Blvd Paralowie - Lot36 |  |  |  | Developer | Lofty Building Group | 16/06 - Awaiting Frames and FCR for BRC/DA application. In Selections | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [12 empty] | 2026-03-26 | 2026-05-28 | [7 empty] | 2026-06-04 | [20 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 28 | 1020-28 | 1497 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot37 | 84 -88 Greentree Blvd Paralowie - Lot37 |  |  |  | Developer | Lofty Building Group | 16/06 - Awaiting Frames and FCR for BRC/DA application. In Selections | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [13 empty] | 2026-05-28 | [7 empty] | 2026-06-04 | [20 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 29 | 1020-29 | 1498 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot38 | 84 -88 Greentree Blvd Paralowie - Lot38 |  |  |  | Developer | Lofty Building Group | 16/06 - WDs requested | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [42 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 30 | 1020-30 | 1499 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot39 | 84 -88 Greentree Blvd Paralowie - Lot39 |  |  |  | Developer | Lofty Building Group | 16/06 - Awaiting Frames for BRC/DA application. In selections | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [12 empty] | 2026-04-08 | 2026-05-28 | [7 empty] | 2026-06-04 | [7 empty] | 2026-06-03 | [12 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 31 | 1020-31 | 1500 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot40 | 84 -88 Greentree Blvd Paralowie - Lot40 |  |  |  | Developer | Lofty Building Group | 16/06 - Awaiting Frames and FCR for BRC/DA application. In Selections | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [12 empty] | 2026-05-27 | 2026-06-04 | [7 empty] | 2026-06-04 | [20 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 32 | 1020-32 | 1501 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot41 | 84 -88 Greentree Blvd Paralowie - Lot41 |  |  |  | Developer | Lofty Building Group | 16/06 - Awaiting Frames for BRC/DA application. In selections | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [12 empty] | 2026-03-20 | 2026-05-28 | [7 empty] | 2026-06-04 | [7 empty] | 2026-06-03 | [12 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 33 | 1020-33 | 1502 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot42 | 84 -88 Greentree Blvd Paralowie - Lot42 |  |  |  | Developer | Lofty Building Group | 16/06 - Awaiting Frames for BRC/DA application. In selections | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [12 empty] | 2026-05-19 | 2026-05-27 | [7 empty] | 2026-06-04 | [20 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 34 | 1020-34 | 1503 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot43 | 84 -88 Greentree Blvd Paralowie - Lot43 |  |  |  | Developer | Lofty Building Group | 16/06 - Awaiting Frames and FCR for BRC/DA application. In Selections | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [12 empty] | 2026-04-01 | 2026-05-27 | [7 empty] | 2026-06-04 | [20 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 35 | 1020-35 | 1504 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot44 | 84 -88 Greentree Blvd Paralowie - Lot44 |  |  |  | Developer | Lofty Building Group | 05/05 - Awaiting Frames and FCR for BRC/DA application. In selections | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [12 empty] | 2026-03-23 | 2026-04-29 | [7 empty] | 2026-06-04 | [7 empty] | 2026-05-13 | [12 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 36 | 1020-36 | 1505 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot45 | 84 -88 Greentree Blvd Paralowie - Lot45 |  |  |  | Developer | Lofty Building Group | 16/06 - Awaiting Frames for BRC/DA application. In selections | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [12 empty] | 2026-03-12 | 2026-04-13 | [7 empty] | 2026-04-14 | 2026-04-15 | [6 empty] | 2026-05-13 | [12 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 37 | 1020-37 | 1506 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot46 | 84 -88 Greentree Blvd Paralowie - Lot46 |  |  |  | Developer | Lofty Building Group | 16/06 - Awaiting Frames for BRC/DA application. Selections completed | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [12 empty] | 2026-03-26 | 2026-05-27 | [7 empty] | 2026-06-04 | [7 empty] | 2026-05-27 | [12 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 38 | 1020-38 | 1507 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot47 | 84 -88 Greentree Blvd Paralowie - Lot47 |  |  |  | Developer | Lofty Building Group | 16/06 - Awaiting Frames for BRC/DA application. Selections completed | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [12 empty] | 2026-03-12 | 2026-04-30 | [7 empty] | 2026-06-04 | [7 empty] | 2026-05-13 | [12 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 39 | 1020-39 | 1508 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot48 | 84 -88 Greentree Blvd Paralowie - Lot48 |  |  |  | Developer | Lofty Building Group | 16/06 - Awaiting Frames for BRC/DA application. Selections completed | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [12 empty] | 2026-03-12 | 2026-03-25 | [7 empty] | 2026-04-14 | 2026-04-15 | [6 empty] | 2026-05-13 | [12 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 40 | 1020-40 | 1509 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot49 | 84 -88 Greentree Blvd Paralowie - Lot49 |  |  |  | Developer | Lofty Building Group | 16/06 - Awaiting Frames for BRC/DA application. In selections | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [12 empty] | 2026-03-12 | 2026-03-05 | [7 empty] | 2026-03-13 | 2026-03-18 | [6 empty] | 2026-05-13 | [12 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 41 | 1020-41 | 1510 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot50 | 84 -88 Greentree Blvd Paralowie - Lot50 |  |  |  | Developer | Lofty Building Group | 16/06 - Awaiting Frames for BRC/DA application. Selections completed | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [12 empty] | 2026-04-08 | 2026-04-22 | [7 empty] | 2026-04-24 | 2026-04-28 | [6 empty] | 2026-05-13 | 2026-06-02 | [11 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 42 | 1020-42 | 1511 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot51 | 84 -88 Greentree Blvd Paralowie - Lot51 |  |  |  | Developer | Lofty Building Group | 16/06 - Awaiting Frames and FCR for BRC/DA application. In Selections | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [12 empty] | 2026-03-26 | 2026-05-28 | [7 empty] | 2026-06-04 | [20 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 43 | 1020-43 | 1512 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot52 | 84 -88 Greentree Blvd Paralowie - Lot52 |  |  |  | Developer | Lofty Building Group | 16/06 - Awaiting Frames and FCR for BRC/DA application. In Selections | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [13 empty] | 2026-05-28 | [7 empty] | 2026-06-04 | [20 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 44 | 1020-44 | 1513 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot53 | 84 -88 Greentree Blvd Paralowie - Lot53 |  |  |  | Developer | Lofty Building Group | 16/06 - Awaiting Frames and FCR for BRC/DA application. In Selections | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [12 empty] | 2026-06-01 | [29 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 45 | 1020-45 | 1514 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot54 | 84 -88 Greentree Blvd Paralowie - Lot54 |  |  |  | Developer | Lofty Building Group | 16/06 - Awaiting Frames and FCR for BRC/DA application. Selections completed | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [12 empty] | 2026-04-01 | 2026-05-27 | [7 empty] | 2026-06-04 | [20 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1020 | 46 | 1020-46 | 1515 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot55 | 84 -88 Greentree Blvd Paralowie - Lot55 |  |  |  | Developer | Lofty Building Group | 16/06 - Awaiting Frames for BRC/DA application. In selections | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [12 empty] | 2026-04-13 | 2026-04-22 | [7 empty] | 2026-04-24 | 2026-04-28 | [6 empty] | 2026-05-13 | 2026-06-02 | [11 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1021 | 01 | 1021-01 | 1516 | PWA | On Hold | 9 | Addison Ave | Marden |  | 9 Addison Ave, Marden |  |  |  | Retail | Guri & Simer Kang | ON HOLD UNTIL FURTHER NOTICE , likely 3months |  | Mitch G |  |  | 1 | 0 | 1 | 2024-05-23 | 2024-05-30 | 2024-05-30 | 5000 |  | Yes | 2023-09-22 | 2023-09-25 | 2024-06-17 | 2024-06-21 | 2024-07-04 | 2024-06-30 | 2024-07-11 | 2024-06-30 |  | 2024-07-05 | 2024-07-23 | [11 empty] | n/a | n/a | [137 empty] | Elise
1020 | 47 | 1020-47 | 1516 | PWA | - | 84-88 | Greentree Blvd | Paralowie | Lot56 | 84 -88 Greentree Blvd Paralowie - Lot56 |  |  |  | Developer | Lofty Building Group | 16/06 - VO with the client. WDS to be requested | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2024-05-06 | 2024-05-08 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  |  |  |  | 2024-07-22 | 2024-08-01 | 2024-09-25 | 2024-10-23 | 2024-10-24 | [8 empty] | n/a | n/a |  |  |  |  | 2024-08-23 | 2024-12-20 | 2024-09-03 | 2024-09-26 | [42 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | Scheme's | [74 empty] | Elise
1022 | 01 | 1022-01 | 1517 | PWA | Cancelling | 17 | Golding Street | Beverley | Lot 3 | 17 Golding Street Beverley Lot 3 |  |  |  | Developer | Lofty Building Group | RFD | Amy | Mitch G | TBC | No | 1 | 0 | 1 | 2024-08-29 | 2024-09-03 |  |  |  | Yes | 2024-05-21 | 2024-05-24 | 2024-06-18 | 2024-07-16 |  | 2024-06-12 | 2024-08-07 | 2024-08-29 | 2024-10-04 | 2024-06-18 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2024-08-08 | [6 empty] | 2024-06-11 | 2024-08-07 | n/a | n/a |  |  | 2024-04-30 | 2024-10-04 | 2024-08-07 |  | 2024-09-27 | [11 empty] | No | [14 empty] | No | [27 empty] | Phoebe | [75 empty] | Vicki
1023 | 01 | 1023-01 | 1528 | PWA | Cancelling | 3 | Daws Road | Mitchell Park | Lot 1 | 3 Daws Road, Mitchell Park - Lot 1 |  |  |  | Developer | Koteswara Rao Nalluri | BG to follow up client re signing of PWA - email and VM left | Masha | Brenton G | TBC | No | 1 | 0 | 1 | 2024-07-23 |  |  |  | Yes | Yes | [22 empty] | n/a | n/a | [38 empty] | 45679 | [22 empty] | Phoebe | Full Selections | [74 empty] | vicki
1023 | 02 | 1023-02 | 1528 | PWA | Cancelling | 3 | Daws Road | Mitchell Park | Lot 2 | 3 Daws Road, Mitchell Park - Lot 2 |  |  |  | Developer | Koteswara Rao Nalluri | Client overseas with family | Masha | Brenton G | TBC | No | 1 | 0 | 1 | 2024-07-23 |  |  |  | Yes | Yes | [22 empty] | n/a | n/a | [38 empty] | 45679 | [22 empty] | Phoebe | [75 empty] | vicki
1023 | 03 | 1023-03 | 1528 | PWA | Cancelling | 3 | Daws Road | Mitchell Park | Lot 3 | 3 Daws Road, Mitchell Park - Lot 3 |  |  |  | Developer | Koteswara Rao Nalluri | On Hold - per BG 7/08/2024 | Masha | Brenton G | TBC | No | 1 | 0 | 1 | 2024-07-23 |  |  |  | Yes | Yes | [22 empty] | n/a | n/a | [38 empty] | 45679 | [22 empty] | Phoebe | [75 empty] | vicki
1024 | 01 | 1024-01 | 1576 | PWA | - |  | Dankie Rd | Murray Bridge | Res 1 | Res 1 , Lot 311 (portion of lot 232) Dankie Rd, Murray Bridge |  |  |  | Developer | Lofty Building Group | 13/5 - Contract sent | Marie | Mitch G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a | Yes | Yes | 2024-09-09 | 2024-09-20 | n/a | n/a | 2024-09-20 | 2025-02-05 | 2025-02-21 | 2025-06-02 | 2025-07-10 | 2024-09-23 | 2024-09-26 | 2024-11-13 | 2024-11-25 | 2025-07-21 | 2025-07-21 | 2025-07-31 |  |  |  |  | 2025-02-05 | 2025-02-28 | n/a | n/a |  |  | 2025-06-04 | 2025-07-10 | 2024-09-26 | 2025-07-31 |  |  | 2025-07-31 | [11 empty] | 2025-07-31 | 2025-09-19 | [7 empty] | 2025-09-23 | 2025-09-29 | [6 empty] | 2025-09-23 | 2025-10-14 | [11 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | [75 empty] | Elise
1024 | 02 | 1024-02 | 1577 | PWA | - |  | Dankie Rd | Murray Bridge | Res 2 | Res 2 , Lot 310 (portion of lot 232) Dankie Rd, Murray Bridge |  |  |  | Developer | Lofty Building Group | 05/05 - WD update requested | Marie | Mitch G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a | Yes | Yes | 2024-09-09 | 2024-09-20 | n/a | n/a | 2024-09-20 | 2025-02-05 | 2025-02-21 | 2025-06-02 | 2025-07-10 | 2024-09-23 | 2024-09-26 | 2024-11-13 | 2024-11-25 | 2025-07-21 | 2025-07-21 | 2025-07-31 |  |  |  |  | 2025-02-05 | 2025-03-28 | n/a | n/a |  |  | 2025-06-04 | 2025-07-10 | 2024-09-26 | 2025-07-31 |  |  | 2025-07-31 | [12 empty] | 2025-09-19 | [7 empty] | 2025-09-23 | 2025-09-29 | [6 empty] | 2025-09-23 | 2025-10-14 | [11 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | [75 empty] | Elise
1024 | 03 | 1024-03 | 1578 | PWA | - |  | Dankie Rd | Murray Bridge | Res 3 | Res 3 , Lot 309 (portion of lot 232) Dankie Rd, Murray Bridge |  |  |  | Developer | Lofty Building Group | 05/05 - WD update requested | Marie | Mitch G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a | Yes | Yes | 2024-09-09 | 2024-09-20 | n/a | n/a | 2024-09-20 | 2025-02-05 | 2025-02-21 | 2025-06-02 | 2025-07-10 | 2024-09-23 | 2024-09-26 | 2024-11-13 | 2024-11-25 | 2025-07-21 | 2025-07-21 | 2025-07-31 |  |  |  |  | 2025-02-05 | 2025-03-28 | n/a | n/a |  |  | 2025-06-04 | 2025-07-10 | 2024-09-26 | 2025-07-31 |  |  | 2025-07-31 | [12 empty] | 2025-09-19 | [7 empty] | 2025-09-23 | 2025-09-29 | [6 empty] | 2025-09-23 | 2025-10-14 | [11 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | [75 empty] | Elise
1024 | 04 | 1024-04 | 1579 | PWA | - |  | Dankie Rd | Murray Bridge | Res 4 | Res 4 , Lot 308 (portion of lot 232) Dankie Rd, Murray Bridge |  |  |  | Developer | Lofty Building Group | 05/05 - WD update requested | [74 empty] | 2025-09-23 | 2025-10-14
1024 | 05 | 1024-05 | 1580 | PWA | - |  | Dankie Rd | Murray Bridge | Res 5 | Res 5 , Lot 307 (portion of lot 232) Dankie Rd, Murray Bridge |  |  |  | Developer | Lofty Building Group | 05/05 - WD update requested | [74 empty] | 2025-09-23 | 2025-10-14
1024 | 06 | 1024-06 | 1581 | PWA | - |  | Dankie Rd | Murray Bridge | Res 6 | Res 6 , Lot 306 (portion of lot 232) Dankie Rd, Murray Bridge |  |  |  | Developer | Lofty Building Group | 05/05 - WD update requested | Marie | Mitch G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a | Yes | Yes | 2024-09-09 | 2024-09-20 | n/a | n/a | 2024-09-20 | 2025-02-05 | 2025-02-21 | 2025-06-02 | 2025-07-10 | 2024-09-23 | 2024-09-26 | 2024-11-13 | 2024-11-25 | 2025-07-21 | 2025-07-21 | 2025-07-31 |  |  |  |  | 2025-02-05 | 2025-03-28 | n/a | n/a |  |  | 2025-06-04 | 2025-07-10 | 2024-09-26 | 2025-07-31 |  |  | 2025-07-31 | [12 empty] | 2025-09-19 | [7 empty] | 2025-09-23 | 2025-09-29 | [6 empty] | 2025-09-23 | 2025-10-14 | [11 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | [61 empty] | Yes | [13 empty] | Elise
1024 | 07 | 1024-07 | 1582 | PWA | - |  | Dankie Rd | Murray Bridge | Res 7 | Res 7 , Lot 305 (portion of lot 232) Dankie Rd, Murray Bridge |  |  |  | Developer | Lofty Building Group | 15/5 - Contract sent | Marie | Mitch G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a | Yes | Yes | 2024-09-09 | 2024-09-20 | n/a | n/a | 2024-09-20 | 2025-02-05 | 2025-02-21 | 2025-06-02 | 2025-07-10 | 2024-09-23 | 2024-09-26 | 2024-11-13 | 2024-11-25 | 2025-07-21 | 2025-07-21 | 2025-07-31 |  |  |  |  | 2025-02-05 | 2025-03-28 | n/a | n/a |  |  | 2025-06-04 | 2025-07-10 | 2024-09-26 | 2025-07-31 |  |  | 2025-07-31 | [12 empty] | 2025-09-19 | [7 empty] | 2025-09-23 | 2025-09-29 | [6 empty] | 2025-09-23 | 2025-10-14 | [11 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | [61 empty] | Yes | [13 empty] | Elise
1024 | 08 | 1024-08 | 1583 | PWA | - |  | Dankie Rd | Murray Bridge | Res 8 | Res 8 , Lot 304 (portion of lot 232) Dankie Rd, Murray Bridge |  |  |  | Developer | Lofty Building Group | 05/05 - WD update requested | Marie | Mitch G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a | Yes | Yes | 2024-09-09 | 2024-09-20 | n/a | n/a | 2024-09-20 | 2025-02-05 | 2025-02-21 | 2025-06-02 | 2025-07-10 | 2024-09-23 | 2024-09-26 | 2024-11-13 | 2024-11-25 | 2025-07-21 | 2025-07-21 | 2025-07-31 |  |  |  |  | 2025-02-05 | 2025-03-28 | n/a | n/a |  |  | 2025-06-04 | 2025-07-10 | 2024-09-26 | 2025-07-31 |  |  | 2025-07-31 | [12 empty] | 2025-09-19 | [7 empty] | 2025-09-23 | 2025-09-29 | [6 empty] | 2025-09-23 | 2025-10-14 | [11 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | [61 empty] | Yes | [13 empty] | Elise
1024 | 09 | 1024-09 | 1584 | PWA | - |  | Dankie Rd | Murray Bridge | Res 9 | Res 9 , Lot 303 (portion of lot 232) Dankie Rd, Murray Bridge |  |  |  | Developer | Lofty Building Group | 05/05 - WD update requested | Marie | Mitch G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a | Yes | Yes | 2024-09-09 | 2024-09-20 | n/a | n/a | 2024-09-20 | 2025-02-05 | 2025-02-21 | 2025-06-02 | 2025-07-10 | 2024-09-23 | 2024-09-26 | 2024-11-13 | 2024-11-25 | 2025-07-21 | 2025-07-21 | 2025-07-31 |  |  |  |  | 2025-02-05 | 2025-03-28 | n/a | n/a |  |  | 2025-06-04 | 2025-07-10 | 2024-09-26 | 2025-07-31 |  |  | 2025-07-31 | [12 empty] | 2025-09-19 | [7 empty] | 2025-09-23 | 2025-09-29 | [6 empty] | 2025-09-23 | 2025-10-14 | [11 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | [61 empty] | Yes | [13 empty] | Elise
1024 | 10 | 1024-10 | 1585 | PWA | - |  | Dankie Rd | Murray Bridge | Res 10 | Res 10 , Lot 302 (portion of lot 232) Dankie Rd, Murray Bridge |  |  |  | Developer | Lofty Building Group | 05/05 - WD update requested | Marie | Mitch G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a | Yes | Yes | 2024-09-09 | 2024-09-20 | n/a | n/a | 2024-09-20 | 2025-02-05 | 2025-02-21 | 2025-06-02 | 2025-07-10 | 2024-09-23 | 2024-09-26 | 2024-11-13 | 2024-11-25 | 2025-07-21 | 2025-07-21 | 2025-07-31 |  |  |  |  | 2025-02-05 | 2025-03-28 | n/a | n/a |  |  | 2025-06-04 | 2025-07-10 | 2024-09-26 | 2025-07-31 |  |  | 2025-07-31 | [12 empty] | 2025-09-19 | [7 empty] | 2025-09-23 | 2025-09-29 | [6 empty] | 2025-09-23 | 2025-10-14 | [11 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | [61 empty] | Yes | [13 empty] | Elise
1024 | 11 | 1024-11 | 1586 | PWA | - |  | Dankie Rd | Murray Bridge | Res 11 | Res 11 , Lot 301 (portion of lot 232) Dankie Rd, Murray Bridge |  |  |  | Developer | Lofty Building Group | 16/06 - Contract deposit requested | Marie | Mitch G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a | Yes | Yes | 2024-09-09 | 2024-09-20 | n/a | n/a | 2024-09-20 | 2025-02-05 | 2025-02-21 | 2025-06-02 | 2025-07-10 | 2024-09-23 | 2024-09-26 | 2024-11-13 | 2024-11-25 | 2025-07-21 | 2025-07-21 | 2025-07-31 |  |  |  |  | 2025-02-05 | 2025-03-28 | n/a | n/a |  |  | 2025-06-04 | 2025-07-10 | 2024-09-26 | 2025-07-31 |  |  | 2025-07-31 | [12 empty] | 2025-09-19 | [7 empty] | 2025-09-23 | 2025-09-29 | [6 empty] | 2025-09-23 | 2025-10-14 | [11 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | [61 empty] | Yes | [13 empty] | Elise
1024 | 12 | 1024-12 | 1587 | PWA | - |  | Dankie Rd | Murray Bridge | Res 12 | Res 12 , Lot 300 (portion of lot 232) Dankie Rd, Murray Bridge |  |  |  | Developer | Lofty Building Group | 05/05 - WD update requested | [74 empty] | 2025-09-23 | 2025-10-14
1024 | 13 | 1024-13 | 1588 | PWA | - |  | Dankie Rd | Murray Bridge | Res 13 | Res 13 , Lot 319 (portion of lot 232) Dankie Rd, Murray Bridge |  |  |  | Developer | Lofty Building Group | 05/05 - WD update requested | [74 empty] | 2025-09-23 | 2025-10-14
1024 | 14 | 1024-14 | 1589 | PWA | - |  | Dankie Rd | Murray Bridge | Res 14 | Res 14 , Lot 318 (portion of lot 232) Dankie Rd, Murray Bridge |  |  |  | Developer | Lofty Building Group | 12/01 - Received DA. ON MARKET | Marie | Mitch G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a | Yes | Yes | 2024-09-09 | 2024-09-20 | n/a | n/a | 2024-09-20 | 2025-02-05 | 2025-02-21 | 2025-06-02 | 2025-07-10 | 2024-09-23 | 2024-09-26 | 2024-11-13 | 2024-11-25 | 2025-07-21 | 2025-07-21 | 2025-07-31 |  |  |  |  | 2025-02-05 | 2025-03-28 | n/a | n/a |  |  | 2025-06-04 | 2025-07-10 | 2024-09-26 | 2025-07-31 |  |  | 2025-07-31 | [12 empty] | 2025-09-19 | [7 empty] | 2025-09-23 | 2025-09-29 | [6 empty] | 2025-09-23 | 2025-10-14 | [11 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | [61 empty] | Yes | [13 empty] | Elise
1024 | 15 | 1024-15 | 1590 | PWA | - |  | Dankie Rd | Murray Bridge | Res 15 | Res 15 , Lot 317 (portion of lot 232) Dankie Rd, Murray Bridge |  |  |  | Developer | Lofty Building Group | 12/01 - Received DA. ON MARKET | Marie | Mitch G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a | Yes | Yes | 2024-09-09 | 2024-09-20 | n/a | n/a | 2024-09-20 | 2025-02-05 | 2025-02-21 | 2025-06-02 | 2025-07-10 | 2024-09-23 | 2024-09-26 | 2024-11-13 | 2024-11-25 | 2025-07-21 | 2025-07-21 | 2025-07-31 |  |  |  |  | 2025-02-05 | 2025-03-28 | n/a | n/a |  |  | 2025-06-04 | 2025-07-10 | 2024-09-26 | 2025-07-31 |  |  | 2025-07-31 | [12 empty] | 2025-09-19 | [7 empty] | 2025-09-23 | 2025-09-29 | [6 empty] | 2025-09-23 | 2025-10-14 | [11 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | [61 empty] | Yes | [13 empty] | Elise
1024 | 16 | 1024-16 | 1591 | PWA | - |  | Dankie Rd | Murray Bridge | Res 16 | Res 16 , Lot 316 (portion of lot 232) Dankie Rd, Murray Bridge |  |  |  | Developer | Lofty Building Group | 12/01 - Received DA. ON MARKET | Marie | Mitch G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a | Yes | Yes | 2024-09-09 | 2024-09-20 | n/a | n/a | 2024-09-20 | 2025-02-05 | 2025-02-21 | 2025-06-02 | 2025-07-10 | 2024-09-23 | 2024-09-26 | 2024-11-13 | 2024-11-25 | 2025-07-21 | 2025-07-21 | 2025-07-31 |  |  |  |  | 2025-02-05 | 2025-03-28 | n/a | n/a |  |  | 2025-06-04 | 2025-07-10 | 2024-09-26 | 2025-07-31 |  |  | 2025-07-31 | [12 empty] | 2025-09-19 | [7 empty] | 2025-09-23 | 2025-09-29 | [6 empty] | 2025-09-23 | 2025-10-14 | [11 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | [61 empty] | Yes | [13 empty] | Elise
1024 | 17 | 1024-17 | 1592 | PWA | - |  | Dankie Rd | Murray Bridge | Res 17 | Res 17 , Lot 315 (portion of lot 232) Dankie Rd, Murray Bridge |  |  |  | Developer | Lofty Building Group | 05/05 - WD update requested | Marie | Mitch G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a | Yes | Yes | 2024-09-09 | 2024-09-20 | n/a | n/a | 2024-09-20 | 2025-02-05 | 2025-02-21 | 2025-06-02 | 2025-07-10 | 2024-09-23 | 2024-09-26 | 2024-11-13 | 2024-11-25 | 2025-07-21 | 2025-07-21 | 2025-07-31 |  |  |  |  | 2025-02-05 | 2025-03-28 | n/a | n/a |  |  | 2025-06-04 | 2025-07-10 | 2024-09-26 | 2025-07-31 |  |  | 2025-07-31 | [12 empty] | 2025-09-19 | [7 empty] | 2025-09-23 | 2025-09-29 | [6 empty] | 2025-09-23 | 2025-10-14 | [11 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | [60 empty] | Yes | [14 empty] | Elise
1024 | 18 | 1024-18 | 1593 | PWA | - |  | Dankie Rd | Murray Bridge | Res 18 | Res 18 , Lot 314 (portion of lot 232) Dankie Rd, Murray Bridge |  |  |  | Developer | Lofty Building Group | 12/01 - Received DA. ON MARKET | Marie | Mitch G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a | Yes | Yes | 2024-09-09 | 2024-09-20 | n/a | n/a | 2024-09-20 | 2025-02-05 | 2025-02-21 | 2025-06-02 | 2025-07-10 | 2024-09-23 | 2024-09-26 | 2024-11-13 | 2024-11-25 | 2025-07-21 | 2025-07-21 | 2025-07-31 |  |  |  |  | 2025-02-05 | 2025-03-28 | n/a | n/a |  |  | 2025-06-04 | 2025-07-10 | 2024-09-26 | 2025-07-31 |  |  | 2025-07-31 | [12 empty] | 2025-09-19 | [7 empty] | 2025-09-23 | 2025-09-29 | [6 empty] | 2025-09-23 | 2025-10-14 | [11 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | [60 empty] | Yes | [14 empty] | Elise
1024 | 19 | 1024-19 | 1594 | PWA | - |  | Dankie Rd | Murray Bridge | Res 19 | Res 19 , Lot 313 (portion of lot 232) Dankie Rd, Murray Bridge |  |  |  | Developer | Lofty Building Group | 16/06 - Contract sent | Marie | Mitch G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a | Yes | Yes | 2024-09-09 | 2024-09-20 | n/a | n/a | 2024-09-20 | 2025-02-05 | 2025-02-21 | 2025-06-02 | 2025-07-10 | 2024-09-23 | 2024-09-26 | 2024-11-13 | 2024-11-25 | 2025-07-21 | 2025-07-21 | 2025-07-31 |  |  |  |  | 2025-02-05 | 2025-03-28 | n/a | n/a |  |  | 2025-06-04 | 2025-07-10 | 2024-09-26 | 2025-07-31 |  |  | 2025-07-31 | [12 empty] | 2025-09-19 | [7 empty] | 2025-09-23 | 2025-09-29 | [6 empty] | 2025-09-23 | 2025-10-14 | [11 empty] | Steel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Phoebe | [60 empty] | Yes | [14 empty] | Elise
1024 | 20 | 1024-20 | 1595 | PWA | - |  | Dankie Rd | Murray Bridge | Res 20 | Res 20 , Lot 312 (portion of lot 232) Dankie Rd, Murray Bridge |  |  |  | Developer | Lofty Building Group | 05/05 - WD update requested | Marie | Mitch G | TBC | No | 1 | 0 | 1 | n/a | n/a |  | n/a | yes | yes | 2024-09-09 | 2024-09-20 |  |  | 2024-09-20 | 2025-02-05 | 2025-02-21 | 2025-06-02 | 2025-07-10 | 2024-09-23 | 2024-09-26 | 2024-11-13 | 2024-11-25 | 2025-07-21 | 2025-07-21 | 2025-07-31 |  |  |  |  | 2025-02-05 | 2025-03-28 |  |  |  |  | 2025-06-04 | 2025-07-10 | 2024-09-26 | 2025-07-31 |  |  | 2025-07-31 | [12 empty] | 2025-09-19 | [7 empty] | 2025-09-23 | 2025-09-29 | [6 empty] | 2025-09-23 | 2025-10-14 | [98 empty] | Elise
1025 | 01 | 1025-01 | 1597 | PWA | On Hold | 4-11/9 | Bald Street | Smithfield Plains | Res 1 | Res 1, 4-11/9 Bald Street, Smithfield Plains |  |  |  | Developer | Frank Cecere | 25/3 - Brenton chasing client to sign off on concept plans. Concept plans done Nov 2024. Full deposit not paid. | Marie | Brenton G | TBC | No | 0 | 1 | 1 | 2024-09-17 | 2024-09-18 |  | 3000 | Yes | Yes | 2024-08-20 | 2024-11-13 | [20 empty] | n/a | n/a |  |  |  |  | 2024-09-30 | [45 empty] | Steel | [10 empty] | Phoebe | [60 empty] | Yes | [14 empty] | Elise
1025 | 02 | 1025-02 | 1597 | PWA | On Hold | 4-11/9 | Bald Street | Smithfield Plains | Res 2 | Res 2, 4-11/9 Bald Street, Smithfield Plains |  |  |  | Developer | Frank Cecere | 25/3 - Brenton chasing client to sign off on concept plans. Concept plans done Nov 2024. Full deposit not paid 15/4 no update | Marie | Brenton G | TBC | No | 0 | 1 | 1 | 2024-09-17 | 2024-09-18 |  | 3000 | Yes | Yes | 2024-08-20 | 2024-11-13 | 2024-11-15 | 2024-11-15 | [18 empty] | n/a | n/a |  |  |  |  | 2024-09-30 | [56 empty] | Phoebe | [59 empty] | Yes | [15 empty] | Elise
1025 | 03 | 1025-03 | 1597 | PWA | On Hold | 4-11/9 | Bald Street | Smithfield Plains | Res 3 | Res 3, 4-11/9 Bald Street, Smithfield Plains |  |  |  | Developer | Frank Cecere | 25/3 - Brenton chasing client to sign off on concept plans. Concept plans done Nov 2024. Full deposit not paid | Marie | Brenton G | TBC | No | 0 | 1 | 1 | 2024-09-17 | 2024-09-18 |  | 3000 | Yes | Yes | 2024-08-20 | 2024-11-13 | 2024-11-15 | 2024-11-15 | [18 empty] | n/a | n/a |  |  |  |  | 2024-09-30 | [56 empty] | Phoebe | [59 empty] | Yes | [15 empty] | Elise
1025 | 04 | 1025-04 | 1597 | PWA | On Hold | 4-11/9 | Bald Street | Smithfield Plains | Res 4 | Res 4, 4-11/9 Bald Street, Smithfield Plains |  |  |  | Developer | Frank Cecere | 25/3 - Brenton chasing client to sign off on concept plans. Concept plans done Nov 2024. Full deposit not paid | Marie | Brenton G | TBC | No | 0 | 1 | 1 | 2024-09-17 | 2024-09-18 |  | 3000 | Yes | Yes | 2024-08-20 | 2024-11-13 | 2024-11-15 | 2024-11-15 | [18 empty] | n/a | n/a |  |  |  |  | 2024-09-30 | [56 empty] | Phoebe | [59 empty] | Yes | [15 empty] | Elise
1025 | 05 | 1025-05 | 1597 | PWA | On Hold | 4-11/9 | Bald Street | Smithfield Plains | Res 5 | Res 5, 4-11/9 Bald Street, Smithfield Plains |  |  |  | Developer | Frank Cecere | 25/3 - Brenton chasing client to sign off on concept plans. Concept plans done Nov 2024. Full deposit not paid | Marie | Brenton G | TBC | No | 0 | 1 | 1 | 2024-09-17 | 2024-09-18 |  | 3000 | Yes | Yes | 2024-08-20 | 2024-11-13 | 2024-11-15 | 2024-11-15 | [18 empty] | n/a | n/a |  |  |  |  | 2024-09-30 | [56 empty] | Phoebe | [58 empty] | Yes | [16 empty] | Elise
1025 | 06 | 1025-06 | 1597 | PWA | On Hold | 4-11/9 | Bald Street | Smithfield Plains | Res 6 | Res 6, 4-11/9 Bald Street, Smithfield Plains |  |  |  | Developer | Frank Cecere | 25/3 - Brenton chasing client to sign off on concept plans. Concept plans done Nov 2024. Full deposit not paid | Marie | Brenton G | TBC | No | 0 | 1 | 1 | 2024-09-17 | 2024-09-18 |  | 3000 | Yes | Yes | 2024-08-20 | 2024-11-13 | 2024-11-15 | 2024-11-15 | [18 empty] | n/a | n/a |  |  |  |  | 2024-09-30 | [56 empty] | Phoebe | [58 empty] | Yes | [16 empty] | Elise
1025 | 07 | 1025-07 | 1597 | PWA | On Hold | 4-11/9 | Bald Street | Smithfield Plains | Res 7 | Res 7, 4-11/9 Bald Street, Smithfield Plains |  |  |  | Developer | Frank Cecere | 25/3 - Brenton chasing client to sign off on concept plans. Concept plans done Nov 2024. Full deposit not paid | Marie | Brenton G | TBC | No | 0 | 1 | 1 | 2024-09-17 | 2024-09-18 |  | 3000 | Yes | Yes | 2024-08-20 | 2024-11-13 | 2024-11-15 | 2024-11-15 | [18 empty] | n/a | n/a |  |  |  |  | 2024-09-30 | [56 empty] | Phoebe | [58 empty] | Yes | [16 empty] | Elise
1025 | 08 | 1025-08 | 1597 | PWA | On Hold | 4-11/9 | Bald Street | Smithfield Plains | Res 8 | Res 8, 4-11/9 Bald Street, Smithfield Plains |  |  |  | Developer | Frank Cecere | 25/3 - Brenton chasing client to sign off on concept plans. Concept plans done Nov 2024. Full deposit not paid | Marie | Brenton G | TBC | No | 0 | 1 | 1 | 2024-09-17 | 2024-09-18 |  | 3000 | Yes | Yes | 2024-08-20 | 2024-11-13 | 2024-11-15 | 2024-11-15 | [18 empty] | n/a | n/a |  |  |  |  | 2024-09-30 | [56 empty] | Phoebe | [57 empty] | Yes | [17 empty] | Elise
1025 | 09 | 1025-09 | 1597 | PWA | On Hold | 4-11/9 | Bald Street | Smithfield Plains | Res 8 | Res 8, 4-11/9 Bald Street, Smithfield Plains |  |  |  | Developer | Frank Cecere | 25/3 - Brenton chasing client to sign off on concept plans. Concept plans done Nov 2024. Full deposit not paid | Marie | Brenton G | TBC | No | 0 | 1 | 1 | 2024-09-17 | 2024-09-18 |  | 3000 | Yes | Yes | 2024-08-20 | 2024-11-13 | 2024-11-15 | 2024-11-15 | [18 empty] | n/a | n/a |  |  |  |  | 2024-09-30 | [56 empty] | Phoebe | [56 empty] | Yes | [18 empty] | Elise
1026 | 01 | 1026-01 | 1609 | PWA | - | 37 | East Street | Hectorville |  | 37 East Street, Hectorville |  |  |  | Developer | Lofty Building Group - Brenton | 15/07 - FCR Received. VO with the client. | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a | Yes | Yes | 2024-10-11 | 2024-10-25 | 2024-11-25 | 2024-12-06 | 2025-02-06 | 2024-10-28 | 2004-12-10 | 2025-06-02 |  | 2025-02-06 | 2025-02-20 | 2025-01-17 | 2025-02-25 | 2025-02-05 | [6 empty] | 2025-03-05 | 2025-04-04 | n/a | n/a |  |  |  |  | 2025-02-25 | 2026-01-27 | 2025-07-01 | [130 empty] | Elise
1026 | 02 | 1026-02 | 1610 | PWA | - | 37 | East Street | Hectorville |  | 37 East Street, Hectorville |  |  |  | Developer | Lofty Building Group - Brenton | 15/07 - FCR Received. In selections | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a | Yes | Yes | 2024-10-11 | 2024-10-25 | 2024-11-25 | 2024-12-06 | 2025-02-06 | 2024-10-28 | 2024-12-10 | 2025-06-02 |  | 2025-02-06 | 2025-02-20 | 2025-01-17 | 2025-02-25 | 2025-02-05 | [6 empty] | 2025-03-05 | 2025-04-04 | n/a | n/a |  |  |  |  | 2025-02-25 | 2026-01-27 | 2025-07-01 | [130 empty] | Elise
1026 | 03 | 1026-03 | 1611 | PWA | - | 37 | East Street | Hectorville |  | 37 East Street, Hectorville |  |  |  | Developer | Lofty Building Group - Brenton | 15/07 - FCR Received. In selections | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a | Yes | Yes | 2024-10-11 | 2024-10-25 | 2024-11-25 | 2024-12-06 | 2025-02-06 | 2024-10-28 | 2024-12-10 | 2025-06-02 |  | 2025-02-06 | 2025-02-20 | 2025-01-17 | 2025-02-25 | 2025-02-05 | [6 empty] | 2025-03-05 | 2025-04-04 | n/a | n/a |  |  |  |  | 2025-02-25 | 2026-01-27 | 2025-07-01 | [130 empty] | Elise
1026 | 04 | 1026-04 | 1612 | PWA | - | 37 | East Street | Hectorville |  | 37 East Street, Hectorville |  |  |  | Developer | Lofty Building Group - Brenton | 15/07 - FCR Received. Awaiting optional upgrades | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a | Yes | Yes | 2024-10-11 | 2024-10-25 | 2024-11-25 | 2024-12-06 | 2025-02-06 | 2024-10-28 | 2024-12-10 | 2025-06-02 |  | 2025-02-06 | 2025-02-20 | 2025-01-17 | 2025-02-25 | 2025-02-05 | [6 empty] | 2025-03-05 | 2025-04-04 | n/a | n/a |  |  |  |  | 2025-02-25 | 2026-01-27 | 2025-07-01 | [130 empty] | Elise
1026 | 05 | 1026-05 | 1613 | PWA | - | 37 | East Street | Hectorville |  | 37 East Street, Hectorville |  |  |  | Developer | Lofty Building Group - Brenton | 15/07 - FCR Received. In selections | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a | Yes | Yes | 2024-10-11 | 2024-10-25 | 2024-11-25 | 2024-12-06 | 2025-02-06 | 2024-10-28 | 2024-12-10 | 2025-06-02 |  | 2025-02-06 | 2025-02-20 | 2025-01-17 | 2025-02-25 | 2025-02-05 | [6 empty] | 2025-03-05 | 2025-04-04 | n/a | n/a |  |  |  |  | 2025-02-25 | 2026-01-27 | 2025-07-01 | [130 empty] | Elise
1026 | 06 | 1026-06 | 1614 | PWA | - | 37 | East Street | Hectorville |  | 37 East Street, Hectorville |  |  |  | Developer | Lofty Building Group - Brenton | 15/07 - PA received. Prelims footings received. ON MARKET. Waiting on titles.. Framing quotes received.- FCR and final EER Received. | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a | Yes | Yes | 2024-10-11 | 2024-10-25 | 2024-11-25 | 2024-12-06 | 2025-02-06 | 2024-10-28 | 2024-12-10 |  |  | 2025-02-06 | 2025-02-20 | 2025-01-17 | 2025-02-25 | 2025-02-05 | [6 empty] | 2025-03-05 | 2025-04-04 | n/a | n/a |  |  |  |  | 2025-02-25 | 2026-01-27 | 2025-07-01 | [130 empty] | Elise
1026 | 07 | 1026-07 | 1615 | PWA | - | 37 | East Street | Hectorville |  | 37 East Street, Hectorville |  |  |  | Developer | Lofty Building Group - Brenton | 15/07 - PA received. Prelims footings received. ON MARKET. Waiting on titles.. Framing quotes received.- FCR and final EER Received. | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a | Yes | Yes | 2024-10-11 | 2024-10-25 | 2024-11-25 | 2024-12-06 | 2025-02-06 | 2024-10-28 | 2024-12-10 |  |  | 2025-02-06 | 2025-02-20 | 2025-01-17 | 2025-02-25 | 2025-02-05 | [6 empty] | 2025-03-05 | 2025-04-04 | n/a | n/a |  |  |  |  | 2025-02-25 | 2026-01-27 | 2025-07-01 | [130 empty] | Elise
1026 | 08 | 1026-08 | 1616 | PWA | - | 37 | East Street | Hectorville |  | 37 East Street, Hectorville |  |  |  | Developer | Lofty Building Group - Brenton | 15/07 - PA received. Prelims footings received. ON MARKET. Waiting on titles.. Framing quotes received.- FCR and final EER Received. | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a | Yes | Yes | 2024-10-11 | 2024-10-25 | 2024-11-25 | 2024-12-06 | 2025-02-06 | 2024-10-28 | 2024-12-10 |  |  | 2025-02-06 | 2025-02-20 | 2025-01-17 | 2025-02-25 | 2025-02-05 | [6 empty] | 2025-03-05 | 2025-04-04 | n/a | n/a |  |  |  |  | 2025-02-25 | 2026-01-27 | 2025-07-01 | [130 empty] | Elise
1026 | 09 | 1026-09 | 1617 | PWA | - | 37 | East Street | Hectorville |  | 37 East Street, Hectorville |  |  |  | Developer | Lofty Building Group - Brenton | 15/07 - PA received. Prelims footings received. ON MARKET. Waiting on titles.. Framing quotes received.- FCR and final EER Received. | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a | Yes | Yes | 2024-10-11 | 2024-10-25 | 2024-11-25 | 2024-12-06 | 2025-02-06 | 2024-10-28 | 2024-12-10 |  |  | 2025-02-06 | 2025-02-20 | 2025-01-17 | 2025-02-25 | 2025-02-05 | [6 empty] | 2025-03-05 | 2025-04-04 | n/a | n/a |  |  |  |  | 2025-02-25 | 2026-01-27 | 2025-07-01 | [130 empty] | Elise
1026 | 10 | 1026-10 | 1618 | PWA | - | 37 | East Street | Hectorville |  | 37 East Street, Hectorville |  |  |  | Developer | Lofty Building Group - Brenton | 15/07 - PA received. Prelims footings received. ON MARKET. Waiting on titles.. Framing quotes received.- FCR and final EER Received. | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a | Yes | Yes | 2024-10-11 | 2024-10-25 | 2024-11-25 | 2024-12-06 | 2025-02-06 | 2024-10-28 | 2024-12-10 |  |  | 2025-02-06 | 2025-02-20 | 2025-01-17 | 2025-02-25 | 2025-02-05 | [6 empty] | 2025-03-05 | 2025-04-04 | n/a | n/a |  |  |  |  | 2025-02-25 | 2026-01-27 | 2025-07-01 | [130 empty] | Elise
1026 | 11 | 1026-11 | 1619 | PWA | - | 37 | East Street | Hectorville |  | 37 East Street, Hectorville |  |  |  | Developer | Lofty Building Group - Brenton | 15/07 - PA received. Prelims footings received. ON MARKET. Waiting on titles.. Framing quotes received.- FCR and final EER Received. | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a | Yes | Yes | 2024-10-11 | 2024-10-25 | 2024-11-25 | 2024-12-06 | 2025-02-06 | 2024-10-28 | 2024-12-10 |  |  |  | 2025-02-20 | 2025-01-17 | 2025-02-25 | 2025-02-05 | [6 empty] | 2025-03-05 | 2025-04-04 | n/a | n/a |  |  |  |  | 2025-02-25 | 2026-01-27 | 2025-07-01 | [130 empty] | Elise
1026 | 12 | 1026-12 | 1620 | PWA | - | 37 | East Street | Hectorville |  | 37 East Street, Hectorville |  |  |  | Developer | Lofty Building Group - Brenton | 15/07 - PA received. Prelims footings received. ON MARKET. Waiting on titles.. Framing quotes received.- FCR and final EER Received. | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a | Yes | Yes | 2024-10-11 | 2024-10-25 | 2024-11-25 | 2024-12-06 | 2025-02-06 | 2024-10-28 | 2024-12-10 |  |  | 2025-02-06 | 2025-02-20 | 2025-01-17 | 2025-02-25 | 2025-02-05 | [6 empty] | 2025-03-05 | 2025-04-04 | n/a | n/a |  |  |  |  | 2025-02-25 | 2026-01-27 | 2025-07-01 | [130 empty] | Elise
1026 | 13 | 1026-13 | 1621 | PWA | - | 37 | East Street | Hectorville |  | 37 East Street, Hectorville |  |  |  | Developer | Lofty Building Group - Brenton | 15/07 - PA received. Prelims footings received. ON MARKET. Waiting on titles.. Framing quotes received.- FCR and final EER Received. | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a | Yes | Yes | 2024-10-11 | 2024-10-25 | 2024-11-25 | 2024-12-06 | 2025-02-06 | 2024-10-28 | 2024-12-10 |  |  | 2025-02-06 | 2025-02-20 | 2025-01-17 | 2025-02-25 | 2025-02-05 | [6 empty] | 2025-03-05 | 2025-04-04 | n/a | n/a |  |  |  |  | 2025-02-25 | 2026-01-27 | 2025-07-01 | [130 empty] | Elise
1026 | 14 | 1026-14 | 1622 | PWA | - | 37 | East Street | Hectorville |  | 37 East Street, Hectorville |  |  |  | Developer | Lofty Building Group - Brenton | 15/07 - PA received. Prelims footings received. ON MARKET. Waiting on titles.. Framing quotes received.- FCR and final EER Received. | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a | Yes | Yes | 2024-10-11 | 2024-10-25 | 2024-11-25 | 2024-12-06 | 2025-02-06 | 2024-10-28 | 2024-12-10 |  |  | 2025-02-06 | 2025-02-20 | 2025-01-17 | 2025-02-25 | 2025-02-05 | [6 empty] | 2025-03-05 | 2025-04-04 | n/a | n/a |  |  |  |  | 2025-02-25 | 2026-01-27 | 2025-07-01 | [130 empty] | Elise
1026 | 15 | 1026-15 | 1623 | PWA | - | 37 | East Street | Hectorville |  | 37 East Street, Hectorville |  |  |  | Developer | Lofty Building Group - Brenton | 15/07 - PA received. Prelims footings received. ON MARKET. Waiting on titles.. Framing quotes received.- FCR and final EER Received. | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a | Yes | Yes | 2024-10-11 | 2024-10-25 | 2024-11-25 | 2024-12-06 | 2025-02-06 | 2024-10-28 | 2024-12-10 |  |  | 2025-02-06 | 2025-02-20 | 2025-01-17 | 2025-02-25 | 2025-02-05 | [6 empty] | 2025-03-05 | 2025-04-04 | n/a | n/a |  |  |  |  | 2025-02-25 | 2026-01-27 | 2025-07-01 | [130 empty] | Elise
1026 | 16 | 1026-16 | 1624 | PWA | - | 37 | East Street | Hectorville |  | 37 East Street, Hectorville |  |  |  | Developer | Lofty Building Group - Brenton | 15/07 - PA received. Prelims footings received. ON MARKET. Waiting on titles.. Framing quotes received.- FCR and final EER Received. | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a | Yes | Yes | 2024-10-11 | 2024-10-25 | 2024-11-25 | 2024-12-06 | 2025-02-06 | 2024-10-28 | 2024-12-10 |  |  | 2025-02-06 | 2025-02-20 | 2025-01-17 | 2025-02-25 | 2025-02-05 | [6 empty] | 2025-03-05 | 2025-04-04 | n/a | n/a |  |  |  |  | 2025-02-25 | 2026-01-27 | 2025-07-01 | [130 empty] | Elise
1026 | 17 | 1026-17 | 1625 | PWA | - | 37 | East Street | Hectorville |  | 37 East Street, Hectorville |  |  |  | Developer | Lofty Building Group - Brenton | 15/07 - PA received. Prelims footings received. ON MARKET. Waiting on titles.. Framing quotes received.- FCR and final EER Received. | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a | Yes | Yes | 2024-10-11 | 2024-10-25 | 2024-11-25 | 2024-12-06 | 2025-02-06 | 2024-10-28 | 2024-12-10 |  |  | 2025-02-06 | 2025-02-20 | 2025-01-17 | 2025-02-25 | 2025-02-05 | [6 empty] | 2025-03-05 | 2025-04-04 | n/a | n/a |  |  |  |  | 2025-02-25 | 2026-01-27 | 2025-07-01 | [130 empty] | Elise
1026 | 18 | 1026-18 | 1626 | PWA | - | 37 | East Street | Hectorville |  | 37 East Street, Hectorville |  |  |  | Developer | Lofty Building Group - Brenton | 15/07 - PA received. Prelims footings received. ON MARKET. Waiting on titles.. Framing quotes received.- FCR and final EER Received. | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a | Yes | Yes | 2024-10-11 | 2024-10-25 | 2024-11-25 | 2024-12-06 | 2025-02-06 | 2024-10-28 | 2024-12-10 |  |  | 2025-02-06 | 2025-02-20 | 2025-01-17 | 2025-02-25 | 2025-02-05 | [6 empty] | 2025-03-05 | 2025-04-04 | n/a | n/a |  |  |  |  | 2025-02-25 | 2026-01-27 | 2025-07-01 | [130 empty] | Elise
1026 | 19 | 1026-19 | 1627 | PWA | - | 37 | East Street | Hectorville |  | 37 East Street, Hectorville |  |  |  | Developer | Lofty Building Group - Brenton | 15/07 - PA received. Prelims footings received. ON MARKET. Waiting on titles.. Framing quotes received.- FCR and final EER Received. | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a | Yes | Yes | 2024-10-11 | 2024-10-25 | 2024-11-25 | 2024-12-06 | 2025-02-06 | 2024-10-28 | 2024-12-10 |  |  | 2025-02-06 | 2025-02-20 | 2025-01-17 | 2025-02-25 | 2025-02-05 | [6 empty] | 2025-03-05 | 2025-04-04 | n/a | n/a |  |  |  |  | 2025-02-25 | 2026-01-27 | 2025-07-01 | [130 empty] | Elise
1026 | 20 | 1026-20 | 1628 | PWA | - | 37 | East Street | Hectorville |  | 37 East Street, Hectorville |  |  |  | Developer | Lofty Building Group - Brenton | 15/07 - PA received. Prelims footings received. ON MARKET. Waiting on titles.. Framing quotes received.- FCR and final EER Received. | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a | Yes | Yes | 2024-10-11 | 2024-10-25 | 2024-11-25 | 2024-12-06 | 2025-02-06 | 2024-10-28 | 2024-12-10 |  |  | 2025-02-06 | 2025-02-20 | 2025-01-17 | 2025-02-25 | 2025-02-05 | [6 empty] | 2025-03-05 | 2025-04-04 | n/a | n/a |  |  |  |  | 2025-02-25 | 2026-01-27 | 2025-07-01 | [130 empty] | Elise
1026 | 21 | 1026-21 | 1629 | PWA | - | 37 | East Street | Hectorville |  | 37 East Street, Hectorville |  |  |  | Developer | Lofty Building Group - Brenton | 15/07 - Optional upgrades VO issued | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a | Yes | Yes | 2024-10-11 | 2024-10-25 | 2024-11-25 | 2024-12-06 | 2025-02-06 | 2024-10-28 | 2024-12-10 |  |  | 2025-02-06 | 2025-02-20 | 2025-01-17 | 2025-02-25 | 2025-02-05 | [6 empty] | 2025-03-05 | 2025-04-04 | n/a | n/a |  |  |  |  | 2025-02-25 | 2026-01-27 | 2025-07-01 | [130 empty] | Elise
1026 | 22 | 1026-22 | 1630 | PWA | - | 37 | East Street | Hectorville |  | 37 East Street, Hectorville |  |  |  | Developer | Lofty Building Group - Brenton | 15/07 - Optional upgrades VO issued | Marie | Brenton G | TBC | No | 1 | 0 | 1 | n/a | n/a | n/a | n/a | Yes | Yes | 2024-10-11 | 2024-10-25 | 2024-11-25 | 2024-12-06 | 2025-02-06 | 2024-10-28 | 2024-12-10 |  |  | 2025-02-06 | 2025-02-20 | 2025-01-17 | 2025-02-25 | 2025-02-05 | [6 empty] | 2025-03-05 | 2025-04-04 | n/a | n/a |  |  |  |  | 2025-02-25 | 2026-01-27 | 2025-07-01 | [130 empty] | Elise
1027 | 01 | 1027-01 | [11 empty] | Developer
1028 | 01 | 1028-01 | [11 empty] | Developer
1029 | 01 | 1029-01 | [11 empty] | Developer
1030 | 01 | 1030-01 | 1658 | PWA | - |  | Young Court | Murray Bridge | Lot 12 | Lot 12 Young Court, Murray Bridge |  |  |  | Developer | Cornerstone Housing Paul Klose | 27/1 - Logged for Planning Approval (MLEI). Logged for Encumbrance (MLEI). Logged in design for EER options, Refreshed Pricing schedule Logged | Marie | Paul | TBC | No | 1 | 0 | 1 | 2024-11-20 | 2024-11-22 | 2024-12-02 | 5000 | Yes | Yes | 2024-10-15 | 2024-11-01 | n/a | n/a | n/a |  | 2025-09-25 |  | 2025-09-25 | 2024-11-22 |  |  |  |  | 2026-01-19 | [146 empty] | Elise
1030 | 02 | 1030-02 | 1659 | PWA | - |  | Young Court | Murray Bridge | Lot 13 | Lot 13 Young Court, Murray Bridge |  |  |  | Developer | Cornerstone Housing Paul Klose | 27/1 - Logged for Planning Approval (MLEI). Logged for Encumbrance (MLEI). Logged in design for EER options, Refreshed Pricing schedule Logged | Marie | Paul | TBC | No | 1 | 0 | 1 | 2024-11-20 | 2024-11-22 | 2024-12-02 | 5000 | Yes | Yes | 2024-10-15 | 2024-11-01 | n/a | n/a | n/a |  | 2025-09-25 |  | 2025-09-25 | 2024-11-22 | 2025-01-15 |  |  |  | 2026-01-19 | [146 empty] | Elise
1031 | 01 | 1031-01 | 1660 | PWA | - |  | Ellendale Road | Murray Bridge | Lot 21 | Lot 21 Ellendale Road, Murray Bridge |  |  |  | Developer | Cornerstone Housing Paul Klose | 27/1 - Logged for Planning Approval (MLEI). Logged for Encumbrance (MLEI). Logged in design for EER options, Refreshed Pricing schedule Logged | Marie | Paul | TBC | No | 1 | 0 | 1 | 2024-11-20 | 2024-11-22 | 2024-12-02 | 5000 | Yes | Yes | 2024-10-15 | 2024-11-01 | n/a | n/a | n/a |  |  |  |  | 2024-11-22 | 2025-01-17 |  |  |  | 2026-01-19 | [146 empty] | Elise
1031 | 02 | 1031-02 | 1661 | PWA | - |  | Ellendale Road | Murray Bridge | Lot 22 | Lot 22 Ellendale Road, Murray Bridge |  |  |  | Developer | Cornerstone Housing Paul Klose | 27/1 - Logged for Planning Approval (MLEI). Logged for Encumbrance (MLEI). Logged in design for EER options, Refreshed Pricing schedule Logged | Marie | Paul | TBC | No | 1 | 0 | 1 | 2024-11-20 | 2024-11-22 | 2024-12-02 | 5000 | Yes | Yes | 2024-10-15 | 2024-11-01 | n/a | n/a | n/a |  |  |  |  | 2024-11-22 | 2024-12-20 |  |  |  | 2026-01-19 | [146 empty] | Elise
1032 | 01 | 1032-01 | 1662 | PWA | - |  | Piper Court | Murray Bridge | Lot 52 | Lot 52 Piper Court, Murray Bridge |  |  |  | Developer | Cornerstone Housing Paul Klose | 23/1 - Awaiting prelim footing report and soils. Logged for Planning Approval (KP AUSTRUCT). Civil Plan revision requested to fix RWT details. Lodge Revised Plan to Council | Marie | Paul | TBC | No | 1 | 0 | 1 | 2024-11-20 | 2024-11-22 | 2024-12-02 | 5000 | Yes | Yes | 2024-10-15 | 2024-11-01 | n/a | n/a | n/a |  |  |  |  | 2024-11-22 | 2024-12-20 |  |  |  | 2026-01-19 | [146 empty] | Elise
1032 | 02 | 1032-02 | 1663 | PWA | - |  | Piper Court | Murray Bridge | Lot 56 | Lot 56 Piper Court, Murray Bridge |  |  |  | Developer | Cornerstone Housing Paul Klose | 23/1 - Awaiting prelim footing report and soils. Logged for Planning Approval (KP AUSTRUCT). Civil Plan revision requested to fix RWT details. Lodge Revised Plan to Council | Marie | Paul | TBC | No | 1 | 0 | 1 | 2024-11-20 | 2024-11-22 | 2024-12-02 | 5000 | Yes | Yes | 2024-10-15 | 2024-11-01 | n/a | n/a | n/a |  |  |  |  | 2024-11-22 | 2024-12-20 |  |  |  | 2026-01-19 | [146 empty] | Elise
1033 | 01 | 1033-01 | 1674 | PWA | - | 2 | Luke Ave | Salisbury Downs | Res 1 | 2 Luke Ave, Salisbury Downs (Res 1) |  |  |  | Developer | Lofty Building Group | 16/06 - PA received. Reserved matter to be addressed. FQC done. ON MARKET. Framing quotes received. To be logged for WDs. In for Stage 1 BRC - siteworks | Marie | Brenton G | TBC |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2025-01-17 | 2025-02-05 | n/a | n/a | 2025-02-06 | 2025-01-13 | 2025-02-03 | 2025-05-19 | 2025-06-24 | 2025-02-06 | 2025-03-04 | 2025-04-22 | n/a | [7 empty] | 2025-05-15 | 2025-06-02 | [6 empty] | 2025-03-11 | 2025-12-03 | [131 empty] | Elise
1033 | 02 | 1033-02 | 1675 | PWA | - | 2 | Luke Ave | Salisbury Downs | Res 2 | 2 Luke Ave, Salisbury Downs (Res 2) |  |  |  | Developer | Lofty Building Group | 16/06 - PA received. Reserved matter to be addressed. FQC done. ON MARKET. Framing quotes received. To be logged for WDs. In for Stage 1 BRC - siteworks | Marie | Brenton G | TBC |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2025-01-17 | 2025-02-05 | n/a | n/a | 2025-02-06 | 2025-01-13 | 2025-02-03 | 2025-05-19 | 2025-06-24 | 2025-02-06 | 2025-03-04 | 2025-04-22 | n/a | [7 empty] | 2025-05-15 | 2025-06-02 | [6 empty] | 2025-03-11 | 2025-12-03 | [131 empty] | Elise
1033 | 03 | 1033-03 | 1676 | PWA | - | 2 | Luke Ave | Salisbury Downs | Res 3 | 2 Luke Ave, Salisbury Downs (Res 3) |  |  |  | Developer | Lofty Building Group | 16/06 - PA received. Reserved matter to be addressed. FQC done. ON MARKET. Framing quotes received. To be logged for WDs. In for Stage 1 BRC - siteworks | Marie | Brenton G | TBC |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2025-01-17 | 2025-02-05 | n/a | n/a | 2025-02-06 | 2025-01-13 | 2025-02-03 | 2025-05-19 | 2025-06-24 | 2025-02-06 | 2025-03-04 | 2025-04-22 | n/a | [7 empty] | 2025-05-15 | 2025-06-02 | [6 empty] | 2025-03-11 | 2025-12-03 | [131 empty] | Elise
1033 | 04 | 1033-04 | 1677 | PWA | - | 2 | Luke Ave | Salisbury Downs | Res 4 | 2 Luke Ave, Salisbury Downs (Res 4) |  |  |  | Developer | Lofty Building Group | 16/06 - PA received. Reserved matter to be addressed. FQC done. ON MARKET. Framing quotes received. To be logged for WDs. In for Stage 1 BRC - siteworks | Marie | Brenton G | TBC |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2025-01-17 | 2025-02-05 | n/a | n/a | 2025-02-06 | 2025-01-13 | 2025-02-03 | 2025-05-19 | 2025-06-24 | 2025-02-06 | 2025-03-04 | 2025-04-22 | n/a | [7 empty] | 2025-05-15 | 2025-06-02 | [6 empty] | 2025-03-11 | 2025-12-03 | [131 empty] | Elise
1033 | 05 | 1033-05 | 1678 | PWA | - | 2 | Luke Ave | Salisbury Downs | Res 5 | 2 Luke Ave, Salisbury Downs (Res 5) |  |  |  | Developer | Lofty Building Group | 16/06 - PA received. Reserved matter to be addressed. FQC done. ON MARKET. Framing quotes received. To be logged for WDs. In for Stage 1 BRC - siteworks | Marie | Brenton G | TBC |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2025-01-17 | 2025-02-05 | n/a | n/a | 2025-02-06 | 2025-01-13 | 2025-02-03 | 2025-05-19 | 2025-06-24 | 2025-02-06 | 2025-03-04 | 2025-04-22 | n/a | [7 empty] | 2025-05-15 | 2025-06-02 | [6 empty] | 2025-03-11 | 2025-12-03 | [131 empty] | Elise
1033 | 06 | 1033-06 | 1679 | PWA | - | 2 | Luke Ave | Salisbury Downs | Res 6 | 2 Luke Ave, Salisbury Downs (Res 6) |  |  |  | Developer | Lofty Building Group | 16/06 - PA received. Reserved matter to be addressed. FQC done. ON MARKET. Framing quotes received. To be logged for WDs. In for Stage 1 BRC - siteworks | Marie | Brenton G | TBC |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2025-01-17 | 2025-02-05 | n/a | n/a | 2025-02-06 | 2025-01-13 | 2025-02-03 | 2025-05-19 | 2025-06-24 | 2025-02-06 | 2025-03-04 | 2025-04-22 | n/a | [7 empty] | 2025-05-15 | 2025-06-02 | [6 empty] | 2025-03-11 | 2025-12-03 | [131 empty] | Elise
1033 | 07 | 1033-07 | 1680 | PWA | - | 2 | Luke Ave | Salisbury Downs | Res 7 | 2 Luke Ave, Salisbury Downs (Res 7) |  |  |  | Developer | Lofty Building Group | 16/06 - PA received. Reserved matter to be addressed. FQC done. ON MARKET. Framing quotes received. To be logged for WDs. In for Stage 1 BRC - siteworks | Marie | Brenton G | TBC |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2025-01-17 | 2025-02-05 | n/a | n/a | 2025-02-06 | 2025-01-13 | 2025-02-03 | 2025-05-19 | 2025-06-24 | 2025-02-06 | 2025-03-04 | 2025-04-22 | n/a | [7 empty] | 2025-05-15 | 2025-06-02 | [6 empty] | 2025-03-11 | 2025-12-03 | [131 empty] | Elise
1033 | 08 | 1033-08 | 1681 | PWA | - | 2 | Luke Ave | Salisbury Downs | Res 8 | 2 Luke Ave, Salisbury Downs (Res 8) |  |  |  | Developer | Lofty Building Group | 16/06 - PA received. Reserved matter to be addressed. FQC done. ON MARKET. Framing quotes received. To be logged for WDs. In for Stage 1 BRC - siteworks | Marie | Brenton G | TBC |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2025-01-17 | 2025-02-05 | n/a | n/a | 2025-02-06 | 2025-01-13 | 2025-02-03 | 2025-05-19 | 2025-06-24 | 2025-02-06 | 2025-03-04 | 2025-04-22 | n/a | [7 empty] | 2025-05-15 | 2025-06-02 | [6 empty] | 2025-03-11 | 2025-12-03 | [131 empty] | Elise
1033 | 09 | 1033-09 | 1682 | PWA | - | 2 | Luke Ave | Salisbury Downs | Res 9 | 2 Luke Ave, Salisbury Downs (Res 9) |  |  |  | Developer | Lofty Building Group | 16/06 - PA received. Reserved matter to be addressed. FQC done. ON MARKET. Framing quotes received. To be logged for WDs. In for Stage 1 BRC - siteworks | Marie | Brenton G | TBC |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2025-01-17 | 2025-02-05 | n/a | n/a | 2025-02-06 | 2025-01-13 | 2025-02-03 | 2025-05-19 | 2025-06-24 | 2025-02-06 | 2025-03-04 | 2025-04-22 | n/a | [7 empty] | 2025-05-15 | 2025-06-02 | [6 empty] | 2025-03-11 | 2025-12-03 | [131 empty] | Elise
1033 | 10 | 1033-10 | 1683 | PWA | - | 2 | Luke Ave | Salisbury Downs | Res 10 | 2 Luke Ave, Salisbury Downs (Res 10) |  |  |  | Developer | Lofty Building Group | 16/06 - PA received. Reserved matter to be addressed. FQC done. ON MARKET. Framing quotes received. To be logged for WDs. In for Stage 1 BRC - siteworks | Marie | Brenton G | TBC |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2025-01-17 | 2025-02-05 | n/a | n/a | 2025-02-06 | 2025-01-13 | 2025-02-03 | 2025-05-19 | 2025-06-24 | 2025-02-06 | 2025-03-04 | 2025-04-22 | n/a | [7 empty] | 2025-05-15 | 2025-06-02 | [6 empty] | 2025-03-11 | 2025-12-03 | [131 empty] | Elise
1033 | 11 | 1033-11 | 1684 | PWA | - | 2 | Luke Ave | Salisbury Downs | Res 11 | 2 Luke Ave, Salisbury Downs (Res 11) |  |  |  | Developer | Lofty Building Group | 16/06 - PA received. Reserved matter to be addressed. FQC done. ON MARKET. Framing quotes received. To be logged for WDs. In for Stage 1 BRC - siteworks | Marie | Brenton G | TBC |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2025-01-17 | 2025-02-05 | n/a | n/a | 2025-02-06 | 2025-01-13 | 2025-02-03 | 2025-05-19 | 2025-06-24 | 2025-02-06 | 2025-03-04 | 2025-04-22 | n/a | [7 empty] | 2025-05-15 | 2025-06-02 | [6 empty] | 2025-03-11 | 2025-12-03 | [131 empty] | Elise
1033 | 12 | 1033-12 | 1685 | PWA | - | 2 | Luke Ave | Salisbury Downs | Res 12 | 2 Luke Ave, Salisbury Downs (Res 12) |  |  |  | Developer | Lofty Building Group | 16/06 - PA received. Reserved matter to be addressed. FQC done. ON MARKET. Framing quotes received. To be logged for WDs. In for Stage 1 BRC - siteworks | Marie | Brenton G | TBC |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2025-01-17 | 2025-02-05 | n/a | n/a | 2025-02-06 | 2025-01-13 | 2025-02-03 | 2025-05-19 | 2025-06-24 | 2025-02-06 | 2025-03-04 | 2025-04-22 | n/a | [7 empty] | 2025-05-15 | 2025-06-02 | [6 empty] | 2025-03-11 | 2025-12-03 | [131 empty] | Elise
1033 | 13 | 1033-13 | 1686 | PWA | - | 2 | Luke Ave | Salisbury Downs | Res 13 | 2 Luke Ave, Salisbury Downs (Res 13) |  |  |  | Developer | Lofty Building Group | 16/06 - PA received. Reserved matter to be addressed. FQC done. ON MARKET. Framing quotes received. To be logged for WDs. In for Stage 1 BRC - siteworks | Marie | Brenton G | TBC |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2025-01-17 | 2025-02-05 | n/a | n/a | 2025-02-06 | 2025-01-13 | 2025-02-03 | 2025-05-19 | 2025-06-24 | 2025-02-06 | 2025-03-04 | 2025-04-22 | n/a | [7 empty] | 2025-05-15 | 2025-06-02 | [6 empty] | 2025-03-11 | 2025-12-03 | [131 empty] | Elise
1033 | 14 | 1033-14 | 1687 | PWA | - | 2 | Luke Ave | Salisbury Downs | Res 14 | 2 Luke Ave, Salisbury Downs (Res 14) |  |  |  | Developer | Lofty Building Group | 16/06 - PA received. Reserved matter to be addressed. FQC done. ON MARKET. Framing quotes received. To be logged for WDs. In for Stage 1 BRC - siteworks | Marie | Brenton G | TBC |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2025-01-17 | 2025-02-05 | n/a | n/a | 2025-02-06 | 2025-01-13 | 2025-02-03 | 2025-05-19 | 2025-06-24 | 2025-02-06 | 2025-03-04 | 2025-04-22 | n/a | [7 empty] | 2025-05-15 | 2025-06-02 | [6 empty] | 2025-03-11 | 2025-12-03 | [131 empty] | Elise
1033 | 15 | 1033-15 | 1688 | PWA | - | 2 | Luke Ave | Salisbury Downs | Res 15 | 2 Luke Ave, Salisbury Downs (Res 15) |  |  |  | Developer | Lofty Building Group | 16/06 - PA received. Reserved matter to be addressed. FQC done. ON MARKET. Framing quotes received. To be logged for WDs. In for Stage 1 BRC - siteworks | Marie | Brenton G | TBC |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2025-01-17 | 2025-02-05 | n/a | n/a | 2025-02-06 | 2025-01-13 | 2025-02-03 | 2025-05-19 | 2025-06-24 | 2025-02-06 | 2025-03-04 | 2025-04-22 | n/a | [7 empty] | 2025-05-15 | 2025-06-02 | [6 empty] | 2025-03-11 | 2025-12-03 | [131 empty] | Elise
1033 | 16 | 1033-16 | 1689 | PWA | - | 2 | Luke Ave | Salisbury Downs | Res 16 | 2 Luke Ave, Salisbury Downs (Res 16) |  |  |  | Developer | Lofty Building Group | 16/06 - PA received. Reserved matter to be addressed. FQC done. ON MARKET. Framing quotes received. To be logged for WDs. In for Stage 1 BRC - siteworks | Marie | Brenton G | TBC |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2025-01-17 | 2025-02-05 | n/a | n/a | 2025-02-06 | 2025-01-13 | 2025-02-03 | 2025-05-19 | 2025-06-24 | 2025-02-06 | 2025-03-04 | 2025-04-22 | n/a | [7 empty] | 2025-05-15 | 2025-06-02 | [6 empty] | 2025-03-11 | 2025-12-03 | [131 empty] | Elise
1033 | 17 | 1033-17 | 1690 | PWA | - | 2 | Luke Ave | Salisbury Downs | Res 17 | 2 Luke Ave, Salisbury Downs (Res 17) |  |  |  | Developer | Lofty Building Group | 16/06 - PA received. Reserved matter to be addressed. FQC done. ON MARKET. Framing quotes received. To be logged for WDs. In for Stage 1 BRC - siteworks | Marie | Brenton G | TBC |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2025-01-17 | 2025-02-05 | n/a | n/a | 2025-02-06 | 2025-01-13 | 2025-02-03 | 2025-05-19 | 2025-06-24 | 2025-02-06 | 2025-03-04 | 2025-04-22 | n/a | [7 empty] | 2025-05-15 | 2025-06-02 | [6 empty] | 2025-03-11 | 2025-12-03 | [131 empty] | Elise
1033 | 18 | 1033-18 | 1691 | PWA | - | 2 | Luke Ave | Salisbury Downs | Res 18 | 2 Luke Ave, Salisbury Downs (Res 18) |  |  |  | Developer | Lofty Building Group | 16/06 - PA received. Reserved matter to be addressed. FQC done. ON MARKET. Framing quotes received. To be logged for WDs. In for Stage 1 BRC - siteworks | Marie | Brenton G | TBC |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2025-01-17 | 2025-02-05 | n/a | n/a | 2025-02-06 | 2025-01-13 | 2025-02-03 | 2025-05-19 | 2025-06-24 | 2025-02-06 | 2025-03-04 | 2025-04-22 | n/a | [7 empty] | 2025-05-15 | 2025-06-02 | [6 empty] | 2025-03-11 | 2025-12-03 | [131 empty] | Elise
1033 | 19 | 1033-19 | 1692 | PWA | - | 2 | Luke Ave | Salisbury Downs | Res 19 | 2 Luke Ave, Salisbury Downs (Res 19) |  |  |  | Developer | Lofty Building Group | 16/06 - PA received. Reserved matter to be addressed. FQC done. ON MARKET. Framing quotes received. To be logged for WDs. In for Stage 1 BRC - siteworks | Marie | Brenton G | TBC |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2025-01-17 | 2025-02-05 | n/a | n/a | 2025-02-06 | 2025-01-13 | 2025-02-03 | 2025-05-19 | 2025-06-24 | 2025-02-06 | 2025-03-04 | 2025-04-22 | n/a | [7 empty] | 2025-05-15 | 2025-06-02 | [6 empty] | 2025-03-11 | 2025-12-03 | [131 empty] | Elise
1033 | 20 | 1033-20 | 1693 | PWA | - | 2 | Luke Ave | Salisbury Downs | Res 20 | 2 Luke Ave, Salisbury Downs (Res 20) |  |  |  | Developer | Lofty Building Group | 16/06 - PA received. Reserved matter to be addressed. FQC done. ON MARKET. Framing quotes received. To be logged for WDs. In for Stage 1 BRC - siteworks | Marie | Brenton G | TBC |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2025-01-17 | 2025-02-05 | n/a | n/a | 2025-02-06 | 2025-01-13 | 2025-02-03 | 2025-05-19 | 2025-06-24 | 2025-02-06 | 2025-03-04 | 2025-04-22 | n/a | [7 empty] | 2025-05-15 | 2025-06-02 | [6 empty] | 2025-03-11 | 2025-12-03 | [131 empty] | Elise
1033 | 21 | 1033-21 | 1694 | PWA | - | 2 | Luke Ave | Salisbury Downs | Res 21 | 2 Luke Ave, Salisbury Downs (Res 21) |  |  |  | Developer | Lofty Building Group | 16/06 - PA received. Reserved matter to be addressed. FQC done. ON MARKET. Framing quotes received. To be logged for WDs. In for Stage 1 BRC - siteworks | Marie | Brenton G | TBC |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2025-01-17 | 2025-02-05 | n/a | n/a | 2025-02-06 | 2025-01-13 | 2025-02-03 | 2025-05-19 | 2025-06-24 | 2025-02-06 | 2025-03-04 | 2025-04-22 | n/a | [7 empty] | 2025-05-15 | 2025-06-02 | [6 empty] | 2025-03-11 | 2025-12-03 | [131 empty] | Elise
1033 | 22 | 1033-22 | 1695 | PWA | - | 2 | Luke Ave | Salisbury Downs | Res 22 | 2 Luke Ave, Salisbury Downs (Res 22) |  |  |  | Developer | Lofty Building Group | 16/06 - PA received. Reserved matter to be addressed. FQC done. ON MARKET. Framing quotes received. To be logged for WDs. In for Stage 1 BRC - siteworks | Marie | Brenton G | TBC |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2025-01-17 | 2025-02-05 | n/a | n/a | 2025-02-06 | 2025-01-13 | 2025-02-03 | 2025-05-19 | 2025-06-24 | 2025-02-06 | 2025-03-04 | 2025-04-22 | n/a | [7 empty] | 2025-05-15 | 2025-06-02 | [6 empty] | 2025-03-11 | 2025-12-03 | [131 empty] | Elise
1033 | 23 | 1033-23 | 1696 | PWA | - | 2 | Luke Ave | Salisbury Downs | Res 23 | 2 Luke Ave, Salisbury Downs (Res 23) |  |  |  | Developer | Lofty Building Group | 16/06 - PA received. Reserved matter to be addressed. FQC done. ON MARKET. Framing quotes received. To be logged for WDs. In for Stage 1 BRC - siteworks | Marie | Brenton G | TBC |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2025-01-17 | 2025-02-05 | n/a | n/a | 2025-02-06 | 2025-01-13 | 2025-02-03 | 2025-05-19 | 2025-06-24 | 2025-02-06 | 2025-03-04 | 2025-04-22 | n/a | [7 empty] | 2025-05-15 | 2025-06-02 | [6 empty] | 2025-03-11 | 2025-12-03 | [131 empty] | Elise
1033 | 24 | 1033-24 | 1697 | PWA | - | 2 | Luke Ave | Salisbury Downs | Res 24 | 2 Luke Ave, Salisbury Downs (Res 24) |  |  |  | Developer | Lofty Building Group | 16/06 - PA received. Reserved matter to be addressed. FQC done. ON MARKET. Framing quotes received. To be logged for WDs. In for Stage 1 BRC - siteworks | Marie | Brenton G | TBC |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2025-01-17 | 2025-02-05 | n/a | n/a | 2025-02-06 | 2025-01-13 | 2025-02-03 | 2025-05-19 | 2025-06-24 | 2025-02-06 | 2025-03-04 | 2025-04-22 | n/a | [7 empty] | 2025-05-15 | 2025-06-02 | [6 empty] | 2025-03-11 | 2025-12-03 | [131 empty] | Elise
1033 | 25 | 1033-25 | 1698 | PWA | - | 2 | Luke Ave | Salisbury Downs | Res 25 | 2 Luke Ave, Salisbury Downs (Res 25) |  |  |  | Developer | Lofty Building Group | 16/06 - PA received. Reserved matter to be addressed. FQC done. ON MARKET. Framing quotes received. To be logged for WDs. In for Stage 1 BRC - siteworks | Marie | Brenton G | TBC |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2025-01-17 | 2025-02-05 | n/a | n/a | 2025-02-06 | 2025-01-13 | 2025-02-03 | 2025-05-19 | 2025-06-24 | 2025-02-06 | 2025-03-04 | 2025-04-22 | n/a | [7 empty] | 2025-05-15 | 2025-06-02 | [6 empty] | 2025-03-11 | 2025-12-03 | [131 empty] | Elise
1033 | 26 | 1033-26 | 1699 | PWA | - | 2 | Luke Ave | Salisbury Downs | Res 26 | 2 Luke Ave, Salisbury Downs (Res 26) |  |  |  | Developer | Lofty Building Group | Dwelling has been dropped | Marie | Brenton G | TBC |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | Yes | 2025-01-17 | 2025-02-05 | n/a | n/a | 2025-02-06 | 2025-01-13 | 2025-02-03 | n/a | n/a | 2025-02-06 | 2025-03-04 | 2025-04-22 | n/a | [7 empty] | 2025-05-15 | 2025-06-02 | [6 empty] | 2025-03-11 | 2025-12-03 | [131 empty] | Elise
1034 | 01 | 1034-01 | 1704 | PWA | - | 28 | Guthrie Road | Christies Beach | Lot 1 | 28 Guthrie Road, Christies Beach (Lot 1) |  |  |  | Retail | Haume Group | 14/04 - Logged for PA | Marie | Mitch G | TBC |  | 1 | 0 | 1 | 2025-01-13 | 2025-01-15 | 2025-01-16 | 5000 |  | Yes | 2025-01-17 | 2025-01-24 | 2025-01-28 | 2025-01-30 | 2025-02-10 | 2025-01-16 | 2025-02-13 | 2025-02-27 | 2025-03-25 | 2025-02-10 | 2025-02-25 | 2025-02-27 | 2025-03-11 |  | 2025-02-27 | 2025-03-07 |  |  |  |  | 2025-02-17 | 2025-02-21 |  | 2025-03-18 | 2025-02-27 |  | 2025-02-27 | 2025-03-25 | 2025-03-19 | [132 empty] | Elise
1034 | 02 | 1034-02 | 1705 | PWA | - | 28 | Guthrie Road | Christies Beach | Lot 2 | 28 Guthrie Road, Christies Beach (Lot 2) |  |  |  | Retail | Haume Group | 14/04 - Logged for PA | Marie | Mitch G | TBC |  | 1 | 0 | 1 | 2025-01-13 | 2025-01-15 | 2025-01-16 | 5000 |  | Yes | 2025-01-17 | 2025-01-24 | 2025-01-28 | 2025-01-30 | 2025-02-10 | 2025-01-16 | 2025-02-13 | 2025-02-27 | 2025-03-25 | 2025-02-10 | 2025-02-25 | 2025-02-27 | 2025-03-11 |  | 2025-02-27 | 2025-03-07 |  |  |  |  | 2025-02-17 | 2025-02-21 |  | 2025-03-18 | 2025-02-27 |  | 2025-02-27 | 2025-03-25 | 2025-03-19 | [132 empty] | Elise
1034 | 03 | 1034-03 | 1706 | PWA | - | 28 | Guthrie Road | Christies Beach | Lot 3 | 28 Guthrie Road, Christies Beach (Lot 3) |  |  |  | Retail | Haume Group | 14/04 - Logged for PA | Marie | Mitch G | TBC |  | 1 | 0 | 1 | 2025-01-13 | 2025-01-15 | 2025-01-16 | 5000 |  | Yes | 2025-01-17 | 2025-01-24 | 2025-01-28 | 2025-01-30 | 2025-02-10 | 2025-01-16 | 2025-02-13 | 2025-02-27 | 2025-03-25 | 2025-02-10 | 2025-02-25 | 2025-02-27 | 2025-03-11 |  | 2025-02-27 | 2025-03-07 |  |  |  |  | 2025-02-17 | 2025-02-21 |  | 2025-03-18 | 2025-02-27 |  | 2025-02-27 | 2025-03-25 | 2025-03-19 | [132 empty] | Elise
1034 | 04 | 1034-04 | 1707 | PWA | - | 28 | Guthrie Road | Christies Beach | Lot 4 | 28 Guthrie Road, Christies Beach (Lot 4) |  |  |  | Retail | Haume Group | 14/04 - Logged for PA | Marie | Mitch G | TBC |  | 1 | 0 | 1 | 2025-01-13 | 2025-01-15 | 2025-01-16 | 5000 |  | Yes | 2025-01-17 | 2025-01-24 | 2025-01-28 | 2025-01-30 | 2025-02-10 | 2025-01-16 | 2025-02-13 | 2025-02-27 | 2025-03-25 | 2025-02-10 | 2025-02-25 | 2025-02-27 | 2025-03-11 |  | 2025-02-27 | 2025-03-07 |  |  |  |  | 2025-02-17 | 2025-02-21 |  | 2025-03-18 | 2025-02-27 |  | 2025-02-27 | 2025-03-25 | 2025-03-19 | [132 empty] | Elise
1034 | 05 | 1034-05 | 1708 | PWA | - | 28 | Guthrie Road | Christies Beach | Lot 5 | 28 Guthrie Road, Christies Beach (Lot 5) |  |  |  | Retail | Haume Group | 14/04 - Logged for PA | Marie | Mitch G | TBC |  | 1 | 0 | 1 | 2025-01-13 | 2025-01-15 | 2025-01-16 | 5000 |  | Yes | 2025-01-17 | 2025-01-24 | 2025-01-28 | 2025-01-30 | 2025-02-10 | 2025-01-16 | 2025-02-13 | 2025-02-27 | 2025-03-25 | 2025-02-10 | 2025-02-25 | 2025-02-27 | 2025-03-11 |  | 2025-02-27 | 2025-03-07 |  |  |  |  | 2025-02-17 | 2025-02-21 |  | 2025-03-18 | 2025-02-27 |  | 2025-02-27 |  | 2025-03-19 | [132 empty] | Elise
1034 | 06 | 1034-06 | 1709 | PWA | - | 28 | Guthrie Road | Christies Beach | Lot 6 | 28 Guthrie Road, Christies Beach (Lot 6) |  |  |  | Retail | Haume Group | 14/04 - Logged for PA | Marie | Mitch G | TBC |  | 1 | 0 | 1 | 2025-01-13 | 2025-01-15 | 2025-01-16 | 5000 |  | Yes | 2025-01-17 | 2025-01-24 | 2025-01-28 | 2025-01-30 | 2025-02-10 | 2025-01-16 | 2025-02-13 | 2025-02-27 | 2025-03-25 | 2025-02-10 | 2025-02-25 | 2025-02-27 | 2025-03-11 |  | 2025-02-27 | 2025-03-07 |  |  |  |  | 2025-02-17 | 2025-02-21 |  | 2025-03-18 | 2025-02-27 |  | 2025-02-27 | 2025-03-25 | 2025-03-19 | [132 empty] | Elise
1035 | 01 | 1035-01 | 1719 | PWA | - | 10 | Mortimer Ave (formally 15 Mckinlay) Gawler East |  |  | 10 Mortimer Ave (formally 15 Mckinlay) Gawler East |  |  |  | Retail | Kris Charles & David Bull | 9/06 - Framing quotes requested. Contract signed - deposit paid. In for WDs. Received final EER. AC layouts, window layouts to be ordered | Marie | Brenton G | TBC |  | 1 | 0 | 1 | 2025-04-29 | 2025-02-04 | 2025-03-21 | 5000 |  | Yes | 2025-02-04 | 2025-02-19 |  |  | 2025-03-25 |  |  |  |  | 2025-03-21 | 2025-04-04 | [9 empty] | 2025-09-16 | [140 empty] | Elise
1036 | 01 | 1036-01 | 1724 | PWA | On Hold | 8 | Henderson St | Henley Beach |  | 8 Henderson St, Henley Beach |  |  |  | Retail | Anthony Pizanias | 14/7 - Logged for FQC. ON HOLD | Marie | Mitch G |  |  | 0 | 1 | 1 | 2025-02-04 | 2025-02-04 | 2025-02-12 | 5000 |  | Yes | 2025-02-18 | 2025-03-06 | 2025-03-20 | 2025-04-07 | n/a | 2025-02-19 | 2025-03-17 | 2025-02-19 | 2025-03-26 | 2025-04-10 | 2025-06-03 | n/a | n/a | 2025-06-03 | 2025-06-17 | 2025-06-23 |  |  |  |  | 2025-04-17 | 2025-04-23 |  |  |  |  | 2025-06-24 | 2025-07-11 | 2025-03-28 | 2025-07-08 | [131 empty] | Elise
1036 | 02 | 1036-02 | 1725 | PWA | On Hold | 8 | Henderson St | Henley Beach |  | 8 Henderson St, Henley Beach |  |  |  | Retail | Anthony Pizanias | 14/7 - Logged for FQC. ON HOLD | Marie | Mitch G |  |  | 0 | 1 | 1 | 2025-02-04 | 2025-02-04 | 2025-02-12 | 5000 |  | Yes | 2025-02-18 | 2025-03-06 | 2025-03-20 | 2025-04-07 | n/a | 2025-02-19 | 2025-03-17 | 2025-02-19 | 2025-03-26 | 2025-04-10 | 2025-06-03 | n/a | n/a | 2025-06-03 | 2025-06-17 | 2025-06-23 |  |  |  |  | 2025-04-17 | 2025-04-23 |  |  |  |  | 2025-06-24 | 2025-07-11 | 2025-03-28 | 2025-07-08 | [131 empty] | Elise
1037 | 01 | 1037-01 | 1730 | PWA | - | 25 | Stanlake Ave | St Marys |  | 25 Stanlake Ave, St Marys |  |  |  | Retail | Parminder Singh | 13/01 - PA received. Logged for FQC. | Marie | Mitch G | TBC | no | 0 | 1 | 1 | 2025-02-25 | 2025-03-11 |  | 5000 |  |  | 2025-04-02 | 2025-04-24 | n/a | n/a | n/a | 2025-04-02 | 2025-04-14 | 2025-05-19 | 2025-06-06 | 2025-05-02 | 2025-06-02 | [9 empty] | 2025-04-28 | 2025-05-09 |  |  |  |  | 2025-06-10 | 2025-06-20 | 2025-03-28
1037 | 02 | 1037-02 | 1731 | PWA | - | 25 | Stanlake Ave | St Marys |  | 25 Stanlake Ave, St Marys |  |  |  | Retail | Parminder Singh | 13/01 - PA received. Logged for FQC. | Marie | Mitch G | TBC | No | 0 | 1 | 1 | 2025-02-25 | 2025-03-11 |  | 5000 |  |  | 2025-04-02 | 2025-02-24 | n/a | n/a | n/a | 2025-04-02 | 2025-04-14 | 2025-05-19 | 2025-06-06 | 2025-05-02 | 2002-06-02 | [9 empty] | 2025-04-28 | 2025-05-09 |  |  |  |  | 2025-06-10 | 2025-06-20 | 2025-03-28 | [132 empty] | Elise
1038 | 01 | 1038-01 | 1763 | PWA | - | 23 | Coronation Ave | Campbelltown | RES 1 | 23 Coronation Ave, Campbelltown RES 1 |  |  |  | Developer | Calatrava 1839 pty Ltd (Gerard Wong) | 02/06 -With council for Planning Approval |  | Brenton G |  |  | 1 | 0 | 1 | 2025-04-28 | 2025-06-03 | n/a | 5000 |  | yes | 2025-03-14 | 2025-03-17 |  |  |  | 2025-03-21 | 2025-04-11 | 2025-04-29 | 2025-05-20 | 2025-04-07 | 2025-05-14 | [9 empty] | 2025-05-14 | 2025-05-20 | [6 empty] | 2025-03-28 | [132 empty] | Elise
1038 | 02 | 1038-02 | 1764 | PWA | - | 23 | Coronation Ave | Campbelltown | RES 2 | 23 Coronation Ave, Campbelltown RES 2 |  |  |  | Developer | Calatrava 1839 pty Ltd (Gerard Wong) | 02/06 -With council for Planning Approval |  | Brenton G |  |  | 1 | 0 | 1 | 2025-04-28 | 2025-06-03 | n/a | 5000 |  | yes | 2025-03-14 | 2025-03-17 |  |  |  | 2025-03-21 | 2025-04-11 | 2025-04-29 | 2025-05-20 | 2025-04-07 | 2025-05-14 | [9 empty] | 2025-05-14 | 2025-05-20 | [6 empty] | 2025-03-28 | [132 empty] | Elise
1038 | 03 | 1038-03 | 1765 | PWA | - | 23 | Coronation Ave | Campbelltown | RES 3 | 23 Coronation Ave, Campbelltown RES 3 |  |  |  | Developer | Calatrava 1839 pty Ltd (Gerard Wong) | 02/06 -With council for Planning Approval |  | Brenton G |  |  | 1 | 0 | 1 | 2025-04-28 | 2025-06-03 | n/a | 5000 |  | yes | 2025-03-14 | 2025-03-17 |  |  |  | 2025-03-21 | 2025-04-11 | 2025-04-29 | 2025-05-20 | 2025-04-07 | 2025-05-14 | [9 empty] | 2025-05-14 | 2025-05-20 | [6 empty] | 2025-03-28 | [132 empty] | Elise
1038 | 04 | 1038-04 | 1766 | PWA |  | 23 | Coronation Ave | Campbelltown | RES 4 | 23 Coronation Ave, Campbelltown RES 4 |  |  |  | Developer | Calatrava 1839 pty Ltd (Gerard Wong) | 02/06 -With council for Planning Approval |  | Brenton G |  |  | 1 | 0 | 1 | 2025-04-28 | 2025-06-03 | n/a | 5000 |  | yes | 2025-03-14 | 2025-03-17 |  |  |  | 2025-03-21 | 2025-04-11 | 2025-04-29 | 2025-05-20 | 2025-04-07 | 2025-05-14 | [17 empty] | 2025-03-28
1038 | 05 | 1038-05 | 1767 | PWA |  | 23 | Coronation Ave | Campbelltown | RES 5 | 23 Coronation Ave, Campbelltown RES 5 |  |  |  | Developer | Calatrava 1839 pty Ltd (Gerard Wong) | 02/06 -With council for Planning Approval |  | Brenton G |  |  | 1 | 0 | 1 | 2025-04-28 | 2025-06-03 | n/a | 5000 |  | yes | 2025-03-04 | 2025-03-17 |  |  |  | 2025-03-21 | 2025-04-11 | 2025-04-29 | 2025-05-20 | 2025-04-07 | 2025-05-14 | [17 empty] | 2025-03-28
1039 | 01 | 1039-01 | 1752 | PWA | - | 9 | Alor Court | Noarlunga Downs | Lot 1 | 9 Alor Court, Noarlunga Downs Lot 1 |  |  |  | Retail | Li Dong (Astra Pacific Developments) | 29/06- FQC done. Frames ordered. FCR received. ON MARKET |  | Brenton G |  |  | TBA | TBA | TBA | 2025-03-27 | 2025-03-28 | 2025-04-01 | 5000 |  | yes | 2025-04-09 | 2025-04-30 |  |  |  | 2025-04-11 | 2025-05-21 | 2025-07-15 | 2025-07-25 | 2025-05-07 | 2025-06-17 | [9 empty] | 2025-06-24 | 2025-07-02 |  |  | 2025-07-25 | 2025-08-05 | 2025-09-25 |  | 2025-05-14 | 2025-09-25 | [131 empty] | Elise
1039 | 02 | 1039-02 | 1753 | PWA | - | 9 | Alor Court | Noarlunga Downs | Lot 2 | 9 Alor Court, Noarlunga Downs Lot 2 |  |  |  | Retail | Li Dong (Astra Pacific Developments) | 29/06- FQC done. Frames ordered. FCR received. ON MARKET |  | Brenton G |  |  | TBA | TBA | TBA | 2025-03-27 | 2025-03-28 | 2025-04-01 | 5000 |  | yes | 2025-04-09 | 2025-04-30 |  |  |  | 2025-04-11 | 2025-02-21 | 2025-07-15 | 2025-07-25 | 2025-05-07 | 2025-06-17 | [9 empty] | 2025-06-24 | 2025-07-02 |  |  | 2025-07-25 | 2025-08-05 | 2025-09-25 |  | 2025-05-14 | 2025-09-25 | [131 empty] | Elise
1039 | 03 | 1039-03 | 1754 | PWA | - | 9 | Alor Court | Noarlunga Downs | Lot 3 | 9 Alor Court, Noarlunga Downs Lot 3 |  |  |  | Retail | Li Dong (Astra Pacific Developments) | 29/06- FQC done. Frames ordered. FCR received. ON MARKET |  | Brenton G |  |  | TBA | TBA | TBA | 2025-03-27 | 2025-03-28 | 2025-04-01 | 5000 |  | yes | 2025-04-09 | 2025-04-30 |  |  |  | 2025-04-11 | 2025-05-21 | 2025-07-15 | 2025-07-25 | 2025-05-07 | 2025-06-17 | [9 empty] | 2025-06-24 | 2025-07-02 |  |  | 2025-07-25 | 2025-08-05 | 2025-09-25 |  | 2025-05-14 | 2025-09-25 | [131 empty] | Elise
1039 | 04 | 1039-04 | 1755 |  | - | 9 | Alor Court | Noarlunga Downs | Lot 4 | 9 Alor Court, Noarlunga Downs Lot 4 |  |  |  | Retail | Li Dong (Astra Pacific Developments) | 29/06- FQC done. Frames ordered. FCR received. ON MARKET |  |  |  |  | TBA | TBA | TBA | 2025-03-27 | 2025-03-28 | 2025-04-01 | 5000 |  | yes | 2025-04-09 | 2025-04-30 |  |  |  | 2025-04-11 | 2025-05-21 | 2025-07-15 | 2025-07-25 | 2025-05-07 | 2025-06-17 | [9 empty] | 2025-06-24 | 2025-07-02 |  |  | 2025-07-25 | 2025-08-05 | 2025-09-25 |  | 2025-05-14 | 2025-09-25
1039 | 05 | 1039-05 | 1756 | PWA | - | 9 | Alor Court | Noarlunga Downs | Lot 5 | 9 Alor Court, Noarlunga Downs Lot 5 |  |  |  | Retail | Li Dong (Astra Pacific Developments) | 29/06- FQC done. Frames ordered. FCR received. Contract deposit requested |  | Brenton G |  |  | TBA | TBA | TBA | 2025-03-27 | 2025-03-28 | 2025-04-01 | 5000 |  | yes | 2025-04-09 | 2025-04-30 |  |  |  | 2025-04-11 | 2025-05-21 | 2025-07-15 | 2025-07-25 | 2025-05-07 | 2025-06-17 | [9 empty] | 2025-06-24 | 2025-07-02 |  |  | 2025-07-25 | 2025-08-05 | 2025-09-25 |  | 2025-05-14 | 2025-09-25 | [131 empty] | Elise
1040 | 01 | 1040-01 | 1759 | PWA | - | 25 | Stratton Road | Elizabeth Downs | Lot 2 | 25 Stratton Road, Elizabeth Downs Lot 2 |  |  |  | Retail | Ben Scadden | 31/03 - On Market. Ordered frames |  | Mitch G |  |  | 1 | 0 | 1 | 2025-04-24 | 2025-04-24 | 2025-04-28 | 5000 |  | yes | 2025-05-02 | 2025-04-28 | n/a | n/a | 2025-05-20 | 2025-04-29 | 2025-05-16 | 2025-05-02 | 2025-05-27 | 2025-05-20 | 2025-06-26 | [9 empty] | 2025-05-21 | 2025-05-27 |  |  | 2025-08-28 | 2025-09-02 | 2025-07-15 | 2025-08-01 | 2025-07-09 | 2025-10-14 | [131 empty] | Liv
1040 | 02 | 1040-02 | 1760 | PWA | - | 25 | Stratton Road | Elizabeth Downs | Lot 1 | 25 Stratton Road, Elizabeth Downs Lot 1 |  |  |  | Retail | Ben Scadden | 10/06 - On Market. Received DA |  | Mitch G |  |  | 1 | 0 | 1 | 2025-04-24 | 2025-04-24 | 2025-04-28 | 5000 |  | yes | 2025-05-02 | 2025-04-28 | n/a | n/a | 2025-05-20 | 2025-04-29 | 2025-05-16 | 2025-05-02 | 2025-05-27 | 2025-05-20 | 2025-06-26 | [9 empty] | 2025-05-21 | 2025-05-27 |  |  | 2025-08-28 | 2025-09-02 | 2025-07-15 | 2025-08-01 | 2025-07-09 | 2025-10-14 | [131 empty] | Liv
1040 | 03 | 1040-03 | 1761 | PWA | - | 25 | Stratton Road | Elizabeth Downs | Lot 2 | 25 Stratton Road, Elizabeth Downs Lot 2 |  |  |  | Retail | Ben Scadden | 10/06 - On Market. Received DA |  | Mitch G |  |  | 1 | 0 | 1 | 2025-04-24 | 2025-04-24 | 2025-04-28 | 5000 |  | yes | 2025-05-02 | 2025-04-28 | n/a | n/a | 2025-05-20 | 2025-04-29 | 2025-05-16 | 2025-05-02 | 2025-05-27 | 2025-05-20 | 2025-06-26 | [9 empty] | 2025-05-21 | 2025-05-27 |  |  | 2025-08-28 | 2025-09-02 | 2025-07-15 | 2025-08-01 | 2025-07-09 | 2025-10-14 | [131 empty] | Liv
1040 | 04 | 1040-04 | 1762 | PWA | - | 25 | Stratton Road | Elizabeth Downs | Lot 3 | 25 Stratton Road, Elizabeth Downs Lot 3 | Ben Scadden | 24/11 - Second PSA Issued to Client | Liv |  | Ben Scadden | 10/06 - On Market. Received DA |  |  | 1 | 2025-04-24 | 2025-04-24 | 2025-04-28 | 5000 |  | yes | 2025-05-02 | 2025-04-28 | n/a | n/a | 2025-05-20 | 2025-04-29 | 2025-05-16 | 2025-05-02 | 2025-05-27 | 2025-05-20 | 2025-06-26 | [9 empty] | 2025-05-21 | 2025-05-27 |  |  | 2025-08-28 | 2025-09-02 | 2025-07-15 | 2025-08-01 | 2025-07-09 | 2025-10-14 | [136 empty] | 0 | 1
1041 | 01 | 1041-01 | 1768 | PWA | - | 233 | Hogarth Road | Elizabeth Grove | Lot 1 | 233 Hogarth Road, Elizabeth Grove Lot 1 |  |  |  | Retail | Li Dong ( Astra Pacific Projects) | 05/06 - ON MARKET. In for BRC |  | Brenton G |  |  | 1 | 0 | 1 | 2025-04-29 | 2025-04-30 | 2025-05-06 | 1000 |  | yes | 2025-05-06 | 2025-05-16 | 2025-06-02 | 2025-06-17 |  | 2025-05-16 | 2025-06-10 | 2025-06-16 | 2025-07-18 | 2025-07-10 | 2025-07-28 | [9 empty] | 2025-08-06 | 2025-09-22 | [6 empty] | 2025-08-16 | 2025-10-13 | [131 empty] | Liv
1041 | 02 | 1041-02 | 1769 | PWA | - | 233 | Hogarth Road | Elizabeth Grove | Lot 2 | 233 Hogarth Road, Elizabeth Grove Lot 2 |  |  |  | Retail | Li Dong ( Astra Pacific Projects) | 05/06 - ON MARKET. In for BRC |  | Brenton G |  |  | 1 | 0 | 1 | 2025-04-29 | 2025-04-30 | 2025-05-06 | 1000 |  | yes | 2025-05-06 | 2025-05-16 | 2025-06-02 | 2025-06-17 |  | 2025-05-16 | 2025-06-10 | 2025-06-16 | 2025-07-18 | 2025-07-10 | 2025-07-28 | [9 empty] | 2025-08-06 | [7 empty] | 2025-08-16 | 2025-10-13 | [131 empty] | Liv
1041 | 03 | 1041-03 | 1770 | PWA | - | 233 | Hogarth Road | Elizabeth Grove | Lot 3 | 233 Hogarth Road, Elizabeth Grove Lot 3 |  |  |  | Retail | Li Dong ( Astra Pacific Projects) | 05/06 - ON MARKET. In for BRC |  | Brenton G |  |  | 1 | 0 | 1 | 2025-04-29 | 2025-04-30 | 2025-05-06 | 1000 |  | yes | 2025-05-06 | 2025-05-16 | 2025-06-02 | 2025-06-17 |  | 2025-05-16 | 2025-06-10 | 2025-06-16 | 2025-07-18 | 2025-07-10 | 2025-07-28 | [9 empty] | 2025-08-06 | [7 empty] | 2025-08-16 | 2025-10-13 | [131 empty] | Liv
1041 | 04 | 1041-04 | 1771 | PWA | - | 233 | Hogarth Road | Elizabeth Grove | Lot 4 | 233 Hogarth Road, Elizabeth Grove Lot 4 |  |  |  | Retail | Li Dong ( Astra Pacific Projects) | 05/06 - ON MARKET. In for BRC |  | Brenton G |  |  | 1 | 0 | 1 | 2025-04-29 | 2025-04-30 | 2025-05-06 | 1000 |  | yes | 2025-05-06 | 2025-05-16 | 2025-06-02 | 2025-06-17 |  | 2025-05-16 | 2025-06-10 | 2025-06-16 | 2025-07-18 | 2025-07-10 | 2025-07-28 | [9 empty] | 2025-08-06 | [7 empty] | 2025-08-16 | 2025-10-13 | [131 empty] | Liv
1041 | 05 | 1041-05 | 1772 | PWA | - | 233 | Hogarth Road | Elizabeth Grove | Lot 5 | 233 Hogarth Road, Elizabeth Grove Lot 5 |  |  |  | Retail | Li Dong ( Astra Pacific Projects) | 05/06 - ON MARKET. In for BRC |  | Brenton G |  |  | 1 | 0 | 1 | 2025-04-29 | 2025-04-30 | 2025-05-06 | 1000 |  | yes | 2025-05-06 | 2025-05-16 | 2025-06-02 | 2025-06-17 |  | 2025-05-16 | 2025-06-10 | 2025-06-16 | 2025-07-18 | 2025-07-10 | 2025-07-28 | [9 empty] | 2025-08-06 | [7 empty] | 2025-08-16 | 2025-10-13 | [131 empty] | Liv
1041 | 06 | 1041-06 | 1773 | PWA | - | 233 | Hogarth Road | Elizabeth Grove | Lot 6 | 233 Hogarth Road, Elizabeth Grove Lot 6 |  |  |  | Retail | Li Dong ( Astra Pacific Projects) | 27/6/25 Dropped a dwelling |  | Brenton G |  |  | 1 | 0 | 1 | 2025-04-29 | 2025-04-30 | 2025-05-06 | 1000 |  | yes | 2025-05-06 | 2025-05-16 | 2025-06-02 | 2025-06-17 |  | 2025-05-16 | 2025-06-10 | 2025-06-16 | 2025-07-18 | [152 empty] | Liv
1042 | 01 | 1042-01 | 1777 | PWA | - | 21 | Edmund st | Christie Downs | res1 | res1 , 21 Edmund st Christie Downs |  |  |  | Retail | Brenton Keogh | 18/5 - FQC amendments done. On Market. Fames Quotes received. |  | Mitch G |  |  | 1 | 0 | 1 | 2025-06-06 | 2025-06-10 | 2025-06-11 | 5000 |  | yes | 2025-06-11 | 2025-07-08 |  |  |  | 2025-06-11 | 2025-06-25 | 2025-06-19 | 2025-07-16 | 2025-07-09 | 2025-07-21 | [9 empty] | 2025-07-15 | 2025-07-17 |  |  |  |  | 2025-07-17 | 2025-07-24 | 2025-07-24 | 2025-09-30 | [131 empty] | Liv
1042 | 02 | 1042-02 | 1778 | PWA | - | 21 | Edmund st | Christie Downs | res2 | res2 , 21 Edmund st Christie Downs |  |  |  | Retail | Brenton Keogh | 18/5 - FQC amendments done. On Market. Fames Quotes received. |  | Mitch G |  |  | 1 | 0 | 1 | 2025-06-06 | 2025-06-10 | 2025-06-11 | 5000 |  | yes | 2025-06-11 | 2025-07-08 |  |  |  | 2025-06-11 | 2025-06-25 | 2025-06-19 | 2025-07-16 | 2025-07-09 | 2025-07-21 | [9 empty] | 2025-07-15 | 2025-07-17 |  |  |  |  | 2025-07-17 | 2025-07-24 | 2025-07-24 | 2025-09-30 | [131 empty] | Liv
1042 | 03 | 1042-03 | 1779 | PWA | - | 21 | Edmund st | Christie Downs | res3 | res3 , 21 Edmund st Christie Downs |  |  |  | Retail | Brenton Keogh | 18/5 - FQC amendments done. On Market. Fames Quotes received. |  | Mitch G |  |  | 1 | 0 | 1 | 2025-06-06 | 2025-06-10 | 2025-06-11 | 5000 |  | yes | 2025-06-11 | 2025-07-08 |  |  |  | 2025-06-11 | 2025-06-25 | 2025-06-19 | 2025-07-16 | 2025-07-09 | 2025-07-21 | [9 empty] | 2025-07-15 | 2025-07-17 |  |  |  |  | 2025-07-17 | 2025-07-24 | 2025-07-24 | 2025-09-30 | [131 empty] | Liv
1043 | 01 | 1043-01 | 1780 | PWA | - | 3 | Valiant Road | Port Willunga | Lot 1 | 3 Valiant Road, Port Willunga Lot 1 |  |  |  | Retail | Kelly & Adrian Borlace | 18/5 - Planning Approval Received. Pricing done. On Markert. Fames Quotes received. In for WDS |  | Brenton G |  |  | 1 | 0 | 1 | 2025-05-23 | 2025-06-11 | 2025-06-19 | 5000 |  | yes | 2025-06-30 | 2025-08-11 |  |  |  | 2025-06-13 | 2025-06-25 | [22 empty] | 2026-01-06 | [131 empty] | Liv
1043 | 02 | 1043-02 | 1781 | PWA | - | 3 | Valiant Road | Port Willunga | Lot 2 | 3 Valiant Road, Port Willunga Lot 2 |  |  |  | Retail | Kelly & Adrian Borlace | 25/05 - Contract sent |  | Brenton G |  |  | 1 | 0 | 1 | 2025-05-23 | 2025-06-11 | 2025-06-19 | 5000 |  | yes | 2025-06-30 | 2025-08-11 |  |  |  | 2025-06-13 | 2025-06-25 | [22 empty] | 2026-01-06 | [131 empty] | Liv
1043 | 03 | 1043-03 | 1782 | PWA | - | 3 | Valiant Road | Port Willunga | Lot 3 | 3 Valiant Road, Port Willunga Lot 3 |  |  |  | Retail | Kelly & Adrian Borlace | 25/05 - Contract sent |  | Brenton G |  |  | 1 | 0 | 1 | 2025-05-23 | 2025-06-11 | 2025-06-19 | 5000 |  | yes | 2025-06-30 | 2025-08-11 |  |  |  | 2025-06-13 | 2025-06-25 | [22 empty] | 2026-01-06 | [131 empty] | Liv
1044 | 01 | 1044-01 | 1783 | PWA | - | 1 | Chapman Street | Findon (single build) |  | 1 Chapman Street, Findon (single build) |  |  |  | Retail | Vivian Sian | 26/5 - PA received. Logged for FQC. Received EER - Windows quotes requested. Received prelim civils |  | Brenton G |  |  | 1 | 0 | 1 | 2025-06-25 | 2025-06-27 | 2025-06-30 | 1000 |  | yes | 2025-06-30 | [160 empty] | Liv
1045 | 01 | 1045-01 | 1784 | PWA | - | 31 | Raggatt Cres | Mitchell Park | Lot 1 | 31 Raggatt Cres, Mitchell Park Lot 1 |  |  |  | Retail | Binod Poudel | 15/06 - ON MARKET. Frame quotes received. In for FCR. Selections comepleted |  | Brenton G |  |  | 1 | 0 | 1 | 2025-07-01 | 2025-07-01 | 2025-07-08 | 5000 |  | yes | 2025-07-17 |  |  |  |  | 2025-08-04 | 2025-08-27 |  |  | 2025-08-27 | [10 empty] | 2025-09-22 | [8 empty] | 2026-01-13 | [131 empty] | Liv
1045 | 02 | 1045-02 | 1785 | PWA | - | 31 | Raggatt Cres | Mitchell Park | Lot 2 | 31 Raggatt Cres, Mitchell Park Lot 2 |  |  |  | Retail | Binod Poudel | 15/06 - ON MARKET. Frame quotes received. In for FCR. In selections |  | Brenton G |  |  | 1 | 0 | 1 | 2025-07-01 | 2025-07-01 | 2025-07-08 | 5000 |  | yes | 2025-07-17 |  |  |  |  | 2025-08-04 | 2025-08-02 |  |  | 2025-08-27 | [10 empty] | 2025-09-22 | [8 empty] | 2026-01-13 | [131 empty] | Liv
1045 | 03 | 1045-03 | 1786 | PWA | - | 31 | Raggatt Cres | Mitchell Park | Lot 3 | 31 Raggatt Cres, Mitchell Park Lot 3 |  |  |  | Retail | Binod Poudel | 15/06 - ON MARKET. Frame quotes received. In for FCR. Selections comepleted |  | Brenton G |  |  | 1 | 0 | 1 | 2025-07-01 | 2025-07-01 | 2025-07-08 | 5000 |  | yes | 2025-07-17 |  |  |  |  | 2025-08-04 | 2025-08-27 |  |  | 2025-08-27 | [10 empty] | 2025-09-22 | [8 empty] | 2026-01-13 | [131 empty] | Liv
1046 | 01 | 1046-01 | 1787 | PWA | - | 1 | Fowlers Road | Glenunga | Lot 1 | 1 Fowlers Road, Glenunga Lot 1 |  |  |  | Developer | lofty building group | 9/06 - Contract completed. HOWs ordered. In for selections. FCR received. Windows received. Frames ordered. Demo done. Stage 1 DA achievd. Awaiting pegging plans |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | yes | 2025-07-03 | 2025-07-11 | 2025-07-25 | 2025-08-06 |  | 2025-07-03 | 2025-07-23 |  |  | 2025-08-08 | 2025-08-13 | [9 empty] | 2025-08-08 | 2025-08-13 | [6 empty] | 2025-08-15 | 2025-12-04 | [131 empty] | Liv
1046 | 02 | 1046-02 | 1788 | PWA | - | 1 | Fowlers Road | Glenunga | Lot 2 | 1 Fowlers Road, Glenunga Lot 2 |  |  |  | Developer | lofty building group | 9/06 - Contract completed. HOWs ordered. In for selections. FCR received. Windows received. Frames ordered. Demo done. Stage 1 DA achievd. Awaiting pegging plans |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | yes | 2025-07-03 | 2025-07-11 | 2025-07-25 | 2025-08-06 |  | 2025-07-03 | 2025-07-23 |  |  | 2025-08-08 | 2025-08-13 | [9 empty] | 2025-08-08 | 2025-08-13 | [6 empty] | 2025-08-15 | 2025-12-04 | [131 empty] | Liv
1046 | 03 | 1046-03 | 1789 | PWA | - | 1 | Fowlers Road | Glenunga | Lot 3 | 1 Fowlers Road, Glenunga Lot 3 |  |  |  | Developer | lofty building group | 9/06 - Contract completed. HOWs ordered. In for selections. FCR received. Windows received. Frames ordered. Demo done. Stage 1 DA achievd. Awaiting pegging plans |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | yes | 2025-07-03 | 2025-07-11 | 2025-07-25 | 2025-08-06 |  | 2025-07-03 | 2025-07-23 |  |  | 2025-08-08 | 2025-08-13 | [9 empty] | 2025-08-08 | 2025-08-13 | [6 empty] | 2025-08-15 | 2025-12-04 | [131 empty] | Liv
1046 | 04 | 1046-04 | 1790 | PWA | - | 1 | Fowlers Road | Glenunga | Lot 4 | 1 Fowlers Road, Glenunga Lot 4 |  |  |  | Developer | lofty building group | 9/06 - Contract completed. HOWs ordered. In for selections. FCR received. Windows received. Frames ordered. Demo done. Stage 1 DA achievd. Awaiting pegging plans |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | yes | 2025-07-03 | 2025-07-11 | 2025-07-25 | 2025-08-06 |  | 2025-07-03 | 2025-07-23 |  |  | 2025-08-08 | 2025-08-13 | [9 empty] | 2025-08-08 | 2025-08-13 | [6 empty] | 2025-08-15 | 2025-12-04 | [131 empty] | Liv
1046 | 05 | 1046-05 | 1791 | PWA | - | 1 | Fowlers Road | Glenunga | Lot 5 | 1 Fowlers Road, Glenunga Lot 5 |  |  |  | Developer | lofty building group | 9/06 - Contract completed. HOWs ordered. In for selections. FCR received. Windows received. Frames ordered. Demo done. Stage 1 DA achievd. Awaiting pegging plans |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | yes | 2025-07-03 | 2025-07-11 | 2025-07-25 | 2025-08-06 |  | 2025-07-03 | 2025-07-23 |  |  | 2025-08-08 | 2025-08-13 | [9 empty] | 2025-08-08 | 2025-08-13 | [6 empty] | 2025-08-15 | 2025-12-04 | [131 empty] | Liv
1047 | 01 | 1047-01 | 1792 | PWA | - | 13 | Lowan Drive | Ingle Farm | Lot 1 | 13 Lowan Drive, Ingle Farm Lot 1 |  |  |  | Retail | Armando Tascione | 25/5 - Deposit paid. Framing quotes done. In for WDs |  | Brenton G |  |  | 1 | 0 | 1 | 2025-07-07 | 2025-07-08 | 2025-07-09 | 5000 |  | yes | 2025-07-15 |  |  |  |  | 2025-08-04 | 2025-08-15 | 2025-08-27 | [12 empty] | 2025-09-04 | [8 empty] | 2026-02-26 | [131 empty] | Liv
1047 | 02 | 1047-02 | 1793 | PWA | - | 13 | Lowan Drive | Ingle Farm | Lot 2 | 13 Lowan Drive, Ingle Farm Lot 2 |  |  |  | Retail | Armando Tascione | 25/5 - Deposit paid. Framing quotes done. In for WDs |  | Brenton G |  |  | 1 | 0 | 1 | 2025-07-07 | 2025-07-08 | 2025-07-09 | 5000 |  | yes | 2025-07-15 |  |  |  |  | 2025-08-04 | 2025-08-15 | 2025-08-27 | [12 empty] | 2025-09-04 | [8 empty] | 2026-02-26 | [131 empty] | Liv
1047 | 03 | 1047-03 | 1794 | PWA | - | 13 | Lowan Drive | Ingle Farm | Lot 3 | 13 Lowan Drive, Ingle Farm Lot 3 |  |  |  | Retail | Armando Tascione | 25/5 - Deposit paid. Framing quotes done. In for WDs |  | Brenton G |  |  | 1 | 0 | 1 | 2025-07-07 | 2025-07-08 | 2025-07-09 | 5000 |  | yes | 2025-07-15 |  |  |  |  | 2025-08-04 | 2025-08-15 | 2025-08-27 | [12 empty] | 2025-09-04 | [8 empty] | 2026-02-26 | [131 empty] | Liv
1048 | 01 | 1048-01 | 1798 | PWA | - | 57 | Martins Road | Salisbury | Lot 1 | 57 Martins Road, Salisbury Lot 1 |  |  |  | Developer | lofty building group | 26/5 - PA received. To be on Market. FQC completed. Frames quotes done. |  | Brenton G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | yes | 2025-08-06 |  |  |  |  | n/a | n/a | [154 empty] | LIv
1048 | 02 | 1048-02 | 1799 | PWA | - | 57 | Martins Road | Salisbury | Lot 2 | 57 Martins Road, Salisbury Lot 2 |  |  |  | Developer | lofty building group | 26/5 - PA received. To be on Market. FQC completed. Frames quotes done. |  | Brenton G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | yes | 2025-08-06 |  |  |  |  | n/a | n/a | [154 empty] | LIv
1048 | 03 | 1048-03 | 1800 | PWA | - | 57 | Martins Road | Salisbury | Lot 3 | 57 Martins Road, Salisbury Lot 3 |  |  |  | Developer | lofty building group | 26/5 - PA received. To be on Market. FQC completed. Frames quotes done. |  | Brenton G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | yes | 2025-08-06 |  |  |  |  | n/a | n/a | [154 empty] | LIv
1049 | 01 | 1049-01 | 1801 | PWA | - | 2-4 | Tweed Ave | Marion | Lot 1 | 2-4 Tweed Ave, Marion Lot 1 |  |  |  | Retail | Jarrad Hirst | 2/06- With council. Frame quotes received |  | Brenton G |  |  | 1 | 0 | 1 | 2025-07-04 | 2025-07-16 | 2025-07-16 |  |  | yes | 2025-07-28 | [160 empty] | LIv
1049 | 02 | 1049-02 | 1802 | PWA | - | 2-4 | Tweed Ave | Marion | Lot 1 | 2-4 Tweed Ave, Marion Lot 1 |  |  |  | Retail | Jarrad Hirst | 2/06- With council. Frame quotes received |  | Brenton G |  |  | 1 | 0 | 1 | 2025-07-04 | 2025-07-16 | 2025-07-16 |  |  | yes | 2025-07-28 | [160 empty] | LIv
1049 | 03 | 1049-03 | 1803 | PWA | - | 2-4 | Tweed Ave | Marion | Lot 3 | 2-4 Tweed Ave, Marion Lot 3 |  |  |  | Retail | Jarrad Hirst | 2/06- With council. Frame quotes received |  | Brenton G |  |  | 1 | 0 | 1 | 2025-07-04 | 2025-07-16 | 2025-07-16 |  |  | yes | 2025-07-28 | [160 empty] | LIv
1049 | 04 | 1049-04 | 1804 | PWA | - | 2-4 | Tweed Ave | Marion | Lot 4 | 2-4 Tweed Ave, Marion Lot 4 |  |  |  | Retail | Jarrad Hirst | 2/06- With council. Frame quotes received |  | Brenton G |  |  | 1 | 0 | 1 | 2025-07-04 | 2025-07-16 | 2025-07-16 |  |  | yes | 2025-07-28 | [160 empty] | LIv
1049 | 05 | 1049-05 | 1805 | PWA | - | 2-4 | Tweed Ave | Marion | Lot 5 | 2-4 Tweed Ave, Marion Lot 5 |  |  |  | Retail | Jarrad Hirst | 2/06- With council. Frame quotes received |  | Brenton G |  |  | 1 | 0 | 1 | 2025-07-04 | 2025-07-16 | 2025-07-16 |  |  | yes | 2025-07-25 | [160 empty] | LIv
1050 | 01 | 1050-01 | 1825 | PWA | - | 40 | Alexander Cres | Christie Downs | Lot 1 | 40 Alexander Cres, Christie Downs Lot 1 |  |  |  | Retail | Brenton Keogh | 28/4 - ON HOLD |  | Mitch G |  |  | 1 | 0 | 1 | 2025-06-30 | 2025-07-24 | 2025-07-28 | 5000 |  | yes | 2025-07-30 |  |  |  |  | 2025-07-30 | 2025-09-12 | 2025-09-24 | [12 empty] | 2025-09-17 | 2025-09-23 |  |  |  |  | 2025-09-24 |  | 2025-09-24 | [132 empty] | Liv
1050 | 02 | 1050-02 | 1826 | PWA | - | 40 | Alexander Cres | Christie Downs | Lot 2 | 40 Alexander Cres, Christie Downs Lot 2 |  |  |  | Retail | Brenton Keogh | 28/4 - ON HOLD |  | Mitch G |  |  | 1 | 0 | 1 | 2025-06-30 | 2025-07-24 | 2025-07-28 | 5000 |  | yes | 2025-07-30 |  |  |  |  | 2025-07-30 | 2025-09-12 | 2025-09-24 | [12 empty] | 2025-09-17 | 2025-09-23 |  |  |  |  | 2025-09-24 |  | 2025-09-24 | [132 empty] | LIv
1050 | 03 | 1050-03 | 1827 | PWA | - | 40 | Alexander Cres | Christie Downs | Lot 3 | 40 Alexander Cres, Christie Downs Lot 3 |  |  |  | Retail | Brenton Keogh | 28/4 - ON HOLD |  | Mitch G |  |  | 1 | 0 | 1 | 2025-06-30 | 2025-07-24 | 2025-07-28 | 5000 |  | yes | 2025-07-30 |  |  |  |  | 2025-07-30 | 2025-09-12 | 2025-09-24 | [12 empty] | 2025-09-17 | 2025-09-23 |  |  |  |  | 2025-09-24 |  | 2025-09-24 | [132 empty] | Liv
1051 | 01 | 1051-01 | 1828 | PWA |  | 9 | Grafton / 42 Austral Avenue | Morphettville |  | 9 Grafton / 42 Austral Avenue, Morphettville |  |  |  | Developer | lofty building group | 23/06 - Final EER, FCR Received. AC layouts, window layouts and then framing docs to be ordered. In selections |  | Brenton G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | yes | 2025-08-08 | 2025-08-27 |  |  |  | 2025-08-04 | 2025-10-01 |  |  | 2025-09-16 | [10 empty] | 2025-10-01 | [7 empty] | 2025-10-11 | 2026-02-04 | [131 empty] | Liv
1051 | 02 | 1051-02 | 1829 | PWA | - | 9 | Grafton / 42 Austral Avenue | Morphettville |  | 9 Grafton / 42 Austral Avenue, Morphettville |  |  |  | Developer | lofty building group | 23/06 - Final EER, FCR Received. AC layouts, window layouts and then framing docs to be ordered. In for WDs update |  | Brenton G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | yes | 2025-08-08 | 2025-08-27 |  |  |  | 2025-08-04 | 2025-10-01 |  |  | 2025-09-16 | [10 empty] | 2025-10-01 | [7 empty] | 2025-10-11 | 2026-02-04 | [131 empty] | Liv
1051 | 03 | 1051-03 | 1830 | PWA | - | 9 | Grafton / 42 Austral Avenue | Morphettville |  | 9 Grafton / 42 Austral Avenue, Morphettville |  |  |  | Developer | lofty building group | 23/06 - Final EER, FCR Received. AC layouts, window layouts and then framing docs to be ordered. In for WDs update |  | Brenton G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | yes | 2025-08-08 | 2025-08-27 |  |  |  | 2025-08-04 | 2025-10-01 |  |  | 2025-09-16 | [10 empty] | 2025-10-01 | [7 empty] | 2025-10-11 | 2026-02-04 | [131 empty] | Liv
1051 | 04 | 1051-04 | 1831 | PWA | - | 9 | Grafton / 42 Austral Avenue | Morphettville |  | 9 Grafton / 42 Austral Avenue, Morphettville |  |  |  | Developer | lofty building group | 23/06 - Final EER, FCR Received. AC layouts, window layouts and then framing docs to be ordered. Contract deposit requested |  | Brenton G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | yes | 2025-08-05 | 2025-08-27 |  |  |  | 2025-08-05 | 2025-10-01 |  |  | 2025-09-16 | [10 empty] | 2025-10-01 | [7 empty] | 2025-10-11 | 2026-02-04 | [131 empty] | Liv
1051 | 05 | 1051-05 | 1832 | PWA | - | 9 | Grafton / 42 Austral Avenue | Morphettville |  | 9 Grafton / 42 Austral Avenue, Morphettville |  |  |  | Developer | lofty building group | 23/06 - Final EER, FCR Received. AC layouts, window layouts and then framing docs to be ordered. ON Market |  | Brenton G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | yes | 2025-08-05 | 2025-08-27 |  |  |  | 2025-08-05 | 2025-10-01 |  |  | 2025-09-16 | [10 empty] | 2025-10-01 | [7 empty] | 2025-10-11 | 2026-02-04 | [131 empty] | Liv
1051 | 06 | 1051-06 | 1833 | PWA | - | 9 | Grafton / 42 Austral Avenue | Morphettville |  | 9 Grafton / 42 Austral Avenue, Morphettville |  |  |  | Developer | lofty building group | 23/06 - Final EER, FCR Received. AC layouts, window layouts and then framing docs to be ordered. ON Market |  | Brenton G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  | yes | 2025-08-05 | 2025-08-27 |  |  |  | 2025-08-05 | 2025-10-01 |  |  | 2025-09-16 | [10 empty] | 2025-10-01 | [7 empty] | 2025-10-11 | 2026-02-04 | [131 empty] | Liv
1052 | 01 | 1052-01 | 1837 | PWA | - | 20 | Raggatt Cres | Mitchel Park |  | 20 Raggatt Cres, Mitchel Park |  |  |  | Retail | Robert Mwole | 29/06- Site Inspectioon completed. DA achieved. Selections completed. Settled |  | Brenton G |  |  | 1 | 0 | 1 | 2025-08-05 |  |  | 5000 |  |  | 2025-08-18 | 2025-08-25 |  |  |  | 2025-08-14 | 2025-09-04 |  |  | 2025-09-16 | [10 empty] | 2025-09-16 | 2025-09-23 | [6 empty] | 2025-10-04 | 2026-11-18 | [24 empty] | 2026-03-13 | [106 empty] | Liv
1052 | 02 | 1052-02 | 1838 | PWA | - | 20 | Raggatt Cres | Mitchel Park |  | 20 Raggatt Cres, Mitchel Park |  |  |  | Retail | Robert Mwole | 29/06- Site Inspectioon completed. DA achieved. WDs update requested |  | Brenton G |  |  | 1 | 0 | 1 | 2025-08-05 |  |  | 5000 |  |  | 2025-08-18 | 2025-08-25 |  |  |  | 2025-08-14 | 2025-09-04 |  |  | 2025-09-16 | [10 empty] | 2025-09-16 | 2025-09-23 | [6 empty] | 2025-10-04 | 2026-11-18 | [24 empty] | 2026-03-13 | [106 empty] | Liv
1052 | 03 | 1052-03 | 1839 | PWA | - | 20 | Raggatt Cres | Mitchel Park |  | 20 Raggatt Cres, Mitchel Park |  |  |  | Retail | Robert Mwole | 29/06- Site Inspectioon completed. DA achieved. In for selections |  | Brenton G |  |  | 1 | 0 | 1 | 2025-08-05 |  |  | 5000 |  |  | 2025-08-18 | 2025-08-25 |  |  |  | 2025-08-14 | 2025-09-04 |  |  | 2025-09-16 | [10 empty] | 2025-09-16 | 2025-09-23 | [6 empty] | 2025-10-04 | 2026-11-18 | [24 empty] | 2026-03-13 | [106 empty] | Liv
1053 | 01 | 1053-01 | 1840 | PWA | - | 41 | Maltarra Rd | Munno Para |  | 41 Maltarra Rd, Munno Para |  |  |  | Retail | Samuel Weldemichial | 9/06 - PA received. Speed cushion. FQC done- pricing with the clients. Frames quotes requested. Updated quotes with client |  | Brenton G |  |  | 1 | 0 | 1 | 2025-08-05 | 2025-08-06 | 2025-08-06 | 5000 |  |  | 2025-08-08 | 2025-08-20 |  |  |  | 2025-08-06 | 2025-08-19 | 2025-08-06 | 2025-08-20 | [5 empty] | 2025-09-05 | [5 empty] | 2025-09-05 | 2025-09-30 | [6 empty] | 2025-09-29 | 2026-03-06 | [131 empty] | Liv
1053 | 02 | 1053-02 | 1841 | PWA | - | 41 | Maltarra Rd | Munno Para |  | 41 Maltarra Rd, Munno Para |  |  |  | Retail | Samuel Weldemichial | 2/06 - PA received. Speed cushion. FQC done- pricing with the clients.. Frames quotes requested |  | Brenton G |  |  | 1 | 0 | 1 | 2025-08-05 | 2025-08-06 | 2025-08-06 | 5000 |  |  | 2025-08-08 | 2025-08-20 |  |  |  | 2025-08-06 | 2025-08-19 | 2025-08-06 | 2025-08-20 | [5 empty] | 2025-09-05 | [5 empty] | 2025-09-05 | 2025-09-30 | [6 empty] | 2025-09-29 | 2026-03-06 | [131 empty] | Liv
1053 | 03 | 1053-03 | 1842 | PWA | - | 41 | Maltarra Rd | Munno Para |  | 41 Maltarra Rd, Munno Para |  |  |  | Retail | Samuel Weldemichial | 2/06 - PA received. Speed cushion. FQC done- pricing with the clients.. Frames quotes requested |  | Brenton G |  |  | 1 | 0 | 1 | 2025-08-05 | 2025-08-06 | 2025-08-06 | 5000 |  |  | 2025-08-08 | 2025-08-20 |  |  |  | 2025-08-06 | 2025-08-19 | 2025-08-06 | 2025-08-20 | [5 empty] | 2025-09-05 | [5 empty] | 2025-09-05 | 2025-09-30 | [6 empty] | 2025-09-29 | 2026-03-06 | [131 empty] | Liv
1054 | 01 | 1054-01 | 1846 | PWA | - | 8 | Kareela Rd | (AKA 21 Jessamine ave) Reynella | Lot 1 | 8 Kareela Rd, (AKA 21 Jessamine ave) Reynella Lot 1 |  |  |  | Developer | lofty building group | 2/07 - PA received. FQC done. WDs done. Final EER received. AC layouts, window layouts and then framing docs to be ordered. On market |  | Brenton G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-09-30 |  |  |  |  | 2025-09-15 | [22 empty] | 2025-12-04 | 2026-03-03 | [131 empty] | Liv
1054 | 02 | 1054-02 | 1847 | PWA | - | 8 | Kareela Rd | (AKA 21 Jessamine ave) Reynella | Lot 2 | 8 Kareela Rd, (AKA 21 Jessamine ave) Reynella Lot 2 |  |  |  | Developer | lofty building group | 2/07 - PA received. FQC done. WDs done. Final EER received. AC layouts, window layouts and then framing docs to be ordered. On market |  | Brenton G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-09-30 |  |  |  |  | 2025-09-15 | [22 empty] | 2025-12-04 | 2026-03-03 | [131 empty] | Liv
1054 | 03 | 1054-03 | 1848 | PWA | - | 8 | Kareela Rd | (AKA 21 Jessamine ave) Reynella | Lot 3 | 8 Kareela Rd, (AKA 21 Jessamine ave) Reynella Lot 3 |  |  |  | Developer | lofty building group | 2/07 - PA received. FQC done. WDs done. Final EER received. AC layouts, window layouts and then framing docs to be ordered. On market |  | Brenton G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-09-30 |  |  |  |  | 2025-09-15 | [22 empty] | 2025-12-04 | 2026-03-03 | [131 empty] | Liv
1054 | 04 | 1054-04 | 1849 | PWA | - | 8 | Kareela Rd | (AKA 21 Jessamine ave) Reynella | Lot 4 | 8 Kareela Rd, (AKA 21 Jessamine ave) Reynella Lot 4 |  |  |  | Developer | lofty building group | 2/07 - PA received. FQC done. WDs done. Final EER received. AC layouts, window layouts and then framing docs to be ordered. On market |  | Brenton G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-09-30 |  |  |  |  | 2025-09-15 | [22 empty] | 2025-12-04 | 2026-03-03 | [131 empty] | Liv
1054 | 05 | 1054-05 | 1850 | PWA | - | 8 | Kareela Rd | (AKA 21 Jessamine ave) Reynella | Lot 5 | 8 Kareela Rd, (AKA 21 Jessamine ave) Reynella Lot 5 |  |  |  | Developer | lofty building group | 2/07 - PA received. FQC done. WDs done. Final EER received. AC layouts, window layouts and then framing docs to be ordered. On market |  | Brenton G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-09-30 |  |  |  |  | 2025-09-15 | [22 empty] | 2025-12-04 | 2026-03-03 | [131 empty] | Liv
1055 | 01 | 1055-01 | 1851 | PWA | - | 49 | Clifford St | Brooklyn Park | RES 1 | 49 Clifford St, Brooklyn Park RES 1 |  |  |  | Developer | lofty building group | 6/07 - Framing quotes received. Finale EER received. ON MARKET |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2005-09-25 |  |  |  |  | 2025-09-23 | [22 empty] | 2026-02-10 | 2026-05-13 | [131 empty] | Liv
1055 | 02 | 1055-02 | 1852 | PWA | - | 49 | Clifford St | Brooklyn Park | RES 2 | 49 Clifford St, Brooklyn Park RES 2 |  |  |  | Developer | lofty building group | 6/07 - Framing quotes received. Finale EER received. ON MARKET |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2005-09-25 |  |  |  |  | 2025-09-23 | [22 empty] | 2026-02-10 | 2026-05-13 | [131 empty] | 24/9 - With Mitch for review
1055 | 03 | 1055-03 | 1853 | PWA | - | 49 | Clifford St | Brooklyn Park | RES 3 | 49 Clifford St, Brooklyn Park RES 3 |  |  |  | Developer | lofty building group | 6/07 - Framing quotes received. Finale EER received. ON MARKET |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-09-25 |  |  |  |  | 2025-09-23 | [22 empty] | 2026-02-10 | 2026-05-13 | [131 empty] | Liv
1056 | 01 | 1056-01 | 1854 | PWA | - | 12 | Stewart Avenue | Aldinga Beach | res 1 | 12 Stewart Avenue, Aldinga Beach res 1 |  |  |  | Developer | lofty building group | 6/07 - FQC done. On Market. Framing quotes received. Final EER received |  | Brenton G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-09-24 |  |  |  |  | 2025-09-24 | [22 empty] | 2025-12-15 | 2026-05-06 | [131 empty] | Liv
1056 | 02 | 1056-02 | 1855 | PWA | - | 12 | Stewart Avenue | Aldinga Beach | res 2 | 12 Stewart Avenue, Aldinga Beach res 2 |  |  |  | Developer | lofty building group | 6/07 - FQC done. On Market. Framing quotes received. Final EER received |  | Brenton G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-09-24 |  |  |  |  | 2025-09-24 | [22 empty] | 2025-12-15 | 2026-05-06 | [131 empty] | Liv
1056 | 03 | 1056-03 | 1856 | PWA | - | 12 | Stewart Avenue | Aldinga Beach | res 3 | 12 Stewart Avenue, Aldinga Beach res 3 |  |  |  | Developer | lofty building group | 6/07 - FQC done. On Market. Framing quotes received. Final EER received |  | Brenton G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-09-24 |  |  |  |  | 2025-09-24 | [22 empty] | 2025-12-15 | 2026-05-06 | [131 empty] | Liv
1056 | 04 | 1056-04 | 1857 | PWA | - | 12 | Stewart Avenue | Aldinga Beach | res 4 | 12 Stewart Avenue, Aldinga Beach res 4 |  |  |  | Developer | lofty building group | 6/07 - FQC done. On Market. Framing quotes received. Final EER received |  | Brenton G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-09-24 |  |  |  |  | 2025-09-24 | [22 empty] | 2025-12-15 | 2026-05-06 | [131 empty] | Liv
1056 | 05 | 1056-05 | 1858 | PWA | - | 12 | Stewart Avenue | Aldinga Beach | res 5 | 12 Stewart Avenue, Aldinga Beach res 5 |  |  |  | Developer | lofty building group | 6/07 - FQC done. On Market. Framing quotes received. Final EER received |  | Brenton G |  |  | 1 | 0 | 1 | [6 empty] | 2025-09-24 |  |  |  |  | 2025-09-24 | [22 empty] | 2025-12-15 | 2026-05-06 | [131 empty] | Liv
1057 | 01 | 1057-01 | 1859 | PWA | - | 174 | Ridley Rd | Elizabeth Grove | Res 1 | 174 Ridley Rd, Elizabeth Grove Res 1 |  |  |  | Retail | Michael Weldemichial | 22/6 - PDs done. with council. ON MARKET |  | Mitch G |  |  | 1 | 0 | 1 | [6 empty] | 2025-09-25 | [160 empty] | Liv
1057 | 02 | 1057-02 | 1860 | PWA | - | 174 | Ridley Rd | Elizabeth Grove | Res 2 | 174 Ridley Rd, Elizabeth Grove Res 2 |  |  |  | Retail | Michael Weldemichial | 22/6 - PDs done. with council. ON MARKET |  | Mitch G |  |  | 1 | 0 | 1 | [6 empty] | 2025-09-25 | [160 empty] | Liv
1057 | 03 | 1057-03 | 1861 | PWA | - | 174 | Ridley Rd | Elizabeth Grove | Res 3 | 174 Ridley Rd, Elizabeth Grove Res 3 |  |  |  | Retail | Michael Weldemichial | 22/6 - PDs done. with council. ON MARKET |  | Mitch G |  |  | 1 | 0 | 1 | [6 empty] | 2025-09-25 | [160 empty] | Liv
1057 | 04 | 1057-04 | 1862 | PWA | - | 174 | Ridley Rd | Elizabeth Grove | Res 4 | 174 Ridley Rd, Elizabeth Grove Res 4 |  |  |  | Retail | Michael Weldemichial | 24/2 - Logged for concepts |  | Mitch G |  |  | 1 | 0 | 1 | [6 empty] | 2025-09-25 | [160 empty] | Liv
1058 | 01 | 1058-01 | 1863 | PWA | - | 63 | Woodlands Terrace | Edwardstown | RES 1 | 63 Woodlands Terrace, Edwardstown RES 1 |  |  |  | Developer | lofty building group | 29/6 - ON MARKET. Demo done. Pegging done- Site inspection to be reviewed . DA achieved |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-01 | [6 empty] | 2025-10-28 | [20 empty] | 2025-11-19 | 2026-01-16 | [131 empty] | Liv
1058 | 02 | 1058-02 | 1864 | PWA | - | 63 | Woodlands Terrace | Edwardstown | RES 2 | 63 Woodlands Terrace, Edwardstown RES 2 |  |  |  | Developer | lofty building group | 29/6 - ON MARKET. Demo done. Pegging done- Site inspection to be reviewed . DA achieved |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-01 | [6 empty] | 2025-10-28 | [20 empty] | 2025-11-19 | 2026-01-16 | [131 empty] | Liv
1058 | 03 | 1058-03 | 1865 | PWA |  | 63 | Woodlands Terrace | Edwardstown | RES 3 | 63 Woodlands Terrace, Edwardstown RES 3 |  |  |  | Developer | lofty building group | 29/6 - ON MARKET. Demo done. Pegging done- Site inspection to be reviewed . DA achieved |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-01 | [6 empty] | 2025-10-28 | [20 empty] | 2025-11-19 | 2026-01-16 | [131 empty] | Liv
1059 | 01 | 1059-01 | 1866 | PWA | - | 13 | Opal Road | Morphett Vale | Res 1 | 13 Opal Road Morphett Vale Res 1 |  |  |  | Developer | lofty building group | 29/06 - Deposit request sent. Received Final EER. FCR Received. Frames requested. Awaiting titles. Site inspection requested. |  | Brenton G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-04 | [28 empty] | 2026-02-06 | [131 empty] | Liv
1059 | 02 | 1059-02 | 1867 | PWA | - | 13 | Opal Road | Morphett Vale | Res 2 | 13 Opal Road Morphett Vale Res 2 |  |  |  | Developer | lofty building group | 29/06 - Deposit request sent. Received Final EER. FCR Received. Frames requested. Awaiting titles. Site inspection requested. |  | Brenton G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-04 | [28 empty] | 2026-02-06 | [131 empty] | Liv
1059 | 03 | 1059-03 | 1868 | PWA | - | 13 | Opal Road | Morphett Vale | Res 3 | 13 Opal Road Morphett Vale Res 3 |  |  |  | Developer | lofty building group | 29/06 - Deposit request sent. Received Final EER. FCR Received. Frames requested. Awaiting titles. Site inspection requested. |  | Brenton G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-04 | [28 empty] | 2026-02-06 | [131 empty] | Liv
1060 | 01 | 1060-01 | 1869 | PWA | - | 567 | Portrush Road | Glenunga | Res 1 | 567 Portrush Road, Glenunga Res 1 |  |  |  | Retail | Kylie Herbert | 31/03- Concepts amendments with clients |  | Brenton G |  |  | 1 | 0 | 1 | [167 empty] | Liv
1060 | 02 | 1060-02 | 1870 | PWA | - | 567 | Portrush Road | Glenunga | Res 2 | 567 Portrush Road, Glenunga Res 2 |  |  |  | Retail | Kylie Herbert | 31/03- Concepts amendments with clients |  | Brenton G |  |  | 1 | 0 | 1 | [167 empty] | Liv
1060 | 03 | 1060-03 | 1871 | PWA | - | 567 | Portrush Road | Glenunga | Res 3 | 567 Portrush Road, Glenunga Res 3 |  |  |  | Retail | Kylie Herbert | 31/03- Concepts amendments with clients |  | Brenton G |  |  | 1 | 0 | 1 | [167 empty] | Liv
1060 | 04 | 1060-04 | 1872 | PWA | - | 567 | Portrush Road | Glenunga | Res 4 | 567 Portrush Road, Glenunga Res 4 |  |  |  | Retail | Kylie Herbert | 31/03- Concepts amendments with clients |  | Brenton G |  |  | 1 | 0 | 1 | [167 empty] | Liv
1061 | 01 | 1061-01 | 1873 | PWA | - | 113 | Liguria Cres | Noarlunga Downs | Res 1 | 113 Liguria Cres, Noarlunga Downs 1 |  |  |  | Developer | lofty building group | 19/5 - PDs done. To be in for PA |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-04-30 | [132 empty] | Liv
1061 | 02 | 1061-02 | 1874 | PWA | - | 113 | Liguria Cres | Noarlunga Downs | Res 2 | 113 Liguria Cres, Noarlunga Downs 2 |  |  |  | Developer | lofty building group | 19/5 - PDs done. To be in for PA |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-04-30 | [132 empty] | Liv
1061 | 03 | 1061-03 | 1875 | PWA | - | 113 | Liguria Cres | Noarlunga Downs | Res 3 | 113 Liguria Cres, Noarlunga Downs 3 |  |  |  | Developer | lofty building group | 19/5 - PDs done. To be in for PA |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-04-30 | [132 empty] | Liv
1061 | 04 | 1061-04 | 1876 | PWA | - | 113 | Liguria Cres | Noarlunga Downs | Res 4 | 113 Liguria Cres, Noarlunga Downs 4 |  |  |  | Developer | lofty building group | 19/5 - PDs done. To be in for PA |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-04-30 | [132 empty] | Liv
1061 | 05 | 1061-05 | 1877 | PWA | - | 113 | Liguria Cres | Noarlunga Downs | Res 5 | 113 Liguria Cres, Noarlunga Downs 5 |  |  |  | Developer | lofty building group | 19/5 - PDs done. To be in for PA |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-04-30 | [132 empty] | Liv
1061 | 06 | 1061-06 | 1878 | PWA | - | 113 | Liguria Cres | Noarlunga Downs | Res 6 | 113 Liguria Cres, Noarlunga Downs 6 |  |  |  | Developer | lofty building group | 19/5 - PDs done. To be in for PA |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-04-30 | [132 empty] | Liv
1061 | 07 | 1061-07 | 1879 | PWA | - | 113 | Liguria Cres | Noarlunga Downs | Res 7 | 113 Liguria Cres, Noarlunga Downs 7 |  |  |  | Developer | lofty building group | 19/5 - PDs done. To be in for PA |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-04-30 | [132 empty] | Liv
1061 | 08 | 1061-08 | 1880 | PWA | - | 113 | Liguria Cres | Noarlunga Downs | Res 8 | 113 Liguria Cres, Noarlunga Downs 8 |  |  |  | Developer | lofty building group | 19/5 - PDs done. To be in for PA |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-04-30 | [132 empty] | Liv
1061 | 09 | 1061-09 | 1881 | PWA | - | 113 | Liguria Cres | Noarlunga Downs | Res 9 | 113 Liguria Cres, Noarlunga Downs 9 |  |  |  | Developer | lofty building group | 19/5 - PDs done. To be in for PA |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-04-30 | [132 empty] | Liv
1061 | 10 | 1061-10 | 1882 | PWA | - | 113 | Liguria Cres | Noarlunga Downs | Res 10 | 113 Liguria Cres, Noarlunga Downs 10 |  |  |  | Developer | lofty building group | 19/5 - PDs done. To be in for PA |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-04-30 | [132 empty] | Liv
1061 | 11 | 1061-11 | 1883 | PWA | - | 113 | Liguria Cres | Noarlunga Downs | Res 11 | 113 Liguria Cres, Noarlunga Downs 11 |  |  |  | Developer | lofty building group | 19/5 - PDs done. To be in for PA |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-04-30 | [132 empty] | Liv
1061 | 12 | 1061-12 | 1884 | PWA | - | 113 | Liguria Cres | Noarlunga Downs | Res 12 | 113 Liguria Cres, Noarlunga Downs 12 |  |  |  | Developer | lofty building group | 19/5 - PDs done. To be in for PA |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-04-30 | [132 empty] | Liv
1061 | 13 | 1061-13 | 1885 | PWA | - | 113 | Liguria Cres | Noarlunga Downs | Res 13 | 113 Liguria Cres, Noarlunga Downs 13 |  |  |  | Developer | lofty building group | 19/5 - PDs done. To be in for PA |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-04-30 | [132 empty] | Liv
1061 | 14 | 1061-14 | 1886 | PWA | - | 113 | Liguria Cres | Noarlunga Downs | Res 14 | 113 Liguria Cres, Noarlunga Downs 14 |  |  |  | Developer | lofty building group | 19/5 - PDs done. To be in for PA |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-04-30 | [132 empty] | Liv
1061 | 15 | 1061-15 | 1887 | PWA | - | 113 | Liguria Cres | Noarlunga Downs | Res 15 | 113 Liguria Cres, Noarlunga Downs 15 |  |  |  | Developer | lofty building group | 19/5 - PDs done. To be in for PA |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-04-30 | [132 empty] | Liv
1061 | 16 | 1061-16 | 1888 | PWA | - | 113 | Liguria Cres | Noarlunga Downs | Res 16 | 113 Liguria Cres, Noarlunga Downs 16 |  |  |  | Developer | lofty building group | 19/5 - PDs done. To be in for PA |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-04-30 | [132 empty] | Liv
1061 | 17 | 1061-17 | 1889 | PWA | - | 113 | Liguria Cres | Noarlunga Downs | Res 17 | 113 Liguria Cres, Noarlunga Downs 17 |  |  |  | Developer | lofty building group | 19/5 - PDs done. To be in for PA |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-04-30 | [132 empty] | Liv
1061 | 18 | 1061-18 | 1890 | PWA | - | 113 | Liguria Cres | Noarlunga Downs | Res 18 | 113 Liguria Cres, Noarlunga Downs 18 |  |  |  | Developer | lofty building group | 19/5 - PDs done. To be in for PA |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-04-30 | [132 empty] | Liv
1061 | 19 | 1061-19 | 1891 | PWA | - | 113 | Liguria Cres | Noarlunga Downs | Res 19 | 113 Liguria Cres, Noarlunga Downs 19 |  |  |  | Developer | lofty building group | 19/5 - PDs done. To be in for PA |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-04-30 | [132 empty] | Liv
1061 | 20 | 1061-20 | 1892 | PWA | - | 113 | Liguria Cres | Noarlunga Downs | Res 20 | 113 Liguria Cres, Noarlunga Downs 20 |  |  |  | Developer | lofty building group | 19/5 - PDs done. To be in for PA |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-04-30 | [132 empty] | Liv
1061 | 21 | 1061-21 | 1893 | PWA | - | 113 | Liguria Cres | Noarlunga Downs | Res 21 | 113 Liguria Cres, Noarlunga Downs 21 |  |  |  | Developer | lofty building group | 19/5 - PDs done. To be in for PA |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-04-30 | [132 empty] | Liv
1061 | 22 | 1061-22 | 1894 | PWA | - | 113 | Liguria Cres | Noarlunga Downs | Res 22 | 113 Liguria Cres, Noarlunga Downs 22 |  |  |  | Developer | lofty building group | 19/5 - PDs done. To be in for PA |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-04-30 | [132 empty] | Liv
1061 | 23 | 1061-23 | 1895 | PWA | - | 113 | Liguria Cres | Noarlunga Downs | Res 23 | 113 Liguria Cres, Noarlunga Downs 23 |  |  |  | Developer | lofty building group | 19/5 - PDs done. To be in for PA |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-04-30 | [132 empty] | Liv
1061 | 24 | 1061-24 | 1896 | PWA | - | 113 | Liguria Cres | Noarlunga Downs | Res 24 | 113 Liguria Cres, Noarlunga Downs 24 |  |  |  | Developer | lofty building group | 19/5 - PDs done. To be in for PA |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-04-30 | [132 empty] | Liv
1061 | 25 | 1061-25 | 1897 | PWA | - | 113 | Liguria Cres | Noarlunga Downs | Res 25 | 113 Liguria Cres, Noarlunga Downs 25 |  |  |  | Developer | lofty building group | 19/5 - PDs done. To be in for PA |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-04-30 | [132 empty] | Liv
1061 | 26 | 1061-26 | 1898 | PWA | - | 113 | Liguria Cres | Noarlunga Downs | Res 26 | 113 Liguria Cres, Noarlunga Downs 26 |  |  |  | Developer | lofty building group | 19/5 - PDs done. To be in for PA |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-04-30 | [132 empty] | Liv
1061 | 27 | 1061-27 | 1899 | PWA | - | 113 | Liguria Cres | Noarlunga Downs | Res 27 | 113 Liguria Cres, Noarlunga Downs 27 |  |  |  | Developer | lofty building group | 19/5 - PDs done. To be in for PA |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-04-30 | [132 empty] | Liv
1061 | 28 | 1061-28 | 1900 | PWA | - | 113 | Liguria Cres | Noarlunga Downs | Res 28 | 113 Liguria Cres, Noarlunga Downs 28 |  |  |  | Developer | lofty building group | 19/5 - PDs done. To be in for PA |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-04-30 | [132 empty] | Liv
1061 | 29 | 1061-29 | 1901 | PWA | - | 113 | Liguria Cres | Noarlunga Downs | Res 29 | 113 Liguria Cres, Noarlunga Downs 29 |  |  |  | Developer | lofty building group | 19/5 - PDs done. To be in for PA |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-04-30 | [132 empty] | Liv
1061 | 30 | 1061-30 | 1902 | PWA | - | 113 | Liguria Cres | Noarlunga Downs | Res 30 | 113 Liguria Cres, Noarlunga Downs 30 |  |  |  | Developer | lofty building group | 19/5 - PDs done. To be in for PA |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-04-30 | [132 empty] | Liv
1061 | 31 | 1061-31 | 1903 | PWA | - | 113 | Liguria Cres | Noarlunga Downs | Res 31 | 113 Liguria Cres, Noarlunga Downs 31 |  |  |  | Developer | lofty building group | 19/5 - PDs done. To be in for PA |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-04-30 | [132 empty] | Liv
1061 | 32 | 1061-32 | 1904 | PWA | - | 113 | Liguria Cres | Noarlunga Downs | Res 32 | 113 Liguria Cres, Noarlunga Downs 32 |  |  |  | Developer | lofty building group | 19/5 - PDs done. To be in for PA |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-04-30 | [132 empty] | Liv
1061 | 33 | 1061-33 | 1905 | PWA | - | 113 | Liguria Cres | Noarlunga Downs | Res 33 | 113 Liguria Cres, Noarlunga Downs 33 |  |  |  | Developer | lofty building group | 19/5 - PDs done. To be in for PA |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-04-30 | [132 empty] | Liv
1061 | 34 | 1061-34 | 1906 | PWA | - | 113 | Liguria Cres | Noarlunga Downs | Res 34 | 113 Liguria Cres, Noarlunga Downs 34 |  |  |  | Developer | lofty building group | 19/5 - PDs done. To be in for PA |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-04-30 | [132 empty] | Liv
1061 | 35 | 1061-35 | 1907 | PWA | - | 113 | Liguria Cres | Noarlunga Downs | Res 35 | 113 Liguria Cres, Noarlunga Downs 35 |  |  |  | Developer | lofty building group | 19/5 - PDs done. To be in for PA |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-04-30 | [132 empty] | Liv
1061 | 36 | 1061-36 | 1908 | PWA | - | 113 | Liguria Cres | Noarlunga Downs | Res 36 | 113 Liguria Cres, Noarlunga Downs 36 |  |  |  | Developer | lofty building group | 19/5 - PDs done. To be in for PA |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-04-30 | [132 empty] | Liv
1061 | 37 | 1061-37 | 1909 | PWA |  | 113 | Liguria Cres | Noarlunga Downs | Res 37 | 113 Liguria Cres, Noarlunga Downs 37 |  |  |  | Developer | lofty building group | 19/5 - PDs done. To be in for PA |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-04-30 | [132 empty] | Liv
1062 | 01 | 1062-01 | 1929 | PWA | - | 125 | Glengyle Tce | Plympton |  | 125 Glengyle Tce, Plympton |  |  |  | Developer | lofty building group | 29/6 - PA received. FQC done. In for WDs. Frames quotes received. ON MARKET |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-01-29 | 2026-04-28 | [131 empty] | Liv
1062 | 02 | 1062-02 | 1920 | PWA | - | 125 | Glengyle Tce | Plympton |  | 125 Glengyle Tce, Plympton |  |  |  | Developer | lofty building group | 29/6 - PA received. FQC done. In for WDs. Frames quotes received. ON MARKET |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-01-29 | 2026-04-28 | [131 empty] | Liv
1062 | 03 | 1062-03 | 1931 | PWA | - | 125 | Glengyle Tce | Plympton |  | 125 Glengyle Tce, Plympton |  |  |  | Developer | lofty building group | 29/6 - PA received. FQC done. In for WDs. Frames quotes received. ON MARKET |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-15 | [27 empty] | 2026-01-29 | 2026-04-28 | [131 empty] | Liv
1063 | 01 | 1063-01 | 1912 | PWA | - | 1 | Hamilton St / 6 Illford St | Vale Park | Res 1 | 1 Hamilton St / 6 Illford St, Vale Park Res 1 |  |  |  | Developer | lofty building group | 29/6 - Achieved PA. To be on market. In for FQC |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-21 | [27 empty] | 2026-01-12 | 2026-06-11 | [131 empty] | Liv
1063 | 02 | 1063-02 | 1913 | PWA | - | 1 | Hamilton St / 6 Illford St | Vale Park | Res 2 | 1 Hamilton St / 6 Illford St, Vale Park Res 2 |  |  |  | Developer | lofty building group | 29/6 - Achieved PA. To be on market. In for FQC |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-21 | [27 empty] | 2026-01-12 | 2026-06-11 | [131 empty] | Liv
1063 | 03 | 1063-03 | 1914 | PWA | - | 1 | Hamilton St / 6 Illford St | Vale Park | Res 3 | 1 Hamilton St / 6 Illford St, Vale Park Res 3 |  |  |  | Developer | lofty building group | 29/6 - Achieved PA. To be on market. In for FQC |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-21 | [27 empty] | 2026-01-12 | 2026-06-11 | [131 empty] | Liv
1063 | 04 | 1063-04 | 1915 | PWA | - | 1 | Hamilton St / 6 Illford St | Vale Park | Res 4 | 1 Hamilton St / 6 Illford St, Vale Park Res 4 |  |  |  | Developer | lofty building group | 29/6 - Achieved PA. To be on market. In for FQC |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-21 | [27 empty] | 2026-01-12 | 2026-06-11 | [131 empty] | Liv
1063 | 05 | 1063-05 | 1916 | PWA | - | 1 | Hamilton St / 6 Illford St | Vale Park | Res 5 | 1 Hamilton St / 6 Illford St, Vale Park Res 5 |  |  |  | Developer | lofty building group | 29/6 - Achieved PA. To be on market. In for FQC |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-21 | [27 empty] | 2026-01-12 | 2026-06-11 | [131 empty] | Liv
1063 | 06 | 1063-06 | 1917 | PWA | - | 1 | Hamilton St / 6 Illford St | Vale Park | Res 6 | 1 Hamilton St / 6 Illford St, Vale Park Res 6 |  |  |  | Developer | lofty building group | 29/6 - Achieved PA. To be on market. In for FQC |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-21 | [27 empty] | 2026-01-12 | 2026-06-11 | [131 empty] | Liv
1063 | 07 | 1063-07 | 1918 | PWA | - | 1 | Hamilton St / 6 Illford St | Vale Park | Res 7 | 1 Hamilton St / 6 Illford St, Vale Park Res 7 |  |  |  | Developer | lofty building group | 29/6 - Achieved PA. To be on market. In for FQC |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-21 | [27 empty] | 2026-01-12 | 2026-06-11 | [131 empty] | Liv
1063 | 08 | 1063-08 | 1919 | PWA | - | 1 | Hamilton St / 6 Illford St | Vale Park | Res 8 | 1 Hamilton St / 6 Illford St, Vale Park Res 8 |  |  |  | Developer | lofty building group | 29/6 - Achieved PA. To be on market. In for FQC |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-21 | [27 empty] | 2026-01-12 | 2026-06-11 | [131 empty] | Liv
1063 | 09 | 1063-09 | 1920 | PWA | - | 1 | Hamilton St / 6 Illford St | Vale Park | Res 9 | 1 Hamilton St / 6 Illford St, Vale Park Res 9 |  |  |  | Developer | lofty building group | 29/6 - Achieved PA. To be on market. In for FQC |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-21 | [27 empty] | 2026-01-12 | 2026-06-11 | [131 empty] | Liv
1064 | 01 | 1064-01 | 1921 | PWA | - | 7 | Stagg Drive | Tranmere | Res 1 | 7 Stagg Drive, Tranmere Res 1 |  |  |  | Retail | Adam Soininen | 29/6 - PA received. FQC done. 2nd PSA paid. Framing quotes received. ON MARKET. WDs done. Awaiting final EER |  | Brenton G |  |  | 1 | 0 | 1 | [6 empty] | 2025-10-21 | [27 empty] | 2026-01-20 | 2026-03-17 | [131 empty] | Liv
1064 | 02 | 1064-02 | 1922 | PWA |  | 7 | Stagg Drive | Tranmere | Res 2 | 7 Stagg Drive, Tranmere Res 2 |  |  |  | Retail | Adam Soininen | 29/6 - PA received. FQC done. 2nd PSA paid. Framing quotes received. ON MARKET. WDs done. Awaiting final EER |  | Brenton G |  |  | 1 | 0 | 1 | [6 empty] | 2025-10-21 | [27 empty] | 2026-01-20 | 2026-03-17 | [131 empty] | Liv
1064 | 03 | 1064-03 | 1923 | PWA | - | 7 | Stagg Drive | Tranmere | Res 3 | 7 Stagg Drive, Tranmere Res 3 |  |  |  | Retail | Adam Soininen | 29/6 - PA received. FQC done. 2nd PSA paid. Framing quotes received. ON MARKET. WDs done. Awaiting final EER |  | Brenton G |  |  | 1 | 0 | 1 | [6 empty] | 2025-10-21 | [27 empty] | 2026-01-20 | 2026-03-17 | [131 empty] | Liv
1065 | 01 | 1065-01 | 1924 | PWA | - | 82 | Grundy Tce | Christies Beach | Res 1 | 82 Grundy Tce, Christies Beach Res 1 |  |  |  | Developer | Lofty Building Group | 9/06 - Lodged back with council. Demo done |  | Brenton G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-21 | [27 empty] | 2025-12-19 | [132 empty] | Liv
1065 | 02 | 1065-02 | 1925 | PWA | - | 82 | Grundy Tce | Christies Beach | Res 2 | 82 Grundy Tce, Christies Beach Res 2 |  |  |  | Developer | Lofty Building Group | 9/06 - Lodged back with council. Demo done |  | Brenton G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-21 | [27 empty] | 2025-12-19 | [132 empty] | Liv
1065 | 03 | 1065-03 | 1926 | PWA | - | 82 | Grundy Tce | Christies Beach | Res 3 | 82 Grundy Tce, Christies Beach Res 3 |  |  |  | Developer | Lofty Building Group | 9/06 - Lodged back with council. Demo done |  | Brenton G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-21 | [27 empty] | 2025-12-19 | [132 empty] | Liv
1065 | 04 | 1065-04 | 1927 | PWA | - | 82 | Grundy Tce | Christies Beach | Res 4 | 82 Grundy Tce, Christies Beach Res 4 |  |  |  | Developer | Lofty Building Group | 9/06 - Lodged back with council. Demo done |  | Brenton G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-21 | [27 empty] | 2025-12-19 | [132 empty] | Liv
1065 | 05 | 1065-05 | 1928 | PWA | - | 82 | Grundy Tce | Christies Beach | Res 5 | 82 Grundy Tce, Christies Beach Res 5 |  |  |  | Developer | Lofty Building Group | 9/06 - Lodged back with council. Demo done |  | Brenton G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-10-21 | [27 empty] | 2025-12-19 | [132 empty] | Liv
1066 | 01 | 1066-01 | 1932 | PWA | - | 42-44 | Hubbard St | Beverley | Res 1 | 42-44 Hubbard St, Beverley Res 1 |  |  |  | Retail | Westside Housing | 9/02- With Client |  | Mitch G |  |  | 1 | 0 | 1 | [6 empty] | 2025-11-10 | [160 empty] | Liv
1066 | 02 | 1066-02 | 1933 | PWA | - | 42-44 | Hubbard St | Beverley | Res 2 | 42-44 Hubbard St, Beverley Res 2 |  |  |  | Retail | Westside Housing | 9/02- With Client |  | Mitch G |  |  | 1 | 0 | 1 | [6 empty] | 2025-11-10 | [160 empty] | Liv
1066 | 03 | 1066-03 | 1934 | PWA | - | 42-44 | Hubbard St | Beverley | Res 3 | 42-44 Hubbard St, Beverley Res 3 |  |  |  | Retail | Westside Housing | 9/02- With Client |  | Mitch G |  |  | 1 | 0 | 1 | [6 empty] | 2025-11-10 | [160 empty] | Liv
1067 | 01 | 1067-01 | 1935 | PWA | - | 26 | Kenner St | Elizabeth Downs | Res 1 | 26 Kenner St, Elizabeth Downs Res 1 |  |  |  | Retail | Westside Housing | 26/05- In for PDs |  | Mitch G |  |  | 1 | 0 | 1 | [6 empty] | 2025-11-10 | [160 empty] | Liv
1067 | 02 | 1067-02 | 1936 | PWA | - | 26 | Kenner St | Elizabeth Downs | Res 2 | 26 Kenner St, Elizabeth Downs Res 2 |  |  |  | Retail | Westside Housing | 26/05- In for PDs |  | Mitch G |  |  | 1 | 0 | 1 | [6 empty] | 2025-11-10 | [160 empty] | Liv
1067 | 03 | 1067-03 | 1937 | PWA | - | 26 | Kenner St | Elizabeth Downs | Res 3 | 26 Kenner St, Elizabeth Downs Res 3 |  |  |  | Retail | Westside Housing | 26/05- In for PDs |  | Mitch G |  |  | 1 | 0 | 1 | [6 empty] | 2025-11-10 | [160 empty] | Liv
1068 | 01 | 1068-01 | 1938 | PWA | - | 10 | Carousel St | Para Vista | Res 1 | 10 Carousel St, Para Vista Res 1 |  |  |  | Retail | Westside Housing | 18/05- In for PA. RFI. Frame quotes received. ON HOLD |  | Mitch G |  |  | 1 | 0 | 1 | [6 empty] | 2025-11-10 | [160 empty] | Liv
1068 | 02 | 1068-02 | 1939 | PWA | - | 10 | Carousel St | Para Vista | Res 2 | 10 Carousel St, Para Vista Res 2 |  |  |  | Retail | Westside Housing | 18/05- In for PA. RFI. Frame quotes received. ON HOLD |  | Mitch G |  |  | 1 | 0 | 1 | [6 empty] | 2025-11-10 | [160 empty] | Liv
1068 | 03 | 1068-03 | 1940 | PWA | - | 10 | Carousel St | Para Vista | Res 3 | 10 Carousel St, Para Vista Res 3 |  |  |  | Retail | Westside Housing | 18/05- In for PA. RFI. Frame quotes received. ON HOLD |  | Mitch G |  |  | 1 | 0 | 1 | [6 empty] | 2025-11-10 | [160 empty] | Liv
1069 | 01 | 1069-01 | 1941 | PWA | - | 43 | Balcombe Ave | Findon | Res 1 | 43 Balcombe Ave, Findon Res 1 |  |  |  | Developer | Lofty Building Group | 16/6 - PA achieved. FQC done. ON MARKET. In for WDs. Framing quotes received |  | Brenton G |  |  | 1 | 0 | 1 | [6 empty] | 2025-11-10 | [27 empty] | 2026-02-09 | 2026-04-29 | [131 empty] | Liv
1069 | 02 | 1069-02 | 1942 | PWA | - | 43 | Balcombe Ave | Findon | Res 2 | 43 Balcombe Ave, Findon Res 2 |  |  |  | Developer | Lofty Building Group | 16/6 - PA achieved. FQC done. ON MARKET. In for WDs. Framing quotes received |  | Brenton G |  |  | 1 | 0 | 1 | [6 empty] | 2025-11-10 | [27 empty] | 2026-02-09 | 2026-04-29 | [131 empty] | Liv
1069 | 03 | 1069-03 | 1943 | PWA | - | 43 | Balcombe Ave | Findon | Res 3 | 43 Balcombe Ave, Findon Res 3 |  |  |  | Developer | Lofty Building Group | 16/6 - PA achieved. FQC done. ON MARKET. In for WDs. Framing quotes received |  | Brenton G |  |  | 1 | 0 | 1 | [6 empty] | 2025-11-10 | [27 empty] | 2026-02-09 | 2026-04-29 | [131 empty] | Liv
1070 | 01 | 1070-01 | 1944 | PWA | - | 20 | Taylor Ave | Morphett Vale | Res 1 | Lot 20 Taylor Ave, Morphett Vale Res 1 |  |  |  | Developer | Lofty Building Group | 16/06- Logged for PA. Framing quotes received |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-11-12 | [27 empty] | 2026-01-20 | [132 empty] | Liv
1070 | 02 | 1070-02 | 1945 | PWA | - | 20 | Taylor Ave | Morphett Vale | Res 2 | Lot 20 Taylor Ave, Morphett Vale Res 2 |  |  |  | Developer | Lofty Building Group | 16/06- Logged for PA. Framing quotes received |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-11-12 | [27 empty] | 2026-01-20 | [132 empty] | Liv
1070 | 03 | 1070-03 | 1946 | PWA | - | 20 | Taylor Ave | Morphett Vale | Res 3 | Lot 20 Taylor Ave, Morphett Vale Res 3 |  |  |  | Developer | Lofty Building Group | 16/06- Logged for PA. Framing quotes received |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-11-12 | [27 empty] | 2026-01-20 | [132 empty] | Liv
1070 | 04 | 1070-04 | 1947 | PWA | - | 20 | Taylor Ave | Morphett Vale | Res 4 | Lot 20 Taylor Ave, Morphett Vale Res 4 |  |  |  | Developer | Lofty Building Group | 16/06- Logged for PA. Framing quotes received |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-11-12 | [27 empty] | 2026-01-20 | [132 empty] | Liv
1070 | 05 | 1070-05 | 1948 | PWA | - | 20 | Taylor Ave | Morphett Vale | Res 5 | Lot 20 Taylor Ave, Morphett Vale Res 5 |  |  |  | Developer | Lofty Building Group | 16/06- Logged for PA. Framing quotes received |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-11-12 | [27 empty] | 2026-01-20 | [132 empty] | Liv
1070 | 06 | 1070-06 | 1949 | PWA | - | 20 | Taylor Ave | Morphett Vale | Res 6 | Lot 20 Taylor Ave, Morphett Vale Res 6 |  |  |  | Developer | Lofty Building Group | 16/06- Logged for PA. Framing quotes received |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-11-12 | [27 empty] | 2026-01-20 | [132 empty] | Liv
1070 | 07 | 1070-07 | 1950 | PWA | - | 20 | Taylor Ave | Morphett Vale | Res 7 | Lot 20 Taylor Ave, Morphett Vale Res 7 |  |  |  | Developer | Lofty Building Group | 16/06- Logged for PA. Framing quotes received |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-11-12 | [27 empty] | 2026-01-20 | [132 empty] | Liv
1070 | 08 | 1070-08 | 1951 | PWA | - | 20 | Taylor Ave | Morphett Vale | Res 8 | Lot 20 Taylor Ave, Morphett Vale Res 8 |  |  |  | Developer | Lofty Building Group | 16/06- Logged for PA. Framing quotes received |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-11-12 | [27 empty] | 2026-01-20 | [132 empty] | Liv
1070 | 09 | 1070-09 | 1952 | PWA | - | 20 | Taylor Ave | Morphett Vale | Res 9 | Lot 20 Taylor Ave, Morphett Vale Res 9 |  |  |  | Developer | Lofty Building Group | 16/06- Logged for PA. Framing quotes received |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-11-12 | [27 empty] | 2026-01-20 | [132 empty] | Liv
1070 | 10 | 1070-10 | 1953 | PWA | - | 20 | Taylor Ave | Morphett Vale | Res 10 | Lot 20 Taylor Ave, Morphett Vale Res 10 |  |  |  | Developer | Lofty Building Group | 16/06- Logged for PA. Framing quotes received |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-11-12 | [27 empty] | 2026-01-20 | [132 empty] | Liv
1070 | 11 | 1070-11 | 1954 | PWA | - | 20 | Taylor Ave | Morphett Vale | Res 11 | Lot 20 Taylor Ave, Morphett Vale Res 11 |  |  |  | Developer | Lofty Building Group | 16/06- Logged for PA. Framing quotes received |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-11-12 | [27 empty] | 2026-01-20 | [132 empty] | Liv
1070 | 12 | 1070-12 | 1955 | PWA | - | 20 | Taylor Ave | Morphett Vale | Res 12 | Lot 20 Taylor Ave, Morphett Vale Res 12 |  |  |  | Developer | Lofty Building Group | 16/06- Logged for PA. Framing quotes received |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-11-12 | [27 empty] | 2026-01-20 | [132 empty] | Liv
1070 | 13 | 1070-13 | 1956 | PWA | - | 20 | Taylor Ave | Morphett Vale | Res 13 | Lot 20 Taylor Ave, Morphett Vale Res 13 |  |  |  | Developer | Lofty Building Group | 16/06- Logged for PA. Framing quotes received |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-11-12 | [27 empty] | 2026-01-20 | [132 empty] | Liv
1070 | 14 | 1070-14 | 1957 | PWA | - | 20 | Taylor Ave | Morphett Vale | Res 14 | Lot 20 Taylor Ave, Morphett Vale Res 14 |  |  |  | Developer | Lofty Building Group | 16/06- Logged for PA. Framing quotes received |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-11-12 | [27 empty] | 2026-01-20 | [132 empty] | Liv
1070 | 15 | 1070-15 | 1958 | PWA | - | 20 | Taylor Ave | Morphett Vale | Res 15 | Lot 20 Taylor Ave, Morphett Vale Res 15 |  |  |  | Developer | Lofty Building Group | 16/06- Logged for PA. Framing quotes received |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-11-12 | [27 empty] | 2026-01-20 | [132 empty] | Liv
1070 | 16 | 1070-16 | 1959 | PWA | - | 20 | Taylor Ave | Morphett Vale | Res 16 | Lot 20 Taylor Ave, Morphett Vale Res 16 |  |  |  | Developer | Lofty Building Group | 16/06- Logged for PA. Framing quotes received |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-11-12 | [27 empty] | 2026-01-20 | [132 empty] | Liv
1070 | 17 | 1070-17 | 1960 | PWA | - | 20 | Taylor Ave | Morphett Vale | Res 17 | Lot 20 Taylor Ave, Morphett Vale Res 17 |  |  |  | Developer | Lofty Building Group | 16/06- Logged for PA. Framing quotes received |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-11-12 | [27 empty] | 2026-01-20 | [132 empty] | Liv
1070 | 18 | 1070-18 | 1961 | PWA | - | 20 | Taylor Ave | Morphett Vale | Res 18 | Lot 20 Taylor Ave, Morphett Vale Res 18 |  |  |  | Developer | Lofty Building Group | 16/06- Logged for PA. Framing quotes received |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-11-12 | [27 empty] | 2026-01-20 | [132 empty] | Liv
1070 | 19 | 1070-19 | 1962 | PWA | - | 20 | Taylor Ave | Morphett Vale | Res 19 | Lot 20 Taylor Ave, Morphett Vale Res 19 |  |  |  | Developer | Lofty Building Group | 16/06- Logged for PA. Framing quotes received |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-11-12 | [27 empty] | 2026-01-20 | [132 empty] | Liv
1070 | 20 | 1070-20 | 1963 | PWA | - | 20 | Taylor Ave | Morphett Vale | Res 20 | Lot 20 Taylor Ave, Morphett Vale Res 20 |  |  |  | Developer | Lofty Building Group | 16/06- Logged for PA. Framing quotes received |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-11-12 | [27 empty] | 2026-01-20 | [132 empty] | Liv
1070 | 21 | 1070-21 | 1964 | PWA | - | 20 | Taylor Ave | Morphett Vale | Res 21 | Lot 20 Taylor Ave, Morphett Vale Res 21 |  |  |  | Developer | Lofty Building Group | 16/06- Logged for PA. Framing quotes received |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-11-12 | [27 empty] | 2026-01-20 | [132 empty] | Liv
1070 | 22 | 1070-22 | 1965 | PWA | - | 20 | Taylor Ave | Morphett Vale | Res 22 | Lot 20 Taylor Ave, Morphett Vale Res 22 |  |  |  | Developer | Lofty Building Group | 16/06- Logged for PA. Framing quotes received |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-11-12 | [27 empty] | 2026-01-20 | [132 empty] | Liv
1070 | 23 | 1070-23 | 1966 | PWA | - | 20 | Taylor Ave | Morphett Vale | Res 23 | Lot 20 Taylor Ave, Morphett Vale Res 23 |  |  |  | Developer | Lofty Building Group | 16/06- Logged for PA. Framing quotes received |  | Mitch G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-11-12 | [27 empty] | 2026-01-20 | [132 empty] | Liv
1071 | 01 | 1071-01 | 1967 | PWA | - | 8 | Dunedin Street | Dover Gardens | Res | 8 Dunedin Street, Dover Gardens Res |  |  |  | Developer | Lofty Building Group | 22/06 - Framing quotes received. Contract deposit requested. WDs done. Frames requested |  | Brenton G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-11-13 | [27 empty] | 2026-02-04 | 2026-03-11 | [131 empty] | Liv
1071 | 02 | 1071-02 | 1968 | PWA | - | 8 | Dunedin Street | Dover Gardens | Res | 8 Dunedin Street, Dover Gardens Res |  |  |  | Developer | Lofty Building Group | 22/06 - Framing quotes received. Contract deposit paid. WDs done. Frames requested |  | Brenton G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-11-13 | [27 empty] | 2026-02-04 | 2026-03-11 | [131 empty] | Liv
1071 | 03 | 1071-03 | 1969 | PWA | - | 8 | Dunedin Street | Dover Gardens | Res | 8 Dunedin Street, Dover Gardens Res |  |  |  | Developer | Lofty Building Group | 22/06 - Framing quotes received. Contract deposit requested. WDs done. Frames requested |  | Brenton G |  |  | 1 | 0 | 1 | n/a | n/a | n/a | n/a |  |  | 2025-11-13 | [27 empty] | 2026-02-04 | 2026-03-11 | [131 empty] | Liv
1072 | 01 | 1072-01 | 1970 | PWA | - | 31 | A Baden Tce | O'sullivan Beach |  | 31A Baden Tce, O'sullivan Beach |  |  |  | Retail |  | 29/06 - PA received. Frame quotes received |  | Olivia |  |  | 0 | 1 | 1 | 2025-11-14 |  | 2025-11-19 | 5000 |  |  | 2025-11-20 | [27 empty] | 2026-05-06 | [132 empty] | Liv
1073 | 01 | 1073-01 | 1974 | PWA | - | 2 | Mckeller Tce | Morphettville | Res 1 | 2 Mckeller Tce, Morphettville Res 1 |  |  |  | Retail | Grant Walter | 29/09 - In for PA amendment. FQC done. Framing quotes received. ON marked. In for WDs. |  | Mitch G | [8 empty] | 10000 | [30 empty] | 2026-03-03 | 2026-05-08 | [131 empty] | Liv
1073 | 02 | 1073-02 | 1975 | PWA | - | 2 | Mckeller Tce | Morphettville | Res 2 | 2 Mckeller Tce, Morphettville Res 2 |  |  |  | Retail | Grant Walter | 29/09 - In for PA amendment. FQC done. Framing quotes received. ON marked. In for WDs. |  | Mitch G | [8 empty] | 10000 | [30 empty] | 2026-03-03 | 2026-05-08 | [131 empty] | Liv
1073 | 03 | 1073-03 | 1976 | PWA | - | 2 | Mckeller Tce | Morphettville | Res 3 | 2 Mckeller Tce, Morphettville Res 3 |  |  |  | Retail | Grant Walter | 29/09 - In for PA amendment. FQC done. Framing quotes received. ON marked. In for WDs. |  | Mitch G | [8 empty] | 10000 | [30 empty] | 2026-03-03 | 2026-05-08 | [131 empty] | Liv
1074 | 01 | 1074-01 | 1977 | PWA | - | 4 | Leeds Ave | Hope Valley | res 1 | 4 Leeds Ave Hope Valley res 1 |  |  |  | Retail | Westside Housing | 26/05 - logged for PDs |  | Mitch G | [172 empty] | Liv
1074 | 02 | 1074-02 | 1978 | PWA | - | 4 | Leeds Ave | Hope Valley | res 2 | 4 Leeds Ave Hope Valley res 2 |  |  |  | Retail | Westside Housing | 26/05 - logged for PDs |  | Mitch G | [172 empty] | Liv
1074 | 03 | 1074-03 | 1979 | PWA | - | 4 | Leeds Ave | Hope Valley | res 3 | 4 Leeds Ave Hope Valley res 3 |  |  |  | Retail | Westside Housing | 26/05 - logged for PDs |  | Mitch G | [172 empty] | Liv
1075 | 01 | 1075-01 | 1980 | PWA | - | 20 | Grandview Grove Sturt |  | res 1 | 20 Grandview Grove Sturt res 1 |  |  |  | Retail | Westside Housing | 18/05 - Logged for PA. |  | Mitch G | [172 empty] | Liv
1075 | 02 | 1075-02 | 1981 | PWA | - | 20 | Grandview Grove Sturt |  | res 2 | 20 Grandview Grove Sturt res 2 |  |  |  | Retail | Westside Housing | 18/05 - Logged for PA. |  | Mitch G | [172 empty] | Liv
1075 | 03 | 1075-03 | 1982 | PWA | - | 20 | Grandview Grove Sturt |  | res 3 | 20 Grandview Grove Sturt res 3 |  |  |  | Retail | Westside Housing | 18/05 - Logged for PA. |  | Mitch G | [172 empty] | Liv
1076 | 01 | 1076-01 | 1983 | PWA | - | 47 | Ivey ST | Ottoway | Res 1 | 47 Ivey ST, Ottoway Res 1 |  |  |  | Developer | Lofty Building Group | 29/06 -Achieved PA. To be ON MARKET. In for WDs |  | Brenton G | [39 empty] | 2026-03-03 | [132 empty] | Liv
1076 | 02 | 1076-02 | 1984 | PWA | - | 47 | Ivey ST | Ottoway | Res 2 | 47 Ivey ST, Ottoway Res 2 |  |  |  | Developer | Lofty Building Group | 29/06 -Achieved PA. To be ON MARKET. In for WDs |  | Brenton G | [39 empty] | 2026-03-03 | [132 empty] | Liv
1076 | 03 | 1076-03 | 1985 | PWA | - | 47 | Ivey ST | Ottoway | Res 3 | 47 Ivey ST, Ottoway Res 3 |  |  |  | Developer | Lofty Building Group | 29/06 -Achieved PA. To be ON MARKET. In for WDs |  | Brenton G | [39 empty] | 2026-03-03 | [132 empty] | Liv
1077 | 01 | 1077-01 | 1991 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 1 | 51 Maryvale Rd, Athelstone Res 1 (Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 02 | 1077-02 | 1992 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 2 | 51 Maryvale Rd, Athelstone Res 2 (Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 03 | 1077-03 | 1993 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 3 | 51 Maryvale Rd, Athelstone Res 3(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 04 | 1077-04 | 1994 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 4 | 51 Maryvale Rd, Athelstone Res 4(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 05 | 1077-05 | 1995 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 5 | 51 Maryvale Rd, Athelstone Res 5(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 06 | 1077-06 | 1996 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 6 | 51 Maryvale Rd, Athelstone Res 6(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 07 | 1077-07 | 1997 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 7 | 51 Maryvale Rd, Athelstone Res 7(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 08 | 1077-08 | 1998 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 8 | 51 Maryvale Rd, Athelstone Res 8(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 09 | 1077-09 | 1999 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 9 | 51 Maryvale Rd, Athelstone Res 9(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 10 | 1077-10 | 2000 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 10 | 51 Maryvale Rd, Athelstone Res 10(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 11 | 1077-11 | 2001 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 11 | 51 Maryvale Rd, Athelstone Res 11(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 12 | 1077-12 | 2002 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 12 | 51 Maryvale Rd, Athelstone Res 12(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 13 | 1077-13 | 2003 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 13 | 51 Maryvale Rd, Athelstone Res 13(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 14 | 1077-14 | 2004 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 14 | 51 Maryvale Rd, Athelstone Res 14(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 15 | 1077-15 | 2005 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 15 | 51 Maryvale Rd, Athelstone Res 15(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 16 | 1077-16 | 2006 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 16 | 51 Maryvale Rd, Athelstone Res 16(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 17 | 1077-17 | 2007 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 17 | 51 Maryvale Rd, Athelstone Res 17(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 18 | 1077-18 | 2008 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 18 | 51 Maryvale Rd, Athelstone Res 18(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 19 | 1077-19 | 2009 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 19 | 51 Maryvale Rd, Athelstone Res 19(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 20 | 1077-20 | 2010 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 20 | 51 Maryvale Rd, Athelstone Res 20(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 21 | 1077-21 | 2011 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 21 | 51 Maryvale Rd, Athelstone Res 21(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 22 | 1077-22 | 2012 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 22 | 51 Maryvale Rd, Athelstone Res 22(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 23 | 1077-23 | 2013 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 23 | 51 Maryvale Rd, Athelstone Res 23(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 24 | 1077-24 | 2014 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 24 | 51 Maryvale Rd, Athelstone Res 24(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 25 | 1077-25 | 2015 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 25 | 51 Maryvale Rd, Athelstone Res 25(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 26 | 1077-26 | 2016 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 26 | 51 Maryvale Rd, Athelstone Res 26(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 27 | 1077-27 | 2017 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 27 | 51 Maryvale Rd, Athelstone Res 27(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 28 | 1077-28 | 2018 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 28 | 51 Maryvale Rd, Athelstone Res 28(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 29 | 1077-29 | 2019 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 29 | 51 Maryvale Rd, Athelstone Res 29(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 30 | 1077-30 | 2020 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 30 | 51 Maryvale Rd, Athelstone Res 30(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 31 | 1077-31 | 2021 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 31 | 51 Maryvale Rd, Athelstone Res 31(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 32 | 1077-32 | 2022 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 32 | 51 Maryvale Rd, Athelstone Res 32(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 33 | 1077-33 | 2023 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 33 | 51 Maryvale Rd, Athelstone Res 33(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 34 | 1077-34 | 2024 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 34 | 51 Maryvale Rd, Athelstone Res 34(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 35 | 1077-35 | 2025 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 35 | 51 Maryvale Rd, Athelstone Res 35(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 36 | 1077-36 | 2026 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 36 | 51 Maryvale Rd, Athelstone Res 36(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 37 | 1077-37 | 2027 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 37 | 51 Maryvale Rd, Athelstone Res 37(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 38 | 1077-38 | 2028 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 38 | 51 Maryvale Rd, Athelstone Res 38(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 39 | 1077-39 | 2029 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 39 | 51 Maryvale Rd, Athelstone Res 39(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 40 | 1077-40 | 2030 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 40 | 51 Maryvale Rd, Athelstone Res 40(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 41 | 1077-41 | 2031 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 41 | 51 Maryvale Rd, Athelstone Res 41(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 42 | 1077-42 | 2032 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 42 | 51 Maryvale Rd, Athelstone Res 42(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 43 | 1077-43 | 2033 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 43 | 51 Maryvale Rd, Athelstone Res 43(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 44 | 1077-44 | 2034 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 44 | 51 Maryvale Rd, Athelstone Res 44(Community) |  |  |  | Developer | Lofty Building Group | 22/06- Logged PD amends. awaiting civils |  | Brenton G | [172 empty] | Liv
1077 | 45 | 1077-45 | 2035 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 45 | 51 Maryvale Rd, Athelstone Res 45 (torrens) |  |  |  | Developer | Lofty Building Group | 22/06- WDs done. In for PA. Frames quotes received. Windows received. Awaiting AC layouts- Frames to be requested. |  | Brenton G | [39 empty] | 2026-04-18 | [132 empty] | Liv
1077 | 46 | 1077-46 | 2036 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 46 | 51 Maryvale Rd, Athelstone Res 46 (torrens) |  |  |  | Developer | Lofty Building Group | 22/06- WDs done. In for PA. Frames quotes received. Windows received. Awaiting AC layouts- Frames to be requested. |  | Brenton G | [39 empty] | 2026-04-18 | [132 empty] | Liv
1077 | 47 | 1077-47 | 2037 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 47 | 51 Maryvale Rd, Athelstone Res 47 (torrens) |  |  |  | Developer | Lofty Building Group | 22/06- WDs done. In for PA. Frames quotes received. Windows received. Awaiting AC layouts- Frames to be requested. |  | Brenton G | [39 empty] | 2026-04-18 | [132 empty] | Liv
1077 | 48 | 1077-48 | 2038 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 48 | 51 Maryvale Rd, Athelstone Res 48 (torrens) |  |  |  | Developer | Lofty Building Group | 22/06- WDs done. In for PA. Frames quotes received. Windows received. Awaiting AC layouts- Frames to be requested. |  | Brenton G | [39 empty] | 2026-04-18 | [132 empty] | Liv
1077 | 49 | 1077-49 | 2039 | PWA |  | 51 | Maryvale Rd | Athelstone | Res 49 | 51 Maryvale Rd, Athelstone Res 49 (torrens) |  |  |  | Developer | Lofty Building Group | 22/06- WDs done. In for PA. Frames quotes received. Windows received. Awaiting AC layouts- Frames to be requested. |  | Brenton G | [39 empty] | 2026-04-18 | [132 empty] | Liv
1078 | 01 | 1078-01 | 2040 | PWA | [9 empty] | Developer | Lofty Building Group |  |  | Brenton G | [172 empty] | Liv
1079 | 01 | 1079-01 | 2041 | PWA |  | 90 | Greentree BVD | Paralowie | RES 1 | 90 Greentree BVD, Paralowie RES 1 |  |  |  | Developer | Lofty Building Group | 27/5 - Contract sent |  | Brenton G | [172 empty] | Liv
1079 | 02 | 1079-02 | 2042 | PWA |  | 90 | Greentree BVD | Paralowie | RES 2 | 90 Greentree BVD, Paralowie RES 2 |  |  |  | Developer | Lofty Building Group | 26/5 - PA achieved. Frames quotes received. In for WDS. ON MARKET |  | Brenton G | [172 empty] | Liv
1079 | 03 | 1079-03 | 2043 | PWA |  | 90 | Greentree BVD | Paralowie | RES 3 | 90 Greentree BVD, Paralowie RES 3 |  |  |  | Developer | Lofty Building Group | 26/5 - PA achieved. Frames quotes received. In for WDS. ON MARKET |  | Brenton G | [172 empty] | Liv
1079 | 04 | 1079-04 | 2044 | PWA |  | 90 | Greentree BVD | Paralowie | RES 4 | 90 Greentree BVD, Paralowie RES 4 |  |  |  | Developer | Lofty Building Group | 26/5 - PA achieved. Frames quotes received. In for WDS. ON MARKET |  | Brenton G | [172 empty] | Liv
1079 | 05 | 1079-05 | 2045 | PWA |  | 90 | Greentree BVD | Paralowie | RES 5 | 90 Greentree BVD, Paralowie RES 5 |  |  |  | Developer | Lofty Building Group | 26/5 - PA achieved. Frames quotes received. In for WDS. ON MARKET |  | Brenton G | [172 empty] | Liv
1079 | 06 | 1079-06 | 2046 | PWA |  | 90 | Greentree BVD | Paralowie | RES 6 | 90 Greentree BVD, Paralowie RES 6 |  |  |  | Developer | Lofty Building Group | 26/5 - PA achieved. Frames quotes received. In for WDS. ON MARKET |  | Brenton G | [172 empty] | Liv
1079 | 07 | 1079-07 | 2047 | PWA |  | 90 | Greentree BVD | Paralowie | RES 7 | 90 Greentree BVD, Paralowie RES 7 |  |  |  | Developer | Lofty Building Group | 26/5 - PA achieved. Frames quotes received. In for WDS. ON MARKET |  | Brenton G | [172 empty] | Liv
1080 | 01 | 1080-01 | 2048 | PWA |  | 16 | Egan Cres | Mitchell Park | Res 1 | 16 Egan Cres, Mitchell Park Res 1 |  |  |  | Developer | Lofty Building Group | 16/06 - DA Received. On market |  | Mitch G | [39 empty] | 2026-03-24 | 2026-05-08 | [131 empty] | Liv
1080 | 02 | 1080-02 | 2049 | PWA |  | 16 | Egan Cres | Mitchell Park | Res 2 | 16 Egan Cres, Mitchell Park Res 2 |  |  |  | Developer | Lofty Building Group | 16/06 - DA Received. On market |  | Mitch G | [39 empty] | 2026-03-24 | 2026-05-08 | [131 empty] | Liv
1080 | 03 | 1080-03 | 2050 | PWA |  | 16 | Egan Cres | Mitchell Park | Res 3 | 16 Egan Cres, Mitchell Park Res 3 |  |  |  | Developer | Lofty Building Group | 16/06 - DA Received. On market |  | Mitch G | [39 empty] | 2026-03-24 | 2026-05-08 | [131 empty] | Liv
1081 | 01 | 1081-01 | 2051 | PWA |  | 25 | Ayre St | South Plympton | Res 1 | 25 Ayre St, South Plympton Res 1 |  |  |  | Developer | Lofty Building Group | 18/5 - WDs received - to be in for amendments. In for PA . Received final EER. Frames back (amendments req). |  | Mitch G | [39 empty] | 2026-04-14 | [132 empty] | 18/5 - WDs received - to be in for amendments. In for PA . Received final EER. Frames back (amendments req). To be logged for FQC. Awaiting FCR
1081 | 02 | 1081-02 | 2052 | PWA |  | 25 | Ayre St | South Plympton | Res 2 | 25 Ayre St, South Plympton Res 2 |  |  |  | Developer | Lofty Building Group | 18/5 - WDs received - to be in for amendments. In for PA . Received final EER. Frames back (amendments req). |  | Mitch G | [39 empty] | 2026-04-14 | [132 empty] | Liv
1081 | 03 | 1081-03 | 2053 | PWA |  | 25 | Ayre St | South Plympton | Res 3 | 25 Ayre St, South Plympton Res 3 |  |  |  | Developer | Lofty Building Group | 18/5 - WDs received - to be in for amendments. In for PA . Received final EER. Frames back (amendments req). |  | Mitch G | [39 empty] | 2026-04-14 | [132 empty] | Liv
1082 | 01 | 1082-01 | 2054 | PWA |  | 17 | Lewis Rd | Payneham | Res 1 | 17 Lewis Rd, Payneham Res 1 |  |  |  | Developer | Lofty Building Group | 18/05 - Logged for PA. Frame quotes requested |  | Brenton G | [39 empty] | 2026-04-27 | [132 empty] | Liv
1082 | 02 | 1082-02 | 2055 | PWA |  | 17 | Lewis Rd | Payneham | Res 2 | 17 Lewis Rd, Payneham Res 2 |  |  |  | Developer | Lofty Building Group | 18/05 - Logged for PA. Frame quotes requested |  | Brenton G | [39 empty] | 2026-04-27 | [132 empty] | Liv
1082 | 03 | 1082-03 | 2056 | PWA |  | 17 | Lewis Rd | Payneham | Res 3 | 17 Lewis Rd, Payneham Res 3 |  |  |  | Developer | Lofty Building Group | 18/05 - Logged for PA. Frame quotes requested |  | Brenton G | [39 empty] | 2026-04-27 | [132 empty] | Liv
1082 | 04 | 1082-04 | 2057 | PWA |  | 17 | Lewis Rd | Payneham | Res 4 | 17 Lewis Rd, Payneham Res 4 |  |  |  | Developer | Lofty Building Group | 18/05 - Logged for PA. Frame quotes requested |  | Brenton G | [39 empty] | 2026-04-27 | [132 empty] | Liv
1082 | 05 | 1082-05 | 2058 | PWA |  | 17 | Lewis Rd | Payneham | Res 5 | 17 Lewis Rd, Payneham Res 5 |  |  |  | Developer | Lofty Building Group | 18/05 - Logged for PA. Frame quotes requested |  | Brenton G | [39 empty] | 2026-04-27 | [132 empty] | Liv
1083 | 01 | 1083-01 | 2059 | PWA |  | 16 | Jenny Ave Dernancourt |  |  | 16 Jenny Ave Dernancourt |  |  |  | Retail |  | 29/6 - Pricing done. In for PA. RFI |  | paul | [172 empty] | Liv
1084 | 01 | 1084-01 | 2061 | PWA |  | 15 | Peachy Rd | Davoren Park |  | 15 Peachy Rd, Davoren Park | Brenton Garritty |  |  | Developer | Lofty Building Group | 29/06- PA received. Frame quotes received. Logged for FQC |  | Brenton G | [39 empty] | 2026-04-24 | [132 empty] | Liv
1084 | 02 | 1084-02 | 2062 | PWA |  | 15 | Peachy Rd | Davoren Park |  | 15 Peachy Rd, Davoren Park | Brenton Garritty |  |  | Developer | Lofty Building Group | 29/06- PA received. Frame quotes received. Logged for FQC |  | Brenton G | [39 empty] | 2026-04-24 | [132 empty] | Liv
1084 | 03 | 1084-03 | 2063 | PWA |  | 15 | Peachy Rd | Davoren Park |  | 15 Peachy Rd, Davoren Park | Brenton Garritty |  |  | Developer | Lofty Building Group | 29/06- PA received. Frame quotes received. Logged for FQC |  | Brenton G | [39 empty] | 2026-04-24 | [132 empty] | Liv
1085 | 01 | 1085-01 | 2065 | PWA | CAncelling | 593 | Portrush Road & 16 Taminga Ave | Glenunga | res 1 | 593 Portrush Road & 16 Taminga Ave, Glenunga res 1 | Mitch Gurnett |  |  | Developer | Lofty Building Group |  |  | Mitch G | [172 empty] | Liv
1085 | 02 | 1085-02 | 2066 | PWA | CAncelling | 593 | Portrush Road & 16 Taminga Ave | Glenunga | res 2 | 593 Portrush Road & 16 Taminga Ave, Glenunga res 2 | Mitch Gurnett |  |  | Developer | Lofty Building Group |  |  | Mitch G | [172 empty] | Liv
1085 | 03 | 1085-03 | 2067 | PWA | CAncelling | 593 | Portrush Road & 16 Taminga Ave | Glenunga | res 3 | 593 Portrush Road & 16 Taminga Ave, Glenunga res 3 | Mitch Gurnett |  |  | Developer | Lofty Building Group |  |  | Mitch G | [172 empty] | Liv
1085 | 04 | 1085-04 | 2068 | PWA | CAncelling | 593 | Portrush Road & 16 Taminga Ave | Glenunga | res 4 | 593 Portrush Road & 16 Taminga Ave, Glenunga res 4 | Mitch Gurnett |  |  | Developer | Lofty Building Group |  |  | Mitch G | [172 empty] | Liv
1085 | 05 | 1085-05 | 2069 | PWA | CAncelling | 593 | Portrush Road & 16 Taminga Ave | Glenunga | res 5 | 593 Portrush Road & 16 Taminga Ave, Glenunga res 5 | Mitch Gurnett |  |  | Developer | Lofty Building Group |  |  | Mitch G | [172 empty] | Liv
1085 | 06 | 1085-06 | 2070 | PWA | CAncelling | 593 | Portrush Road & 16 Taminga Ave | Glenunga | res 6 | 593 Portrush Road & 16 Taminga Ave, Glenunga res 6 | Mitch Gurnett |  |  | Developer | Lofty Building Group |  |  | Mitch G | [172 empty] | Liv
1086 | 01 | 1086-01 | 2071 | PWA |  | 41 | Alexander Ave | Morphett Vale | Res 1 | 41 Alexander Ave, Morphett Vale Res 1 |  |  |  | Developer | Lofty Building Group | 18/05 - PDs done. Logged for PA. Frame quotes Received |  | Mitch G | [39 empty] | 2026-04-14 | [132 empty] | Liv
1086 | 02 | 1086-02 | 2072 | PWA |  | 41 | Alexander Ave | Morphett Vale | Res 2 | 41 Alexander Ave, Morphett Vale Res 2 |  |  |  | Developer | Lofty Building Group | 18/05 - PDs done. Logged for PA. Frame quotes Received |  | Mitch G | [39 empty] | 2026-04-14 | [132 empty] | Liv
1086 | 03 | 1086-03 | 2073 | PWA |  | 41 | Alexander Ave | Morphett Vale | Res 3 | 41 Alexander Ave, Morphett Vale Res 3 |  |  |  | Developer | Lofty Building Group | 18/05 - PDs done. Logged for PA. Frame quotes Received |  | Mitch G | [39 empty] | 2026-04-14 | [132 empty] | Liv
1086 | 04 | 1086-04 | 2074 | PWA |  | 41 | Alexander Ave | Morphett Vale | Res 4 | 41 Alexander Ave, Morphett Vale Res 4 |  |  |  | Developer | Lofty Building Group | 18/05 - PDs done. Logged for PA. Frame quotes Received |  | Mitch G | [39 empty] | 2026-04-14 | [132 empty] | Liv
1087 | 01 | 1087-01 | 2075 | PWA |  | 33 | Pudney St | Seaton | Res 1 | 33 Pudney St, Seaton Res 1 |  |  |  | Developer | Lofty Building Group | 16/06 - Logged for PA. Framing quotes requested |  | Brenton G | [39 empty] | 2026-04-18 | [132 empty] | Liv
1087 | 02 | 1087-02 | 2076 | PWA |  | 33 | Pudney St | Seaton | Res 2 | 33 Pudney St, Seaton Res 2 |  |  |  | Developer | Lofty Building Group | 16/06 - Logged for PA. Framing quotes requested |  | Brenton G | [39 empty] | 2026-04-18 | [132 empty] | Liv
1087 | 03 | 1087-03 | 2077 | PWA |  | 33 | Pudney St | Seaton | Res 3 | 33 Pudney St, Seaton Res 3 |  |  |  | Developer | Lofty Building Group | 16/06 - Logged for PA. Framing quotes requested |  | Brenton G | [39 empty] | 2026-04-18 | [132 empty] | Liv
1088 | 01 | 1088-01 | 2078 | PWA |  | 50 | Bluehills RD | O'Halloran Hill | Res 1 | 50 Bluehills RD, O'Halloran Hill Res 1 |  |  |  | Developer | Lofty Building Group | 22/6 - In for PA. Framing quotes received. |  | Mitch G | [39 empty] | 2026-05-11 | [132 empty] | Liv
1088 | 02 | 1088-02 | 2079 | PWA |  | 50 | Bluehills RD | O'Halloran Hill | Res 2 | 50 Bluehills RD, O'Halloran Hill Res 2 |  |  |  | Developer | Lofty Building Group | 22/6 - In for PA. Framing quotes received. |  | Mitch G | [39 empty] | 2026-05-11 | [132 empty] | Liv
1088 | 03 | 1088-03 | 2080 | PWA |  | 50 | Bluehills RD | O'Halloran Hill | Res 3 | 50 Bluehills RD, O'Halloran Hill Res 3 |  |  |  | Developer | Lofty Building Group | 22/6 - In for PA. Framing quotes received. |  | Mitch G | [39 empty] | 2026-05-11 | [132 empty] | Liv
1088 | 04 | 1088-04 | 2081 | PWA |  | 50 | Bluehills RD | O'Halloran Hill | Res 4 | 50 Bluehills RD, O'Halloran Hill Res 4 |  |  |  | Developer | Lofty Building Group | 22/6 - In for PA. Framing quotes received. |  | Mitch G | [39 empty] | 2026-05-11 | [132 empty] | Liv
1089 | 01 | 1089-01 | 2082 | PWA |  | 36 | Bayview Rd | Gulfview Heights |  | 36 Bayview Rd, Gulfview Heights |  |  |  | Retail | Harry | 16/06 - With council. |  | Brenton G | [172 empty] | Liv
1090 | 01 | 1090-01 | 2083 | PWA |  | 22 | Jennifer Ave | Happy valley | Res 1 | 22 Jennifer Ave, Happy valley Res 1 | [7 empty] | Brenton G
1091 | 01 | 1091-01 | 2084 | PWA |  | 337&339 | Montacute Rd | Athelstone | Res 1 | 337 & 339 Montacute Rd, Athelstone Res 1 |  |  |  | Developer | Lofty Building Group | 29/06 - PA received. In for FCQ. Framing quotes received |  | Brenton G |  |  | 1 | [8 empty] | 2026-03-13 |  |  |  |  | 2026-03-10 | [22 empty] | 2026-05-13 | [132 empty] | Liv
1091 | 02 | 1091-02 | 2085 | PWA |  | 337&339 | Montacute Rd | Athelstone | Res 2 | 337 & 339 Montacute Rd, Athelstone Res 2 |  |  |  | Developer | Lofty Building Group | 29/06 - PA received. In for FCQ. Framing quotes received |  | Brenton G |  |  | 1 | [8 empty] | 2026-03-13 |  |  |  |  | 2026-03-10 | [22 empty] | 2026-05-13 | [132 empty] | Liv
1091 | 03 | 1091-03 | 2086 | PWA |  | 337&339 | Montacute Rd | Athelstone | Res 3 | 337 & 339 Montacute Rd, Athelstone Res 3 |  |  |  | Developer | Lofty Building Group | 29/06 - PA received. In for FCQ. Framing quotes received |  | Brenton G |  |  | 1 | [8 empty] | 2026-03-13 |  |  |  |  | 2026-03-10 | [22 empty] | 2026-05-13 | [132 empty] | Liv
1091 | 04 | 1091-04 | 2087 | PWA |  | 337&339 | Montacute Rd | Athelstone | Res 4 | 337 & 339 Montacute Rd, Athelstone Res 4 |  |  |  | Developer | Lofty Building Group | 29/06 - PA received. In for FCQ. Framing quotes received |  | Brenton G |  |  | 1 | [8 empty] | 2026-03-13 |  |  |  |  | 2026-03-10 | [22 empty] | 2026-05-13 | [132 empty] | Liv
1091 | 05 | 1091-05 | 2088 | PWA |  | 337&339 | Montacute Rd | Athelstone | Res 5 | 337 & 339 Montacute Rd, Athelstone Res 5 |  |  |  | Developer | Lofty Building Group | 29/06 - PA received. In for FCQ. Framing quotes received |  | Brenton G |  |  | 1 | [8 empty] | 2026-03-13 |  |  |  |  | 2026-03-10 | [22 empty] | 2026-05-13 | [132 empty] | Liv
1091 | 06 | 1091-06 | 2089 | PWA |  | 337&339 | Montacute Rd | Athelstone | Res 6 | 337 & 339 Montacute Rd, Athelstone Res 6 |  |  |  | Developer | Lofty Building Group | 29/06 - PA received. In for FCQ. Framing quotes received |  | Brenton G |  |  | 1 | [8 empty] | 2026-03-13 |  |  |  |  | 2026-03-10 | [22 empty] | 2026-05-13 | [132 empty] | Liv
1091 | 07 | 1091-07 | 2090 | PWA |  | 337&339 | Montacute Rd | Athelstone | Res 7 | 337 & 339 Montacute Rd, Athelstone Res 7 |  |  |  | Developer | Lofty Building Group | 29/06 - PA received. In for FCQ. Framing quotes received |  | Brenton G |  |  | 1 | [8 empty] | 2026-03-13 |  |  |  |  | 2026-03-10 | [22 empty] | 2026-05-13 | [132 empty] | Liv
1091 | 08 | 1091-08 | 2091 | PWA |  | 337&339 | Montacute Rd | Athelstone | Res 8 | 337 & 339 Montacute Rd, Athelstone Res 8 |  |  |  | Developer | Lofty Building Group | 29/06 - PA received. In for FCQ. Framing quotes received |  | Brenton G |  |  | 1 | [8 empty] | 2026-03-13 |  |  |  |  | 2026-03-10 | [22 empty] | 2026-05-13 | [132 empty] | Liv
1091 | 09 | 1091-09 | 2092 | PWA |  | 337&339 | Montacute Rd | Athelstone | Res 9 | 337 & 339 Montacute Rd, Athelstone Res 9 |  |  |  | Developer | Lofty Building Group | 29/06 - PA received. In for FCQ. Framing quotes received |  | Brenton G |  |  | 1 | [8 empty] | 2026-03-13 |  |  |  |  | 2026-03-10 | [22 empty] | 2026-05-13 | [132 empty] | Liv
1091 | 10 | 1091-10 | 2093 | PWA |  | 337&339 | Montacute Rd | Athelstone | Res 10 | 337 & 339 Montacute Rd, Athelstone Res 10 |  |  |  | Developer | Lofty Building Group | 29/06 - PA received. In for FCQ. Framing quotes received |  | Brenton G |  |  | 1 | [8 empty] | 2026-03-13 |  |  |  |  | 2026-03-10 | [22 empty] | 2026-05-13 | [132 empty] | Liv
1091 | 11 | 1091-11 | 2094 | PWA |  | 337&339 | Montacute Rd | Athelstone | Res 11 | 337 & 339 Montacute Rd, Athelstone Res 11 |  |  |  | Developer | Lofty Building Group | 29/06 - PA received. In for FCQ. Framing quotes received |  | Brenton G |  |  | 1 | [8 empty] | 2026-03-13 |  |  |  |  | 2026-03-10 | [22 empty] | 2026-05-13 | [132 empty] | Liv
1091 | 12 | 1091-12 | 2095 | PWA |  | 337&339 | Montacute Rd | Athelstone | Res 12 | 337 & 339 Montacute Rd, Athelstone Res 12 |  |  |  | Developer | Lofty Building Group | 29/06 - PA received. In for FCQ. Framing quotes received |  | Brenton G |  |  | 1 | [8 empty] | 2026-03-13 |  |  |  |  | 2026-03-10 | [22 empty] | 2026-05-13 | [132 empty] | Liv
1091 | 13 | 1091-13 | 2096 | PWA |  | 337&339 | Montacute Rd | Athelstone | Res 13 | 337 & 339 Montacute Rd, Athelstone Res 13 |  |  |  | Developer | Lofty Building Group | 29/06 - PA received. In for FCQ. Framing quotes received |  | Brenton G |  |  | 1 | [8 empty] | 2026-03-13 |  |  |  |  | 2026-03-10 | [22 empty] | 2026-05-13 | [132 empty] | Liv
1091 | 14 | 1091-14 | 2097 | PWA |  | 337&339 | Montacute Rd | Athelstone | Res 14 | 337 & 339 Montacute Rd, Athelstone Res 14 |  |  |  | Developer | Lofty Building Group | 29/06 - PA received. In for FCQ. Framing quotes received |  | Brenton G |  |  | 1 | [8 empty] | 2026-03-13 |  |  |  |  | 2026-03-10 | [22 empty] | 2026-05-13 | [132 empty] | Liv
1091 | 15 | 1091-15 | 2098 | PWA |  | 337&339 | Montacute Rd | Athelstone | Res 15 | 337 & 339 Montacute Rd, Athelstone Res 15 |  |  |  | Developer | Lofty Building Group | 29/06 - PA received. In for FCQ. Framing quotes received |  | Brenton G |  |  | 1 | [8 empty] | 2026-03-13 |  |  |  |  | 2026-03-10 | [22 empty] | 2026-05-13 | [132 empty] | Liv
1091 | 16 | 1091-16 | 2099 | PWA |  | 337&339 | Montacute Rd | Athelstone | Res 16 | 337 & 339 Montacute Rd, Athelstone Res 16 |  |  |  | Developer | Lofty Building Group | 29/06 - PA received. In for FCQ. Framing quotes received |  | Brenton G |  |  | 1 | [8 empty] | 2026-03-13 |  |  |  |  | 2026-03-10 | [22 empty] | 2026-05-13 | [132 empty] | Liv
1092 | 01 | 1092-01 | 2100 | PWA |  | 7 | Budapest Rd | Aberfoyle Park | Res 1 | 7 Budapest Rd, Aberfoyle Park Res 1 |  |  |  |  | Haume | 5/5 -Concept with client. Waiting to settle. Awaiting surveys |  | Mitch G | [172 empty] | Liv
1092 | 02 | 1092-02 | 2101 | PWA |  | 7 | Budapest Rd | Aberfoyle Park | Res 2 | 7 Budapest Rd, Aberfoyle Park Res 2 |  |  |  |  | Haume | 5/5 -Concept with client. Waiting to settle. Awaiting surveys |  | Mitch G | [172 empty] | Liv
1092 | 03 | 1092-03 | 2102 | PWA |  | 7 | Budapest Rd | Aberfoyle Park | Res 3 | 7 Budapest Rd, Aberfoyle Park Res 3 |  |  |  |  | Haume | 5/5 -Concept with client. Waiting to settle. Awaiting surveys |  | Mitch G | [172 empty] | Liv
1092 | 04 | 1092-04 | 2103 | PWA |  | 7 | Budapest Rd | Aberfoyle Park | Res 4 | 7 Budapest Rd, Aberfoyle Park Res 4 |  |  |  |  | Haume | 5/5 -Concept with client. Waiting to settle. Awaiting surveys |  | Mitch G | [172 empty] | Liv
1092 | 05 | 1092-05 | 2104 | PWA |  | 7 | Budapest Rd | Aberfoyle Park | Res 5 | 7 Budapest Rd, Aberfoyle Park Res 5 |  |  |  |  | Haume | 5/5 -Concept with client. Waiting to settle. Awaiting surveys |  | Mitch G | [172 empty] | Liv
1092 | 06 | 1092-06 | 2105 | PWA |  | 7 | Budapest Rd | Aberfoyle Park | Res 6 | 7 Budapest Rd, Aberfoyle Park Res 6 |  |  |  |  | Haume | 5/5 -Concept with client. Waiting to settle. Awaiting surveys |  | Mitch G | [172 empty] | Liv
1090 | 02 | 1090-02 | 2106 | PWA |  | 22 | Jennifer Ave | Happy valley | Res 1 | 22 Jennifer Ave, Happy valley Res 1 |  |  |  | Retail | Sheridan & Dennis | 26/05 - Loged for PA |  | Brenton G | [40 empty] | 2026-05-26 | [131 empty] | Liv
1090 | 03 | 1090-03 | 2107 | PWA |  | 22 | Jennifer Ave | Happy valley | Res 2 | 22 Jennifer Ave, Happy valley Res 2 |  |  |  | Retail | Sheridan & Dennis | 26/05 - Loged for PA |  | Brenton G | [172 empty] | Liv
1090 | 04 | 1090-04 | 2108 | PWA |  | 22 | Jennifer Ave | Happy valley | Res 3 | 22 Jennifer Ave, Happy valley Res 3 |  |  |  | Retail | Sheridan & Dennis | 26/05 - Loged for PA |  | Brenton G | [172 empty] | Liv
1093 | 01 | 1093-01 | 2109 | PWA |  | 2 | Osmund Cres | Christie Downs | Res 1 | 2 Osmund Cres, Christie Downs Res 1 | [5 empty] | 2/06 - In for PA |  | Brenton G | [172 empty] | Liv
1093 | 02 | 1093-02 | 2110 | PWA |  | 2 | Osmund Cres | Christie Downs | Res 2 | 2 Osmund Cres, Christie Downs Res 2 | [5 empty] | 2/06 - In for PA |  | Brenton G | [172 empty] | Liv
1093 | 03 | 1093-03 | 2111 | PWA |  | 2 | Osmund Cres | Christie Downs | Res 3 | 2 Osmund Cres, Christie Downs Res 3 | [5 empty] | 2/06 - In for PA |  | Brenton G | [172 empty] | Liv
1093 | 04 | 1093-04 | 2112 | PWA |  | 2 | Osmund Cres | Christie Downs | Res 4 | 2 Osmund Cres, Christie Downs Res 4 | [5 empty] | 2/06 - In for PA |  | Brenton G | [172 empty] | Liv
1093 | 05 | 1093-05 | 2113 | PWA |  | 2 | Osmund Cres | Christie Downs | Res 5 | 2 Osmund Cres, Christie Downs Res 5 | [5 empty] | 2/06 - In for PA |  | Brenton G | [172 empty] | Liv
1094 | 01 | 1094-01 | 2114 | PWA |  | 7 | Tatiara Rd | Happy valley | Res 1 | 7 Tatiara Rd, Happy valley Res 1 | [5 empty] | 29/06 - In for PA |  | Brenton G | [172 empty] | Liv
1094 | 02 | 1094-02 | 2115 | PWA |  | 7 | Tatiara Rd | Happy valley | Res 2 | 7 Tatiara Rd, Happy valley Res 2 | [5 empty] | 29/06 - In for PA |  | Brenton G | [172 empty] | Liv
1094 | 03 | 1094-03 | 2116 | PWA |  | 7 | Tatiara Rd | Happy valley | Res 3 | 7 Tatiara Rd, Happy valley Res 3 | [5 empty] | 29/06 - In for PA |  | Brenton G | [172 empty] | Liv
1095 | 01 | 1095-01 | 2146 | PWA |  | 3 | Deans Road | Campbelltown | Lot 46 | Lot 46, 3 Deans Road, Campbelltown | [5 empty] | 16/03 - PDs done- facade changes. Surveys received. To be logged for PA |  | Olivia | [172 empty] | Liv
1096 | 01 | 1096-01 | 2117 | PWA |  | 4999 | Dowie Way | Munno Para | Res 1 | Lot 4999 Dowie Way, Munno Para Res 1 | [5 empty] | 14/04 - PA lodged |  | Mitch G | [39 empty] | 2026-02-13 | [132 empty] | Liv
1096 | 02 | 1096-02 | 2118 | PWA |  | 4999 | Dowie Way | Munno Para | Res 2 | 4999 Dowie Way, Munno Para Res 2 | [5 empty] | 14/04 - PA lodged. |  | Mitch G | [39 empty] | 2026-02-13 | [132 empty] | Liv
1096 | 03 | 1096-03 | 2119 | PWA |  | 4999 | Dowie Way | Munno Para | Res 3 | 4999 Dowie Way, Munno Para Res 3 | [5 empty] | 14/04 - PA lodged. |  | Mitch G | [39 empty] | 2026-02-13 | [132 empty] | Liv
1096 | 04 | 1096-04 | 2120 | PWA |  | 4999 | Dowie Way | Munno Para | Res 4 | 4999 Dowie Way, Munno Para Res 4 | [5 empty] | 14/04 - PA lodged. |  | Mitch G | [39 empty] | 2026-02-13 | [132 empty] | Liv
1096 | 05 | 1096-05 | 2121 | PWA |  | 4999 | Dowie Way | Munno Para | Res 5 | 4999 Dowie Way, Munno Para Res 5 | [5 empty] | 14/04 - PA lodged. |  | Mitch G | [39 empty] | 2026-02-13 | [132 empty] | Liv
1096 | 06 | 1096-06 | 2122 | PWA |  | 4999 | Dowie Way | Munno Para | Res 6 | 4999 Dowie Way, Munno Para Res 6 | [5 empty] | 14/04 - PA lodged. |  | Mitch G | [39 empty] | 2026-02-13 | [132 empty] | Liv
1096 | 07 | 1096-07 | 2123 | PWA |  | 4999 | Dowie Way | Munno Para | Res 7 | 4999 Dowie Way, Munno Para Res 7 | [5 empty] | 14/04 - PA lodged. |  | Mitch G | [39 empty] | 2026-02-13 | [132 empty] | Liv
1096 | 08 | 1096-08 | 2124 | PWA |  | 4999 | Dowie Way | Munno Para | Res 8 | 4999 Dowie Way, Munno Para Res 8 | [5 empty] | 14/04 - PA lodged. |  | Mitch G | [39 empty] | 2026-02-13 | [132 empty] | Liv
1096 | 09 | 1096-09 | 2125 | PWA |  | 4999 | Dowie Way | Munno Para | Res 9 | 4999 Dowie Way, Munno Para Res 9 | [5 empty] | 14/04 - PA lodged. |  | Mitch G | [39 empty] | 2026-02-13 | [132 empty] | Liv
1096 | 10 | 1096-10 | 2126 | PWA |  | 4999 | Dowie Way | Munno Para | Res 10 | 4999 Dowie Way, Munno Para Res 10 | [5 empty] | 14/04 - PA lodged. |  | Mitch G | [39 empty] | 2026-02-13 | [132 empty] | Liv
1096 | 11 | 1096-11 | 2127 | PWA |  | 4999 | Dowie Way | Munno Para | Res 11 | 4999 Dowie Way, Munno Para Res 11 | [5 empty] | 14/04 - PA lodged. |  | Mitch G | [39 empty] | 2026-02-13 | [132 empty] | Liv
1096 | 12 | 1096-12 | 2128 | PWA |  | 4999 | Dowie Way | Munno Para | Res 12 | 4999 Dowie Way, Munno Para Res 12 | [5 empty] | 14/04 - PA lodged. |  | Mitch G | [39 empty] | 2026-02-13 | [132 empty] | Liv
1096 | 13 | 1096-13 | 2129 | PWA |  | 4999 | Dowie Way | Munno Para | Res 13 | 4999 Dowie Way, Munno Para Res 13 | [5 empty] | 14/04 - PA lodged. |  | Mitch G | [39 empty] | 2026-02-13 | [132 empty] | Liv
1096 | 14 | 1096-14 | 2130 | PWA |  | 4999 | Dowie Way | Munno Para | Res 14 | 4999 Dowie Way, Munno Para Res 14 | [5 empty] | 14/04 - PA lodged. |  | Mitch G | [39 empty] | 2026-02-13 | [132 empty] | Liv
1096 | 15 | 1096-15 | 2131 | PWA |  | 4999 | Dowie Way | Munno Para | Res 15 | 4999 Dowie Way, Munno Para Res 15 | [5 empty] | 14/04 - PA lodged. |  | Mitch G | [39 empty] | 2026-02-13 | [132 empty] | Liv
1096 | 16 | 1096-16 | 2132 | PWA |  | 4999 | Dowie Way | Munno Para | Res 16 | 4999 Dowie Way, Munno Para Res 16 | [5 empty] | 14/04 - PA lodged. |  | Mitch G | [39 empty] | 2026-02-13 | [132 empty] | Liv
1096 | 17 | 1096-17 | 2133 | PWA |  | 4999 | Dowie Way | Munno Para | Res 17 | 4999 Dowie Way, Munno Para Res 17 | [5 empty] | 14/04 - PA lodged. |  | Mitch G | [39 empty] | 2026-02-13 | [132 empty] | Liv
1096 | 18 | 1096-18 | 2134 | PWA |  | 4999 | Dowie Way | Munno Para | Res 18 | 4999 Dowie Way, Munno Para Res 18 | [5 empty] | 14/04 - PA lodged. |  | Mitch G | [39 empty] | 2026-02-13 | [132 empty] | Liv
1096 | 19 | 1096-19 | 2135 | PWA |  | 4999 | Dowie Way | Munno Para | Res 19 | 4999 Dowie Way, Munno Para Res 19 | [5 empty] | 14/04 - PA lodged. |  | Mitch G | [39 empty] | 2026-02-13 | [132 empty] | Liv
1096 | 20 | 1096-20 | 2136 | PWA |  | 4999 | Dowie Way | Munno Para | Res 20 | 4999 Dowie Way, Munno Para Res 20 | [5 empty] | 14/04 - PA lodged. |  | Mitch G | [39 empty] | 2026-02-13 | [132 empty] | Liv
1096 | 21 | 1096-21 | 2137 | PWA |  | 4999 | Dowie Way | Munno Para | Res 21 | 4999 Dowie Way, Munno Para Res 21 | [5 empty] | 14/04 - PA lodged. |  | Mitch G | [39 empty] | 2026-02-13 | [132 empty] | Liv
1096 | 22 | 1096-22 | 2138 | PWA |  | 4999 | Dowie Way | Munno Para | Res 22 | 4999 Dowie Way, Munno Para Res 22 | [5 empty] | 14/04 - PA lodged. |  | Mitch G | [39 empty] | 2026-02-13 | [132 empty] | Liv
1096 | 23 | 1096-23 | 2139 | PWA |  | 4999 | Dowie Way | Munno Para | Res 23 | 4999 Dowie Way, Munno Para Res 23 | [5 empty] | 14/04 - PA lodged. |  | Mitch G | [39 empty] | 2026-02-13 | [132 empty] | Liv
1096 | 24 | 1096-24 | 2140 | PWA |  | 4999 | Dowie Way | Munno Para | Res 24 | 4999 Dowie Way, Munno Para Res 24 | [5 empty] | 14/04 - PA lodged. |  | Mitch G | [39 empty] | 2026-02-13 | [132 empty] | Liv
1096 | 25 | 1096-25 | 2141 | PWA |  | 4999 | Dowie Way | Munno Para | Res 25 | 4999 Dowie Way, Munno Para Res 25 | [5 empty] | 14/04 - PA lodged. |  | Mitch G | [39 empty] | 2026-02-13 | [132 empty] | Liv
1096 | 26 | 1096-26 | 2142 | PWA |  | 4999 | Dowie Way | Munno Para | Res 26 | 4999 Dowie Way, Munno Para Res 26 | [5 empty] | 14/04 - PA lodged. |  | Mitch G | [39 empty] | 2026-02-13 | [132 empty] | Liv
1096 | 27 | 1096-27 | 2143 | PWA |  | 4999 | Dowie Way | Munno Para | Res 27 | 4999 Dowie Way, Munno Para Res 27 | [5 empty] | 14/04 - PA lodged. |  | Mitch G | [39 empty] | 2026-02-13 | [132 empty] | Liv
1096 | 28 | 1096-28 | 2144 | PWA |  | 4999 | Dowie Way | Munno Para | Res 28 | 4999 Dowie Way, Munno Para Res 28 | [5 empty] | 14/04 - PA lodged. |  | Mitch G | [39 empty] | 2026-02-13 | [132 empty] | Liv
1096 | 29 | 1096-29 | 2145 | PWA |  | 4999 | Dowie Way | Munno Para | Res 29 | 4999 Dowie Way, Munno Para Res 29 | [5 empty] | 14/04 - PA lodged. |  | Mitch G | [172 empty] | Liv
1097 | 01 | 1097-01 | 2147 | PWA |  | 60&62 | Gordons St | Aldinga Beach | Res 1 | 60 & 62 Gordons St, Aldinga Beach Res 1 | [5 empty] | 2/06 - In for PA |  | Brenton G | [172 empty] | Liv
1097 | 02 | 1097-02 | 2148 | PWA |  | 60&62 | Gordons St | Aldinga Beach | Res 2 | 60 & 62 Gordons St, Aldinga Beach Res 2 | [5 empty] | 2/06 - In for PA |  | Brenton G | [172 empty] | Liv
1097 | 03 | 1097-03 | 2149 | PWA |  | 60&62 | Gordons St | Aldinga Beach | Res 3 | 60 & 62 Gordons St, Aldinga Beach Res 3 | [5 empty] | 2/06 - In for PA |  | Brenton G | [172 empty] | Liv
1097 | 04 | 1097-04 | 2150 | PWA |  | 60&62 | Gordons St | Aldinga Beach | Res 4 | 60 & 62 Gordons St, Aldinga Beach Res 4 | [5 empty] | 2/06 - In for PA |  | Brenton G | [172 empty] | Liv
1098 | 01 | 1098-01 | 2151 | PWA |  | 17 | Nashwauk Cres Moana |  | Res 1 | 17 Nashwauk Cres Moana Res 1 | [5 empty] | 12/05 - with clients |  | Brenton G | [172 empty] | Liv
1098 | 02 | 1098-02 | 2152 | PWA |  | 17 | Nashwauk Cres Moana |  | Res 2 | 17 Nashwauk Cres Moana Res 2 | [5 empty] | 12/05 - with clients |  | Brenton G | [172 empty] | Liv
1098 | 03 | 1098-03 | 2153 | PWA |  | 17 | Nashwauk Cres Moana |  | Res 3 | 17 Nashwauk Cres Moana Res 3 | [5 empty] | 12/05 - with clients |  | Brenton G | [172 empty] | Liv
1099 | 01 | 1099-01 | 2154 | PWA |  | 7 | Robinsons Rd | Old Noarlunga | Res 1 | 7 Robinsons Rd, Old Noarlunga Res 1 | [5 empty] | 16/06 - Logged for PA |  | Brenton G | [172 empty] | Liv
1099 | 02 | 1099-02 | 2155 | PWA |  | 7 | Robinsons Rd | Old Noarlunga | Res 2 | 7 Robinsons Rd, Old Noarlunga Res 2 | [5 empty] | 16/06 - Logged for PA |  | Brenton G | [172 empty] | Liv
1099 | 03 | 1099-03 | 2156 | PWA |  | 7 | Robinsons Rd | Old Noarlunga | Res 3 | 7 Robinsons Rd, Old Noarlunga Res 3 | [5 empty] | 16/06 - Logged for PA |  | Brenton G | [172 empty] | Liv
1099 | 04 | 1099-04 | 2157 | PWA |  | 7 | Robinsons Rd | Old Noarlunga | Res 4 | 7 Robinsons Rd, Old Noarlunga Res 4 | [5 empty] | 16/06 - Logged for PA |  | Brenton G | [172 empty] | Liv
1099 | 05 | 1099-05 | 2158 | PWA |  | 7 | Robinsons Rd | Old Noarlunga | Res 5 | 7 Robinsons Rd, Old Noarlunga Res 5 | [5 empty] | 16/06 - Logged for PA |  | Brenton G | [172 empty] | Liv
1099 | 06 | 1099-06 | 2159 | PWA |  | 7 | Robinsons Rd | Old Noarlunga | Res 6 | 7 Robinsons Rd, Old Noarlunga Res 6 | [5 empty] | 16/06 - Logged for PA |  | Brenton G | [172 empty] | Liv
1100 | 01 | 1100-01 | 2160 | [14 empty] | Brenton G
1101 | 001 | 1101-001 | 2161 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 1 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 1
1101 | 002 | 1101-002 | 2162 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 2 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 2
1101 | 003 | 1101-003 | 2163 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 3 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 3
1101 | 004 | 1101-004 | 2164 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 4 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 4
1101 | 005 | 1101-005 | 2165 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 5 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 5
1101 | 006 | 1101-006 | 2166 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 6 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 6
1101 | 007 | 1101-007 | 2167 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 7 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 7
1101 | 008 | 1101-008 | 2168 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 8 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 8
1101 | 009 | 1101-009 | 2169 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 9 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 9
1101 | 010 | 1101-010 | 2170 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 10 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 10
1101 | 011 | 1101-011 | 2171 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 11 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 11
1101 | 012 | 1101-012 | 2172 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 12 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 12
1101 | 013 | 1101-013 | 2173 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 13 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 13
1101 | 014 | 1101-014 | 2174 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 14 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 14
1101 | 015 | 1101-015 | 2175 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 15 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 15
1101 | 016 | 1101-016 | 2176 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 16 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 16
1101 | 017 | 1101-017 | 2177 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 17 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 17
1101 | 018 | 1101-018 | 2178 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 18 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 18
1101 | 019 | 1101-019 | 2179 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 19 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 19
1101 | 020 | 1101-020 | 2180 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 20 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 20
1101 | 021 | 1101-021 | 2181 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 21 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 21
1101 | 022 | 1101-022 | 2182 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 22 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 22
1101 | 023 | 1101-023 | 2183 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 23 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 23
1101 | 024 | 1101-024 | 2184 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 24 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 24
1101 | 025 | 1101-025 | 2185 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 25 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 25
1101 | 026 | 1101-026 | 2186 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 26 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 26
1101 | 027 | 1101-027 | 2187 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 27 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 27
1101 | 028 | 1101-028 | 2188 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 28 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 28
1101 | 029 | 1101-029 | 2189 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 29 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 29
1101 | 030 | 1101-030 | 2190 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 30 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 30
1101 | 031 | 1101-031 | 2191 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 31 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 31
1101 | 032 | 1101-032 | 2192 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 32 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 32
1101 | 033 | 1101-033 | 2193 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 33 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 33
1101 | 034 | 1101-034 | 2194 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 34 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 34
1101 | 035 | 1101-035 | 2195 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 35 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 35
1101 | 036 | 1101-036 | 2196 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 36 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 36
1101 | 037 | 1101-037 | 2197 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 37 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 37
1101 | 038 | 1101-038 | 2198 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 38 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 38
1101 | 039 | 1101-039 | 2199 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 39 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 39
1101 | 040 | 1101-040 | 2200 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 40 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 40
1101 | 041 | 1101-041 | 2201 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 41 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 41
1101 | 042 | 1101-042 | 2202 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 42 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 42
1101 | 043 | 1101-043 | 2203 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 43 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 43
1101 | 044 | 1101-044 | 2204 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 44 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 44
1101 | 045 | 1101-045 | 2205 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 45 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 45
1101 | 046 | 1101-046 | 2206 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 46 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 46
1101 | 047 | 1101-047 | 2207 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 47 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 47
1101 | 048 | 1101-048 | 2208 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 48 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 48
1101 | 049 | 1101-049 | 2209 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 49 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 49
1101 | 050 | 1101-050 | 2210 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 50 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 50
1101 | 051 | 1101-051 | 2211 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 51 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 51
1101 | 052 | 1101-052 | 2212 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 52 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 52
1101 | 053 | 1101-053 | 2213 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 53 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 53
1101 | 054 | 1101-054 | 2214 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 54 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 54
1101 | 055 | 1101-055 | 2215 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 55 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 55
1101 | 056 | 1101-056 | 2216 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 56 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 56
1101 | 057 | 1101-057 | 2217 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 57 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 57
1101 | 058 | 1101-058 | 2218 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 58 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 58
1101 | 059 | 1101-059 | 2219 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 59 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 59
1101 | 060 | 1101-060 | 2220 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 60 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 60
1101 | 061 | 1101-061 | 2221 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 61 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 61
1101 | 062 | 1101-062 | 2222 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 62 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 62
1101 | 063 | 1101-063 | 2223 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 63 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 63
1101 | 064 | 1101-064 | 2224 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 64 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 64
1101 | 065 | 1101-065 | 2225 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 65 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 65
1101 | 066 | 1101-066 | 2226 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 66 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 66
1101 | 067 | 1101-067 | 2227 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 67 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 67
1101 | 068 | 1101-068 | 2228 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 68 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 68
1101 | 069 | 1101-069 | 2229 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 69 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 69
1101 | 070 | 1101-070 | 2230 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 70 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 70
1101 | 071 | 1101-071 | 2231 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 71 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 71
1101 | 072 | 1101-072 | 2232 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 72 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 72
1101 | 073 | 1101-073 | 2233 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 73 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 73
1101 | 074 | 1101-074 | 2234 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 74 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 74
1101 | 075 | 1101-075 | 2235 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 75 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 75
1101 | 076 | 1101-076 | 2236 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 76 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 76
1101 | 077 | 1101-077 | 2237 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 77 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 77
1101 | 078 | 1101-078 | 2238 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 78 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 78
1101 | 079 | 1101-079 | 2239 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 79 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 79
1101 | 080 | 1101-080 | 2240 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 80 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 80
1101 | 081 | 1101-081 | 2241 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 81 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 81
1101 | 082 | 1101-082 | 2242 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 82 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 82
1101 | 083 | 1101-083 | 2243 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 83 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 83
1101 | 084 | 1101-084 | 2244 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 84 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 84
1101 | 085 | 1101-085 | 2245 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 85 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 85
1101 | 086 | 1101-086 | 2246 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 86 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 86
1101 | 087 | 1101-087 | 2247 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 87 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 87
1101 | 088 | 1101-088 | 2248 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 88 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 88
1101 | 089 | 1101-089 | 2249 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 89 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 89
1101 | 090 | 1101-090 | 2250 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 90 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 90
1101 | 091 | 1101-091 | 2251 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 91 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 91
1101 | 092 | 1101-092 | 2252 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 92 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 92
1101 | 093 | 1101-093 | 2253 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 93 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 93
1101 | 094 | 1101-094 | 2254 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 94 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 94
1101 | 095 | 1101-095 | 2255 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 95 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 95
1101 | 096 | 1101-096 | 2256 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 96 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 96
1101 | 097 | 1101-097 | 2257 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 97 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 97
1101 | 098 | 1101-098 | 2258 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 98 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 98
1101 | 099 | 1101-099 | 225 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 99 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 99
1101 | 100 | 1101-100 | 2260 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 100 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 100
1101 | 101 | 1101-101 | 2261 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 101 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 101
1101 | 102 | 1101-102 | 2262 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 102 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 102
1101 | 103 | 1101-103 | 2263 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 103 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 103
1101 | 104 | 1101-104 | 2264 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 104 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 104
1101 | 105 | 1101-105 | 2265 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 105 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 105
1101 | 106 | 1101-106 | 2266 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 106 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 106
1101 | 107 | 1101-107 | 2267 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 107 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 107
1101 | 108 | 1101-108 | 2268 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 108 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 108
1101 | 109 | 1101-109 | 2269 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 109 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 109
1101 | 110 | 1101-110 | 2270 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 110 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 110
1101 | 111 | 1101-111 | 2271 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 110 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 110
1101 | 112 | 1101-112 | 2272 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 112 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 112
1101 | 113 | 1101-113 | 2273 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 113 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 113
1101 | 114 | 1101-114 | 2274 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 114 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 114
1101 | 115 | 1101-115 | 2275 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 115 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 115
1101 | 116 | 1101-116 | 2276 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 116 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 116
1101 | 117 | 1101-117 | 2277 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 117 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 117
1101 | 118 | 1101-118 | 2278 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 118 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 118
1101 | 119 | 1101-119 | 2279 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 119 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 119
1101 | 120 | 1101-120 | 2280 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 120 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 120
1101 | 121 | 1101-121 | 2281 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 121 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 121
1101 | 122 | 1101-122 | 2282 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 122 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 122
1101 | 123 | 1101-123 | 2283 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 123 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 123
1101 | 124 | 1101-124 | 2284 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 124 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 124
1101 | 125 | 1101-125 | 2285 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 125 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 125
1101 | 126 | 1101-126 | 2286 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 126 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 126
1101 | 127 | 1101-127 | 2287 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 127 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 127
1101 | 128 | 1101-128 | 2288 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 128 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 128
1101 | 129 | 1101-129 | 2289 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 129 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 129
1101 | 130 | 1101-130 | 2290 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 130 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 130
1101 | 131 | 1101-131 | 2291 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 131 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 131
1101 | 132 | 1101-132 | 2292 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 132 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 132
1101 | 133 | 1101-133 | 2293 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 133 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 133
1101 | 134 | 1101-134 | 2294 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 134 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 134
1101 | 135 | 1101-135 | 2295 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 135 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 135
1101 | 136 | 1101-136 | 2296 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 136 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 136
1101 | 137 | 1101-137 | 2297 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 137 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 137
1101 | 138 | 1101-138 | 2298 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 138 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 138
1101 | 139 | 1101-139 | 2299 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 139 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 139
1101 | 140 | 1101-140 | 2300 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 140 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 140
1101 | 141 | 1101-141 | 2301 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 141 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 141
1101 | 142 | 1101-142 | 2302 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 142 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 142
1101 | 143 | 1101-143 | 2303 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 143 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 143
1101 | 144 | 1101-144 | 2304 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 144 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 144
1101 | 145 | 1101-145 | 2305 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 145 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 145
1101 | 146 | 1101-146 | 2306 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 146 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 146
1101 | 147 | 1101-147 | 2307 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 147 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 147
1101 | 148 | 1101-148 | 2308 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 148 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 148
1101 | 149 | 1101-149 | 2309 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 149 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 149
1101 | 150 | 1101-150 | 2310 |  |  | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | Res 150 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 150
1102 | 01 | 1102-01 | 2311 | PWA |  | 25 | Tiller Drive | Seaford | res 1 | 25 Tiller Drive, Seaford res 1 | [5 empty] | 16/6 - Logged for PA |  | Brenton G | [172 empty] | Liv
1102 | 02 | 1102-02 | 2312 | PWA |  | 25 | Tiller Drive | Seaford | res 2 | 25 Tiller Drive, Seaford res 2 | [5 empty] | 16/6 - Logged for PA |  | Brenton G | [172 empty] | Liv
1102 | 03 | 1102-03 | 2313 | PWA |  | 25 | Tiller Drive | Seaford | res 3 | 25 Tiller Drive, Seaford res 3 | [5 empty] | 16/6 - Logged for PA |  | Brenton G | [172 empty] | Liv
1103 | 01 | 1103-01 | 2314 | PWA |  | 247 | Main South Road | Hackham West | Res 1 | 247 Main South Road, Hackham West Res 1 | [5 empty] | 26/05 - In for PDs. awaiting civils |  | Brenton G | [172 empty] | Liv
1103 | 02 | 1103-02 | 2315 | PWA |  | 247 | Main South Road | Hackham West | Res 2 | 247 Main South Road, Hackham West Res 2 | [5 empty] | 26/05 - In for PDs. awaiting civils |  | Brenton G | [172 empty] | Liv
1103 | 03 | 1103-03 | 2316 | PWA |  | 247 | Main South Road | Hackham West | Res 3 | 247 Main South Road, Hackham West Res 3 | [5 empty] | 26/05 - In for PDs. awaiting civils |  | Brenton G | [172 empty] | Liv
1104 | 01 | 1104-01 | 2317 | PWA |  | 3&5 | Wootton Street | Davoren Park | Res 1 | 3 & 5 Wootton Street, Davoren Park Res 1 | [5 empty] | 26/05 - In for PDs |  | Brenton G | [172 empty] | Liv
1104 | 02 | 1104-02 | 2318 | PWA |  | 3&5 | Wootton Street | Davoren Park | Res 2 | 3 & 5 Wootton Street, Davoren Park Res 2 | [5 empty] | 26/05 - In for PDs |  | Brenton G | [172 empty] | Liv
1104 | 03 | 1104-03 | 2319 | PWA |  | 3&5 | Wootton Street | Davoren Park | Res 3 | 3 & 5 Wootton Street, Davoren Park Res 3 | [5 empty] | 26/05 - In for PDs |  | Brenton G | [172 empty] | Liv
1104 | 04 | 1104-04 | 2320 | PWA |  | 3&5 | Wootton Street | Davoren Park | Res 4 | 3 & 5 Wootton Street, Davoren Park Res 4 | [5 empty] | 26/05 - In for PDs |  | Brenton G | [172 empty] | Liv
1104 | 05 | 1104-05 | 2321 | PWA |  | 3&5 | Wootton Street | Davoren Park | Res 5 | 3 & 5 Wootton Street, Davoren Park Res 5 | [5 empty] | 26/05 - In for PDs |  | Brenton G | [172 empty] | Liv
1104 | 06 | 1104-06 | 2322 | PWA |  | 3&5 | Wootton Street | Davoren Park | Res 6 | 3 & 5 Wootton Street, Davoren Park Res 6 | [5 empty] | 26/05 - In for PDs |  | Brenton G | [172 empty] | Liv
1104 | 07 | 1104-07 | 2323 | PWA |  | 3&5 | Wootton Street | Davoren Park | Res 7 | 3 & 5 Wootton Street, Davoren Park Res 7 | [5 empty] | 26/05 - In for PDs |  | Brenton G | [172 empty] | Liv
1105 | 01 | 1105-01 | 2324 | PWA |  | 48 | Streeters Road | North Plympton | Res 1 | 48 Streeters Road, North Plympton Res 1 | [5 empty] | 26/05 - Logged for PDs. In for surveys |  | Brenton G | [172 empty] | Liv
1105 | 02 | 1105-02 | 2325 | PWA |  | 48 | Streeters Road | North Plympton | Res 2 | 48 Streeters Road, North Plympton Res 2 | [5 empty] | 26/05 - Logged for PDs. In for surveys |  | Brenton G | [172 empty] | Liv
1105 | 03 | 1105-03 | 2326 | PWA |  | 48 | Streeters Road | North Plympton | Res 3 | 48 Streeters Road, North Plympton Res 3 | [5 empty] | 26/05 - Logged for PDs. In for surveys |  | Brenton G | [172 empty] | Liv
1106 | 01 | 1106-01 | 2327 | PWA |  | 10 | Friar Street | Enfield | Res 1 | 10 Friar Street, Enfield Res 1 | [5 empty] | 29/06 - PDs done. Waiting on civils |  | Mitch G | [172 empty] | Liv
1106 | 02 | 1106-02 | 2328 | PWA |  | 10 | Friar Street | Enfield | Res 2 | 10 Friar Street, Enfield Res 2 | [5 empty] | 29/06 - PDs done. Waiting on civils |  | Mitch G | [172 empty] | Liv
1106 | 03 | 1106-03 | 2329 | PWA |  | 10 | Friar Street | Enfield | Res 3 | 10 Friar Street, Enfield Res 3 | [5 empty] | 29/06 - PDs done. Waiting on civils |  | Mitch G | [172 empty] | Liv
1107 | 01 | 1107-01 | 2330 | PWA |  | 10 | Copernicus Road | Christies Beach |  | 10 Copernicus Road, Christies Beach | [5 empty] | 22/6 - IN for PDs . Ordered surveys |  | Brenton G | [172 empty] | Liv
1107 | 02 | 1107-02 | 2331 | PWA |  | 10 | Copernicus Road | Christies Beach |  | 10 Copernicus Road, Christies Beach | [5 empty] | 22/6 - IN for PDs . Ordered surveys |  | Brenton G | [172 empty] | Liv
1107 | 03 | 1107-03 | 2332 | PWA |  | 10 | Copernicus Road | Christies Beach |  | 10 Copernicus Road, Christies Beach | [5 empty] | 22/6 - IN for PDs . Ordered surveys |  | Brenton G | [172 empty] | Liv
1107 | 04 | 1107-04 | 2333 | PWA |  | 10 | Copernicus Road | Christies Beach |  | 10 Copernicus Road, Christies Beach | [5 empty] | 22/6 - IN for PDs . Ordered surveys |  | Brenton G | [172 empty] | Liv
1108 | 01 | 1108-01 | 2334 | PWA |  | 3 | Patella Street | Seaford rise |  | 3 Patella Street, Seaford rise | [5 empty] | 2/6 - Logged for CDs. Ordered surveys |  | Brenton G | [172 empty] | Liv
1108 | 02 | 1108-02 | 2335 | PWA |  | 3 | Patella Street | Seaford rise |  | 3 Patella Street, Seaford rise | [5 empty] | 2/6 - Logged for CDs. Ordered surveys |  | Brenton G | [172 empty] | Liv
1108 | 03 | 1108-03 | 2336 | PWA |  | 3 | Patella Street | Seaford rise |  | 3 Patella Street, Seaford rise | [5 empty] | 2/6 - Logged for CDs. Ordered surveys |  | Brenton G | [172 empty] | Liv
1108 | 04 | 1108-04 | 2337 | PWA |  | 3 | Patella Street | Seaford rise |  | 3 Patella Street, Seaford rise | [5 empty] | 2/6 - Logged for CDs. Ordered surveys |  | Brenton G | [172 empty] | Liv
1109 | 01 | 1109-01 | 2338 | PWA |  | 21 | Mirrimar Crescent | Reynella |  | 21 Mirrimar Crescent, Reynella | [5 empty] | 29/6 - Logged for PDs. Waiting on surveys |  | Brenton G | [172 empty] | Liv
1109 | 02 | 1109-02 | 2339 | PWA |  | 21 | Mirrimar Crescent | Reynella |  | 21 Mirrimar Crescent, Reynella | [5 empty] | 29/6 - Logged for PDs. Waiting on surveys |  | Brenton G | [172 empty] | Liv
1109 | 03 | 1109-03 | 2340 | PWA |  | 21 | Mirrimar Crescent | Reynella |  | 21 Mirrimar Crescent, Reynella | [5 empty] | 29/6 - Logged for PDs. Waiting on surveys |  | Brenton G | [172 empty] | Liv
1110 | 01 | 1110-01 | 2341 | PWA |  | 10 | Pope Cres | Hope Valley | Res 1 | 10 Pope Cres, Hope Valley Res 1 | [5 empty] | 22/6 - Logged for CDs. |  | Brenton G | [172 empty] | Liv
1110 | 02 | 1110-02 | 2342 | PWA |  | 10 | Pope Cres | Hope Valley | Res 2 | 10 Pope Cres, Hope Valley Res 2 | [5 empty] | 22/6 - Logged for CDs. |  | Brenton G | [172 empty] | Liv
1110 | 03 | 1110-03 | 2343 | PWA |  | 10 | Pope Cres | Hope Valley | Res 3 | 10 Pope Cres, Hope Valley Res 3 | [5 empty] | 22/6 - Logged for CDs. |  | Brenton G | [172 empty] | Liv
1111 | 01 | 1111-01 | 2344 | PWA |  | 26 | Davenport Terrace | Seacliff Park | Res 1 | 26 Davenport Terrace, Seacliff Park Res 1 | [5 empty] | 29/6 - PDs done. - surveys to be overlaid |  | Brenton G | [172 empty] | Liv
1111 | 02 | 1111-02 | 2345 | PWA |  | 26 | Davenport Terrace | Seacliff Park | Res 2 | 26 Davenport Terrace, Seacliff Park Res 2 | [5 empty] | 29/6 - PDs done. - surveys to be overlaid |  | Brenton G | [172 empty] | Liv
1111 | 03 | 1111-03 | 2346 | PWA |  | 26 | Davenport Terrace | Seacliff Park | Res 3 | 26 Davenport Terrace, Seacliff Park Res 3 | [5 empty] | 29/6 - PDs done. - surveys to be overlaid |  | Brenton G | [172 empty] | Liv
1112 | 01 | 1112-01 | 2347 | PWA |  | 3 | Ross Street | Brighton | Res 1 | 3 Ross Street, Brighton Res 1 | [5 empty] | 29/6 - CDs done. Ordered surveys |  | Gary P | [172 empty] | Liv
1112 | 02 | 1112-02 | 2348 | PWA |  | 3 | Ross Street | Brighton | REs 2 | 3 Ross Street, Brighton REs 2 | [5 empty] | 29/6 - CDs done. Ordered surveys | [174 empty] | Liv
1112 | 03 | 1112-03 | 2349 | PWA |  | 3 | Ross Street | Brighton | REs 3 | 3 Ross Street, Brighton REs 3 | [5 empty] | 29/6 - CDs done. Ordered surveys | [174 empty] | Liv
1113 | 01 | 1113-01 | 2350 | PWA |  | 120 | Clairville Road | Newton | Res 1 | 120 Clairville Road, Newton Res 1 | [5 empty] | 16/6 - Logged for CDs. Ordered surveys |  | Brenton G | [172 empty] | Liv
1113 | 02 | 1113-02 | 2351 | PWA |  | 120 | Clairville Road | Newton | Res 2 | 120 Clairville Road, Newton Res 2 | [5 empty] | 16/6 - Logged for CDs. Ordered surveys |  | Brenton G | [172 empty] | Liv
1113 | 03 | 1113-03 | 2352 | PWA |  | 120 | Clairville Road | Newton | Res 3 | 120 Clairville Road, Newton Res 3 | [5 empty] | 16/6 - Logged for CDs. Ordered surveys |  | Brenton G | [172 empty] | Liv
1114 | 01 | 1114-01 | 2353 | PWA |  | 8 | Breckenridge Road | Reynella | Res 1 | 8 Breckenridge Road, Reynella Res 1 | [5 empty] | 22/06 - To be logged for CDs |  | Brenton G | [172 empty] | Liv
1114 | 02 | 1114-02 | 2354 | PWA |  | 8 | Breckenridge Road | Reynella | Res 2 | 8 Breckenridge Road, Reynella Res 2 | [5 empty] | 22/06 - To be logged for CDs |  | Brenton G | [172 empty] | Liv
1114 | 03 | 1114-03 | 2355 | PWA |  | 8 | Breckenridge Road | Reynella | Res 3 | 8 Breckenridge Road, Reynella Res 3 | [5 empty] | 22/06 - To be logged for CDs |  | Brenton G | [172 empty] | Liv
1115 | 01 | 1115-01 | 2356 | PWA |  | 24 | Homington Road | Elizabeth North | Res 1 | 24 Homington Road, Elizabeth North Res 1 | [5 empty] | 22/06 - To be logged for CDs |  | Brenton G | [172 empty] | Liv
1115 | 02 | 1115-02 | 2357 | PWA |  | 24 | Homington Road | Elizabeth North | Res 2 | 24 Homington Road, Elizabeth North Res 2 | [5 empty] | 22/06 - To be logged for CDs |  | Brenton G | [172 empty] | Liv
1115 | 03 | 1115-03 | 2358 | PWA |  | 24 | Homington Road | Elizabeth North | Res 3 | 24 Homington Road, Elizabeth North Res 3 | [5 empty] | 22/06 - To be logged for CDs | [174 empty] | Liv
1116 | 01 | 1116-01 | 2359 | PWA |  | 24 | Brodie Road | Reynella | Res 1 | 24 Brodie Road, Reynella Res 1 | [5 empty] | 22/6 - Logged for CDs. | [174 empty] | Liv
1116 | 02 | 1116-02 | 2360 | PWA |  | 24 | Brodie Road | Reynella | Res 2 | 24 Brodie Road, Reynella Res 2 | [5 empty] | 22/6 - Logged for CDs. | [174 empty] | Liv
1116 | 03 | 1116-03 | 2361 | PWA |  | 24 | Brodie Road | Reynella | Res 3 | 24 Brodie Road, Reynella Res 3 | [5 empty] | 22/6 - Logged for CDs. | [174 empty] | Liv
1117 | 01 | 1117-01 | 2362 | PWA |  | 83 | A Awoonga Road | Hope Valley | Res 1 | 83A Awoonga Road, Hope Valley Res 1 | [180 empty] | Liv
1117 | 02 | 1117-02 | 2363 | PWA |  | 83 | A Awoonga Road | Hope Valley | Res 2 | 83A Awoonga Road, Hope Valley Res 2 | [180 empty] | Liv
1117 | 03 | 1117-03 | 2364 | PWA |  | 83 | A Awoonga Road | Hope Valley | Res 3 | 83A Awoonga Road, Hope Valley Res 3 | [180 empty] | Liv
1117 | 04 | 1117-04 | 2365 | PWA |  | 83 | A Awoonga Road | Hope Valley | Res 4 | 83A Awoonga Road, Hope Valley Res 4 | [180 empty] | Liv
1117 | 05 | 1117-05 | 2366 | PWA |  | 83 | A Awoonga Road | Hope Valley | Res 5 | 83A Awoonga Road, Hope Valley Res 5 | [180 empty] | Liv
1117 | 06 | 1117-06 | 2367 | PWA |  | 83 | A Awoonga Road | Hope Valley | Res 6 | 83A Awoonga Road, Hope Valley Res 6 | [180 empty] | Liv
1117 | 07 | 1117-07 | 2368 | PWA |  | 83 | A Awoonga Road | Hope Valley | Res 7 | 83A Awoonga Road, Hope Valley Res 7 | [180 empty] | Liv
1117 | 08 | 1117-08 | 2369 | PWA |  | 83 | A Awoonga Road | Hope Valley | Res 8 | 83A Awoonga Road, Hope Valley Res 8 | [180 empty] | Liv
1117 | 09 | 1117-09 | 2370 | PWA |  | 83 | A Awoonga Road | Hope Valley | Res 9 | 83A Awoonga Road, Hope Valley Res 9 | [180 empty] | Liv
1117 | 10 | 1117-10 | 2371 | PWA |  | 83 | A Awoonga Road | Hope Valley | Res 10 | 83A Awoonga Road, Hope Valley Res 10 | [180 empty] | Liv
1117 | 11 | 1117-11 | 2372 | PWA |  | 83 | A Awoonga Road | Hope Valley | Res 11 | 83A Awoonga Road, Hope Valley Res 11 | [180 empty] | Liv
1117 | 12 | 1117-12 | 2373 | PWA |  | 83 | A Awoonga Road | Hope Valley | Res 12 | 83A Awoonga Road, Hope Valley Res 12 | [180 empty] | Liv
1117 | 13 | 1117-13 | 2374 | PWA |  | 83 | A Awoonga Road | Hope Valley | Res 13 | 83A Awoonga Road, Hope Valley Res 13 | [180 empty] | Liv
1117 | 14 | 1117-14 | 2375 | PWA |  | 83 | A Awoonga Road | Hope Valley | Res 14 | 83A Awoonga Road, Hope Valley Res 14 | [180 empty] | Liv
1117 | 15 | 1117-15 | 2376 | PWA |  | 83 | A Awoonga Road | Hope Valley | Res 15 | 83A Awoonga Road, Hope Valley Res 15 | [180 empty] | Liv
1117 | 16 | 1117-16 | 2377 | PWA |  | 83 | A Awoonga Road | Hope Valley | Res 16 | 83A Awoonga Road, Hope Valley Res 16 | [180 empty] | Liv
1117 | 17 | 1117-17 | 2378 | PWA |  | 83 | A Awoonga Road | Hope Valley | Res 17 | 83A Awoonga Road, Hope Valley Res 17 | [180 empty] | Liv
1117 | 18 | 1117-18 | 2379 | PWA |  | 83 | A Awoonga Road | Hope Valley | Res 18 | 83A Awoonga Road, Hope Valley Res 18 | [180 empty] | Liv
1117 | 19 | 1117-19 | 2380 | PWA |  | 83 | A Awoonga Road | Hope Valley | Res 19 | 83A Awoonga Road, Hope Valley Res 19 | [180 empty] | Liv
1117 | 20 | 1117-20 | 2381 | PWA |  | 83 | A Awoonga Road | Hope Valley | Res 20 | 83A Awoonga Road, Hope Valley Res 20 | [180 empty] | Liv
1117 | 21 | 1117-21 | 2382 | PWA |  | 83 | A Awoonga Road | Hope Valley | Res 21 | 83A Awoonga Road, Hope Valley Res 21 | [180 empty] | Liv
1117 | 22 | 1117-22 | 2383 | PWA |  | 83 | A Awoonga Road | Hope Valley | Res 22 | 83A Awoonga Road, Hope Valley Res 22 | [180 empty] | Liv
1117 | 23 | 1117-23 | 2384 | PWA |  | 83 | A Awoonga Road | Hope Valley | Res 23 | 83A Awoonga Road, Hope Valley Res 23 | [180 empty] | Liv
1117 | 24 | 1117-24 | 2385 | PWA |  | 83 | A Awoonga Road | Hope Valley | Res 24 | 83A Awoonga Road, Hope Valley Res 24 | [180 empty] | Liv
1117 | 25 | 1117-25 | 2386 | PWA |  | 83 | A Awoonga Road | Hope Valley | Res 25 | 83A Awoonga Road, Hope Valley Res 25 | [180 empty] | Liv
1117 | 26 | 1117-26 | 2387 | PWA |  | 83 | A Awoonga Road | Hope Valley | Res 26 | 83A Awoonga Road, Hope Valley Res 26 | [180 empty] | Liv
1117 | 27 | 1117-27 | 2388 | PWA |  | 83 | A Awoonga Road | Hope Valley | Res 27 | 83A Awoonga Road, Hope Valley Res 27 | [180 empty] | Liv
1117 | 28 | 1117-28 | 2389 | PWA |  | 83 | A Awoonga Road | Hope Valley | Res 28 | 83A Awoonga Road, Hope Valley Res 28 | [180 empty] | Liv
1117 | 29 | 1117-29 | 2390 | PWA |  | 83 | A Awoonga Road | Hope Valley | Res 29 | 83A Awoonga Road, Hope Valley Res 29 | [180 empty] | Liv
1117 | 30 | 1117-30 | 2391 | PWA |  | 83 | A Awoonga Road | Hope Valley | Res 30 | 83A Awoonga Road, Hope Valley Res 30 | [180 empty] | Liv
1118 | 01 | 1118-01 | 2392 | PWA |  | 9 | Riders Street | Seacombe Gardens | Res 1 | 9 Riders Street, Seacombe Gardens Res 1 | [180 empty] | Liv
1118 | 02 | 1118-02 | 2393 | PWA |  | 9 | Riders Street | Seacombe Gardens | Res 2 | 9 Riders Street, Seacombe Gardens Res 2 | [180 empty] | Liv
1118 | 03 | 1118-03 | 2394 | PWA |  | 9 | Riders Street | Seacombe Gardens | Res 3 | 9 Riders Street, Seacombe Gardens Res 3 | [180 empty] | Liv
1119 | 01 | 1119-01 | 2395 | PWA |  | 27 | Howard Street | Windsor Gardens | Res 1 | 27 Howard Street, Windsor Gardens Res 1 | [180 empty] | Liv
1119 | 02 | 1119-02 | 2396 | PWA |  | 27 | Howard Street | Windsor Gardens | Res 2 | 27 Howard Street, Windsor Gardens Res 2 | [180 empty] | Liv
1119 | 03 | 1119-03 | 2397 | PWA |  | 27 | Howard Street | Windsor Gardens | Res 3 | 27 Howard Street, Windsor Gardens Res 3 | [180 empty] | Liv
1119 | 04 | 1119-04 | 2398 | PWA |  | 27 | Howard Street | Windsor Gardens | Res 4 | 27 Howard Street, Windsor Gardens Res 4 | [180 empty] | Liv
1120 | 01 | 1120-01 | 2399 |  |  | 14 | Brodie Road | Reynella | Res 1 | 14 Brodie Road, Reynella Res 1
1120 | 02 | 1120-02 | 2400 |  |  | 14 | Brodie Road | Reynella | Res 2 | 14 Brodie Road, Reynella Res 2
1120 | 03 | 1120-03 | 2401 |  |  | 14 | Brodie Road | Reynella | Res 3 | 14 Brodie Road, Reynella Res 3
1121 | 01 | 1121-01 | 2402 |  |  | 2 | A Launceston Ave | Warradale | Res 1 | 2A Launceston Ave, Warradale Res 1
1121 | 02 | 1121-02 | 2403 |  |  | 2 | A Launceston Ave | Warradale | Res 2 | 2A Launceston Ave, Warradale Res 2
1121 | 03 | 1121-03 | 2404 |  |  | 2 | A Launceston Ave | Warradale | Res 3 | 2A Launceston Ave, Warradale Res 3

## Project Summary
Project Number | Jobs in Project | Site Address (first job) | Street Number | Street | Suburb | Job Numbers | Old Job Numbers | Client Type | With
1001 | 1 | #61 Nelson Avenue, Flinders Park (Lot 611) | #61 | Nelson Avenue | Flinders Park | 1001-01 | 1200 | Residential | Vincent Iannazzone & Lisa Marie Iannazzone
1002 | 1 | #28 Primmer Avenue, Modbury North | #28 | Primmer Avenue | Modbury North | 1002-01 | 1230 | Residential | Mukhtar Jawidi & Kousar Mirzaei
1003 | 1 | #72 Birdwood Terrace, North Plympton (Lot 1) | #72 | Birdwood Terrace | North Plympton | 1003-01 | 1339 - D1 | Developer | Amirreza Jourabchi
1004 | 3 | #13 Perserverance Road, Tea Tree Gully (Lot 1) | #13 | Perserverance Road | Tea Tree Gully | 1004-01, 1004-02, 1004-03 | 1288 | Residential | Jarrad Martin Hawkins
1005 | 3 | #30 Luprena Avenue, Ingle Farm (Lot 3) | #30 | Luprena Avenue | Ingle Farm | 1005-01, 1005-02, 1005-03 | 1216 - D1, 1216 - D2, 1216 - D3 | Developer | Michelle & Peter Macfarlane
1006 | 3 | #1 Waninga Drive, Holden Hill SA 5088 | #1 | Waninga Drive | Holden Hill | 1006-01, 1006-02, 1006-03 | 1197 - D1, 1197 - D2, 1197 - D3 | Developer | Pavitar Dhillon
1007 | 13 | #13 Hunt Crescent, Christies Beach (Lot 9) | #13 | Hunt Crescent | Christies Beach | 1007-01, 1007-02, 1007-03, 1007-04, 1007-05, 1007-06, 1007-07, 1007-08, 1007-09, 1007-10, 1007-11, 1007-12, 1007-13 | 1126, 1126 - D1, 1126 - D10, 1126 - D11, 1126 - D12, 1126 - D2, 1126 - D3, 1126 - D4, 1126 - D5, 1126 - D6, 1126 - D7, 1126 - D8, 1126 - D9 | Developer | 13-15 Hunt Crescent Pty Ltd
1008 | 1 | 5A Dennis Crescent, Para Hills | 5 | A Dennis Crescent | Para Hills | 1008-01 | 1426 | Residential | Mirza Ali
1009 | 3 | #78 Queen Street, Norwood | #78 | Queen Street | Norwood | 1009-01, 1009-02, 1009-03 | 1399 | Developer | Annemarie & Premjeet Dhillon
1010 | 3 | 124 Nelson Road, Valley View (Lot 1) | 124 | Nelson Road | Valley View | 1010-01, 1010-02, 1010-03 | 1382 | Developer | Daniel Giles and Mitchelle Trezise
1011 | 1 | 1a Cootra Avenue , Parkside | 1a | Cootra Avenue | Parkside | 1011-01 | 1380 | Residential | Mein Douglas
1012 | 1 | 3 Wallis Street, Parkside | 3 | Wallis Street | Parkside | 1012-01 | 1379 | Residential | Mein Douglas
1013 | 2 | #137 Bradley Grove, Mitchell Park 5043 (Lot 300) | #137 | Bradley Grove | Mitchell Park | 1013-01, 1013-02 | 1265, 1325 | Residential | Christopher Edwards & Jennifer Edwards
1014 | 1 | #4a Gangara Avenue, Warradale | #4a | Gangara Avenue | Warradale | 1014-01 | 1324 | Residential | Barbara Puzio & Barry Pilkington
1015 | 1 | #6 Kareda Drive, Campbelltown (Lot 101) | #6 | Kareda Drive | Campbelltown | 1015-01 | 1217 | Residential | Emma Louise Frewin
1016 | 2 | #12 Foster Avenue, Paradise (Lot 1) | #12 | Foster Avenue | Paradise | 1016-01, 1016-02 |  | Developer | Sarah McInerney
1017 | 1 | #187 Portrush Road, Maylands (CA) | #187 | Portrush Road | Maylands | 1017-01 | 1005 | Developer | George Isaac
1018 | 1 | 200 Oakden Avenue, Oakden | 200 | Oakden Avenue | Oakden | 1018-01 | 1455 | Residential | Vedprakash Patel, Shruti Patel
1019 | 2 | 3 Cannes Avenue, Grange - Single Storey | 3 | Cannes Avenue | Grange | 1019-01, 1019-02 | 1457, 1458 | Developer | Mario Monteleone
1020 | 47 | 84 -88 Greentree Blvd Paralowie - Lot 10 | 84-88 | Greentree Blvd | Paralowie | 1020-01, 1020-02, 1020-03, 1020-04, 1020-05, 1020-06, 1020-07, 1020-08, 1020-09, 1020-10, 1020-11, 1020-12, 1020-13, 1020-14, 1020-15, 1020-16, 1020-17, 1020-18, 1020-19, 1020-20, 1020-21, 1020-22, 1020-23, 1020-24, 1020-25, 1020-26, 1020-27, 1020-28, 1020-29, 1020-30, 1020-31, 1020-32, 1020-33, 1020-34, 1020-35, 1020-36, 1020-37, 1020-38, 1020-39, 1020-40, 1020-41, 1020-42, 1020-43, 1020-44, 1020-45, 1020-46, 1020-47 | 1470, 1471, 1472, 1473, 1474, 1475, 1476, 1477, 1478, 1479, 1480, 1481, 1482, 1483, 1484, 1485, 1486, 1487, 1488, 1489, 1490, 1491, 1492, 1493, 1494, 1495, 1496, 1497, 1498, 1499, 1500, 1501, 1502, 1503, 1504, 1505, 1506, 1507, 1508, 1509, 1510, 1511, 1512, 1513, 1514, 1515, 1516 | Developer | Lofty Building Group
1021 | 1 | 9 Addison Ave, Marden | 9 | Addison Ave | Marden | 1021-01 | 1516 | Residential | Guri & Simer Kang
1022 | 1 | 17 Golding Street Beverley Lot 3 | 17 | Golding Street | Beverley | 1022-01 | 1517 | Developer | Lofty Building Group
1023 | 3 | 3 Daws Road, Mitchell Park - Lot 1 | 3 | Daws Road | Mitchell Park | 1023-01, 1023-02, 1023-03 | 1528 | Developer | Koteswara Rao Nalluri
1024 | 20 | Res 1 , Lot 311 (portion of lot 232) Dankie Rd, Murray Bridge |  | Dankie Rd | Murray Bridge | 1024-01, 1024-02, 1024-03, 1024-04, 1024-05, 1024-06, 1024-07, 1024-08, 1024-09, 1024-10, 1024-11, 1024-12, 1024-13, 1024-14, 1024-15, 1024-16, 1024-17, 1024-18, 1024-19, 1024-20 | 1576, 1577, 1578, 1579, 1580, 1581, 1582, 1583, 1584, 1585, 1586, 1587, 1588, 1589, 1590, 1591, 1592, 1593, 1594, 1595 | Developer | Lofty Building Group
1025 | 9 | Res 1, 4-11/9 Bald Street, Smithfield Plains | 4-11/9 | Bald Street | Smithfield Plains | 1025-01, 1025-02, 1025-03, 1025-04, 1025-05, 1025-06, 1025-07, 1025-08, 1025-09 | 1597 | Developer | Frank Cecere
1026 | 22 | 37 East Street, Hectorville | 37 | East Street | Hectorville | 1026-01, 1026-02, 1026-03, 1026-04, 1026-05, 1026-06, 1026-07, 1026-08, 1026-09, 1026-10, 1026-11, 1026-12, 1026-13, 1026-14, 1026-15, 1026-16, 1026-17, 1026-18, 1026-19, 1026-20, 1026-21, 1026-22 | 1609, 1610, 1611, 1612, 1613, 1614, 1615, 1616, 1617, 1618, 1619, 1620, 1621, 1622, 1623, 1624, 1625, 1626, 1627, 1628, 1629, 1630 | Developer | Lofty Building Group - Brenton
1027 | 1 |  |  |  |  | 1027-01 |  | Developer
1028 | 1 |  |  |  |  | 1028-01 |  | Developer
1029 | 1 |  |  |  |  | 1029-01 |  | Developer
1030 | 2 | Lot 12 Young Court, Murray Bridge |  | Young Court | Murray Bridge | 1030-01, 1030-02 | 1658, 1659 | Developer | Cornerstone Housing Paul Klose
1031 | 2 | Lot 21 Ellendale Road, Murray Bridge |  | Ellendale Road | Murray Bridge | 1031-01, 1031-02 | 1660, 1661 | Developer | Cornerstone Housing Paul Klose
1032 | 2 | Lot 52 Piper Court, Murray Bridge |  | Piper Court | Murray Bridge | 1032-01, 1032-02 | 1662, 1663 | Developer | Cornerstone Housing Paul Klose
1033 | 26 | 2 Luke Ave, Salisbury Downs (Res 1) | 2 | Luke Ave | Salisbury Downs | 1033-01, 1033-02, 1033-03, 1033-04, 1033-05, 1033-06, 1033-07, 1033-08, 1033-09, 1033-10, 1033-11, 1033-12, 1033-13, 1033-14, 1033-15, 1033-16, 1033-17, 1033-18, 1033-19, 1033-20, 1033-21, 1033-22, 1033-23, 1033-24, 1033-25, 1033-26 | 1674, 1675, 1676, 1677, 1678, 1679, 1680, 1681, 1682, 1683, 1684, 1685, 1686, 1687, 1688, 1689, 1690, 1691, 1692, 1693, 1694, 1695, 1696, 1697, 1698, 1699 | Developer | Lofty Building Group
1034 | 6 | 28 Guthrie Road, Christies Beach (Lot 1) | 28 | Guthrie Road | Christies Beach | 1034-01, 1034-02, 1034-03, 1034-04, 1034-05, 1034-06 | 1704, 1705, 1706, 1707, 1708, 1709 | Residential | Haume Group
1035 | 1 | 10 Mortimer Ave (formally 15 Mckinlay) Gawler East | 10 | Mortimer Ave (formally 15 Mckinlay) Gawler East |  | 1035-01 | 1719 | Residential | Kris Charles & David Bull
1036 | 2 | 8 Henderson St, Henley Beach | 8 | Henderson St | Henley Beach | 1036-01, 1036-02 | 1724, 1725 | Residential | Anthony Pizanias
1037 | 2 | 25 Stanlake Ave, St Marys | 25 | Stanlake Ave | St Marys | 1037-01, 1037-02 | 1730, 1731 | Residential | Parminder Singh
1038 | 5 | 23 Coronation Ave, Campbelltown RES 1 | 23 | Coronation Ave | Campbelltown | 1038-01, 1038-02, 1038-03, 1038-04, 1038-05 | 1763, 1764, 1765, 1766, 1767 | Developer | Calatrava 1839 pty Ltd (Gerard Wong)
1039 | 5 | 9 Alor Court, Noarlunga Downs Lot 1 | 9 | Alor Court | Noarlunga Downs | 1039-01, 1039-02, 1039-03, 1039-04, 1039-05 | 1752, 1753, 1754, 1755, 1756 | Residential | Li Dong (Astra Pacific Developments)
1040 | 4 | 25 Stratton Road, Elizabeth Downs Lot 2 | 25 | Stratton Road | Elizabeth Downs | 1040-01, 1040-02, 1040-03, 1040-04 | 1759, 1760, 1761, 1762 | Residential | Ben Scadden
1041 | 6 | 233 Hogarth Road, Elizabeth Grove Lot 1 | 233 | Hogarth Road | Elizabeth Grove | 1041-01, 1041-02, 1041-03, 1041-04, 1041-05, 1041-06 | 1768, 1769, 1770, 1771, 1772, 1773 | Residential | Li Dong ( Astra Pacific Projects)
1042 | 3 | res1 , 21 Edmund st Christie Downs | 21 | Edmund st | Christie Downs | 1042-01, 1042-02, 1042-03 | 1777, 1778, 1779 | Residential | Brenton Keogh
1043 | 3 | 3 Valiant Road, Port Willunga Lot 1 | 3 | Valiant Road | Port Willunga | 1043-01, 1043-02, 1043-03 | 1780, 1781, 1782 | Residential | Kelly & Adrian Borlace
1044 | 1 | 1 Chapman Street, Findon (single build) | 1 | Chapman Street | Findon (single build) | 1044-01 | 1783 | Residential | Vivian Sian
1045 | 3 | 31 Raggatt Cres, Mitchell Park Lot 1 | 31 | Raggatt Cres | Mitchell Park | 1045-01, 1045-02, 1045-03 | 1784, 1785, 1786 | Residential | Binod Poudel
1046 | 5 | 1 Fowlers Road, Glenunga Lot 1 | 1 | Fowlers Road | Glenunga | 1046-01, 1046-02, 1046-03, 1046-04, 1046-05 | 1787, 1788, 1789, 1790, 1791 | Developer | lofty building group
1047 | 3 | 13 Lowan Drive, Ingle Farm Lot 1 | 13 | Lowan Drive | Ingle Farm | 1047-01, 1047-02, 1047-03 | 1792, 1793, 1794 | Residential | Armando Tascione
1048 | 3 | 57 Martins Road, Salisbury Lot 1 | 57 | Martins Road | Salisbury | 1048-01, 1048-02, 1048-03 | 1798, 1799, 1800 | Developer | lofty building group
1049 | 5 | 2-4 Tweed Ave, Marion Lot 1 | 2-4 | Tweed Ave | Marion | 1049-01, 1049-02, 1049-03, 1049-04, 1049-05 | 1801, 1802, 1803, 1804, 1805 | Residential | Jarrad Hirst
1050 | 3 | 40 Alexander Cres, Christie Downs Lot 1 | 40 | Alexander Cres | Christie Downs | 1050-01, 1050-02, 1050-03 | 1825, 1826, 1827 | Residential | Brenton Keogh
1051 | 6 | 9 Grafton / 42 Austral Avenue, Morphettville | 9 | Grafton / 42 Austral Avenue | Morphettville | 1051-01, 1051-02, 1051-03, 1051-04, 1051-05, 1051-06 | 1828, 1829, 1830, 1831, 1832, 1833 | Developer | lofty building group
1052 | 3 | 20 Raggatt Cres, Mitchel Park | 20 | Raggatt Cres | Mitchel Park | 1052-01, 1052-02, 1052-03 | 1837, 1838, 1839 | Residential | Robert Mwole
1053 | 3 | 41 Maltarra Rd, Munno Para | 41 | Maltarra Rd | Munno Para | 1053-01, 1053-02, 1053-03 | 1840, 1841, 1842 | Residential | Samuel Weldemichial
1054 | 5 | 8 Kareela Rd, (AKA 21 Jessamine ave) Reynella Lot 1 | 8 | Kareela Rd | (AKA 21 Jessamine ave) Reynella | 1054-01, 1054-02, 1054-03, 1054-04, 1054-05 | 1846, 1847, 1848, 1849, 1850 | Developer | lofty building group
1055 | 3 | 49 Clifford St, Brooklyn Park RES 1 | 49 | Clifford St | Brooklyn Park | 1055-01, 1055-02, 1055-03 | 1851, 1852, 1853 | Developer | lofty building group
1056 | 5 | 12 Stewart Avenue, Aldinga Beach res 1 | 12 | Stewart Avenue | Aldinga Beach | 1056-01, 1056-02, 1056-03, 1056-04, 1056-05 | 1854, 1855, 1856, 1857, 1858 | Developer | lofty building group
1057 | 4 | 174 Ridley Rd, Elizabeth Grove Res 1 | 174 | Ridley Rd | Elizabeth Grove | 1057-01, 1057-02, 1057-03, 1057-04 | 1859, 1860, 1861, 1862 | Residential | Michael Weldemichial
1058 | 3 | 63 Woodlands Terrace, Edwardstown RES 1 | 63 | Woodlands Terrace | Edwardstown | 1058-01, 1058-02, 1058-03 | 1863, 1864, 1865 | Developer | lofty building group
1059 | 3 | 13 Opal Road Morphett Vale Res 1 | 13 | Opal Road | Morphett Vale | 1059-01, 1059-02, 1059-03 | 1866, 1867, 1868 | Developer | lofty building group
1060 | 4 | 567 Portrush Road, Glenunga Res 1 | 567 | Portrush Road | Glenunga | 1060-01, 1060-02, 1060-03, 1060-04 | 1869, 1870, 1871, 1872 | Residential | Kylie Herbert
1061 | 37 | 113 Liguria Cres, Noarlunga Downs 1 | 113 | Liguria Cres | Noarlunga Downs | 1061-01, 1061-02, 1061-03, 1061-04, 1061-05, 1061-06, 1061-07, 1061-08, 1061-09, 1061-10, 1061-11, 1061-12, 1061-13, 1061-14, 1061-15, 1061-16, 1061-17, 1061-18, 1061-19, 1061-20, 1061-21, 1061-22, 1061-23, 1061-24, 1061-25, 1061-26, 1061-27, 1061-28, 1061-29, 1061-30, 1061-31, 1061-32, 1061-33, 1061-34, 1061-35, 1061-36, 1061-37 | 1873, 1874, 1875, 1876, 1877, 1878, 1879, 1880, 1881, 1882, 1883, 1884, 1885, 1886, 1887, 1888, 1889, 1890, 1891, 1892, 1893, 1894, 1895, 1896, 1897, 1898, 1899, 1900, 1901, 1902, 1903, 1904, 1905, 1906, 1907, 1908, 1909 | Developer | lofty building group
1062 | 3 | 125 Glengyle Tce, Plympton | 125 | Glengyle Tce | Plympton | 1062-01, 1062-02, 1062-03 | 1920, 1929, 1931 | Developer | lofty building group
1063 | 9 | 1 Hamilton St / 6 Illford St, Vale Park Res 1 | 1 | Hamilton St / 6 Illford St | Vale Park | 1063-01, 1063-02, 1063-03, 1063-04, 1063-05, 1063-06, 1063-07, 1063-08, 1063-09 | 1912, 1913, 1914, 1915, 1916, 1917, 1918, 1919, 1920 | Developer | lofty building group
1064 | 3 | 7 Stagg Drive, Tranmere Res 1 | 7 | Stagg Drive | Tranmere | 1064-01, 1064-02, 1064-03 | 1921, 1922, 1923 | Residential | Adam Soininen
1065 | 5 | 82 Grundy Tce, Christies Beach Res 1 | 82 | Grundy Tce | Christies Beach | 1065-01, 1065-02, 1065-03, 1065-04, 1065-05 | 1924, 1925, 1926, 1927, 1928 | Developer | Lofty Building Group
1066 | 3 | 42-44 Hubbard St, Beverley Res 1 | 42-44 | Hubbard St | Beverley | 1066-01, 1066-02, 1066-03 | 1932, 1933, 1934 | Residential | Westside Housing
1067 | 3 | 26 Kenner St, Elizabeth Downs Res 1 | 26 | Kenner St | Elizabeth Downs | 1067-01, 1067-02, 1067-03 | 1935, 1936, 1937 | Residential | Westside Housing
1068 | 3 | 10 Carousel St, Para Vista Res 1 | 10 | Carousel St | Para Vista | 1068-01, 1068-02, 1068-03 | 1938, 1939, 1940 | Residential | Westside Housing
1069 | 3 | 43 Balcombe Ave, Findon Res 1 | 43 | Balcombe Ave | Findon | 1069-01, 1069-02, 1069-03 | 1941, 1942, 1943 | Developer | Lofty Building Group
1070 | 23 | Lot 20 Taylor Ave, Morphett Vale Res 1 | 20 | Taylor Ave | Morphett Vale | 1070-01, 1070-02, 1070-03, 1070-04, 1070-05, 1070-06, 1070-07, 1070-08, 1070-09, 1070-10, 1070-11, 1070-12, 1070-13, 1070-14, 1070-15, 1070-16, 1070-17, 1070-18, 1070-19, 1070-20, 1070-21, 1070-22, 1070-23 | 1944, 1945, 1946, 1947, 1948, 1949, 1950, 1951, 1952, 1953, 1954, 1955, 1956, 1957, 1958, 1959, 1960, 1961, 1962, 1963, 1964, 1965, 1966 | Developer | Lofty Building Group
1071 | 3 | 8 Dunedin Street, Dover Gardens Res | 8 | Dunedin Street | Dover Gardens | 1071-01, 1071-02, 1071-03 | 1967, 1968, 1969 | Developer | Lofty Building Group
1072 | 1 | 31A Baden Tce, O'sullivan Beach | 31 | A Baden Tce | O'sullivan Beach | 1072-01 | 1970 | Residential
1073 | 3 | 2 Mckeller Tce, Morphettville Res 1 | 2 | Mckeller Tce | Morphettville | 1073-01, 1073-02, 1073-03 | 1974, 1975, 1976 | Residential | Grant Walter
1074 | 3 | 4 Leeds Ave Hope Valley res 1 | 4 | Leeds Ave | Hope Valley | 1074-01, 1074-02, 1074-03 | 1977, 1978, 1979 | Residential | Westside Housing
1075 | 3 | 20 Grandview Grove Sturt res 1 | 20 | Grandview Grove Sturt |  | 1075-01, 1075-02, 1075-03 | 1980, 1981, 1982 | Residential | Westside Housing
1076 | 3 | 47 Ivey ST, Ottoway Res 1 | 47 | Ivey ST | Ottoway | 1076-01, 1076-02, 1076-03 | 1983, 1984, 1985 | Developer | Lofty Building Group
1077 | 49 | 51 Maryvale Rd, Athelstone Res 1 (Community) | 51 | Maryvale Rd | Athelstone | 1077-01, 1077-02, 1077-03, 1077-04, 1077-05, 1077-06, 1077-07, 1077-08, 1077-09, 1077-10, 1077-11, 1077-12, 1077-13, 1077-14, 1077-15, 1077-16, 1077-17, 1077-18, 1077-19, 1077-20, 1077-21, 1077-22, 1077-23, 1077-24, 1077-25, 1077-26, 1077-27, 1077-28, 1077-29, 1077-30, 1077-31, 1077-32, 1077-33, 1077-34, 1077-35, 1077-36, 1077-37, 1077-38, 1077-39, 1077-40, 1077-41, 1077-42, 1077-43, 1077-44, 1077-45, 1077-46, 1077-47, 1077-48, 1077-49 | 1991, 1992, 1993, 1994, 1995, 1996, 1997, 1998, 1999, 2000, 2001, 2002, 2003, 2004, 2005, 2006, 2007, 2008, 2009, 2010, 2011, 2012, 2013, 2014, 2015, 2016, 2017, 2018, 2019, 2020, 2021, 2022, 2023, 2024, 2025, 2026, 2027, 2028, 2029, 2030, 2031, 2032, 2033, 2034, 2035, 2036, 2037, 2038, 2039 | Developer | Lofty Building Group
1078 | 1 |  |  |  |  | 1078-01 | 2040 | Developer | Lofty Building Group
1079 | 7 | 90 Greentree BVD, Paralowie RES 1 | 90 | Greentree BVD | Paralowie | 1079-01, 1079-02, 1079-03, 1079-04, 1079-05, 1079-06, 1079-07 | 2041, 2042, 2043, 2044, 2045, 2046, 2047 | Developer | Lofty Building Group
1080 | 3 | 16 Egan Cres, Mitchell Park Res 1 | 16 | Egan Cres | Mitchell Park | 1080-01, 1080-02, 1080-03 | 2048, 2049, 2050 | Developer | Lofty Building Group
1081 | 3 | 25 Ayre St, South Plympton Res 1 | 25 | Ayre St | South Plympton | 1081-01, 1081-02, 1081-03 | 2051, 2052, 2053 | Developer | Lofty Building Group
1082 | 5 | 17 Lewis Rd, Payneham Res 1 | 17 | Lewis Rd | Payneham | 1082-01, 1082-02, 1082-03, 1082-04, 1082-05 | 2054, 2055, 2056, 2057, 2058 | Developer | Lofty Building Group
1083 | 1 | 16 Jenny Ave Dernancourt | 16 | Jenny Ave Dernancourt |  | 1083-01 | 2059 | Residential
1084 | 3 | 15 Peachy Rd, Davoren Park | 15 | Peachy Rd | Davoren Park | 1084-01, 1084-02, 1084-03 | 2061, 2062, 2063 | Developer | Lofty Building Group
1085 | 6 | 593 Portrush Road & 16 Taminga Ave, Glenunga res 1 | 593 | Portrush Road & 16 Taminga Ave | Glenunga | 1085-01, 1085-02, 1085-03, 1085-04, 1085-05, 1085-06 | 2065, 2066, 2067, 2068, 2069, 2070 | Developer | Lofty Building Group
1086 | 4 | 41 Alexander Ave, Morphett Vale Res 1 | 41 | Alexander Ave | Morphett Vale | 1086-01, 1086-02, 1086-03, 1086-04 | 2071, 2072, 2073, 2074 | Developer | Lofty Building Group
1087 | 3 | 33 Pudney St, Seaton Res 1 | 33 | Pudney St | Seaton | 1087-01, 1087-02, 1087-03 | 2075, 2076, 2077 | Developer | Lofty Building Group
1088 | 4 | 50 Bluehills RD, O'Halloran Hill Res 1 | 50 | Bluehills RD | O'Halloran Hill | 1088-01, 1088-02, 1088-03, 1088-04 | 2078, 2079, 2080, 2081 | Developer | Lofty Building Group
1089 | 1 | 36 Bayview Rd, Gulfview Heights | 36 | Bayview Rd | Gulfview Heights | 1089-01 | 2082 | Residential | Harry
1090 | 4 | 22 Jennifer Ave, Happy valley Res 1 | 22 | Jennifer Ave | Happy valley | 1090-01, 1090-02, 1090-03, 1090-04 | 2083, 2106, 2107, 2108
1091 | 16 | 337 & 339 Montacute Rd, Athelstone Res 1 | 337&339 | Montacute Rd | Athelstone | 1091-01, 1091-02, 1091-03, 1091-04, 1091-05, 1091-06, 1091-07, 1091-08, 1091-09, 1091-10, 1091-11, 1091-12, 1091-13, 1091-14, 1091-15, 1091-16 | 2084, 2085, 2086, 2087, 2088, 2089, 2090, 2091, 2092, 2093, 2094, 2095, 2096, 2097, 2098, 2099 | Developer | Lofty Building Group
1092 | 6 | 7 Budapest Rd, Aberfoyle Park Res 1 | 7 | Budapest Rd | Aberfoyle Park | 1092-01, 1092-02, 1092-03, 1092-04, 1092-05, 1092-06 | 2100, 2101, 2102, 2103, 2104, 2105 |  | Haume
1093 | 5 | 2 Osmund Cres, Christie Downs Res 1 | 2 | Osmund Cres | Christie Downs | 1093-01, 1093-02, 1093-03, 1093-04, 1093-05 | 2109, 2110, 2111, 2112, 2113
1094 | 3 | 7 Tatiara Rd, Happy valley Res 1 | 7 | Tatiara Rd | Happy valley | 1094-01, 1094-02, 1094-03 | 2114, 2115, 2116
1095 | 1 | Lot 46, 3 Deans Road, Campbelltown | 3 | Deans Road | Campbelltown | 1095-01 | 2146
1096 | 29 | Lot 4999 Dowie Way, Munno Para Res 1 | 4999 | Dowie Way | Munno Para | 1096-01, 1096-02, 1096-03, 1096-04, 1096-05, 1096-06, 1096-07, 1096-08, 1096-09, 1096-10, 1096-11, 1096-12, 1096-13, 1096-14, 1096-15, 1096-16, 1096-17, 1096-18, 1096-19, 1096-20, 1096-21, 1096-22, 1096-23, 1096-24, 1096-25, 1096-26, 1096-27, 1096-28, 1096-29 | 2117, 2118, 2119, 2120, 2121, 2122, 2123, 2124, 2125, 2126, 2127, 2128, 2129, 2130, 2131, 2132, 2133, 2134, 2135, 2136, 2137, 2138, 2139, 2140, 2141, 2142, 2143, 2144, 2145
1097 | 4 | 60 & 62 Gordons St, Aldinga Beach Res 1 | 60&62 | Gordons St | Aldinga Beach | 1097-01, 1097-02, 1097-03, 1097-04 | 2147, 2148, 2149, 2150
1098 | 3 | 17 Nashwauk Cres Moana Res 1 | 17 | Nashwauk Cres Moana |  | 1098-01, 1098-02, 1098-03 | 2151, 2152, 2153
1099 | 6 | 7 Robinsons Rd, Old Noarlunga Res 1 | 7 | Robinsons Rd | Old Noarlunga | 1099-01, 1099-02, 1099-03, 1099-04, 1099-05, 1099-06 | 2154, 2155, 2156, 2157, 2158, 2159
1100 | 1 |  |  |  |  | 1100-01 | 2160
1101 | 150 | 13-15,17-19,21-23 Bremer Road, Murray Bridge Res 1 | 13-15 | 17-19, 21-23 Bremer Road | Murray Bridge | 1101-001, 1101-002, 1101-003, 1101-004, 1101-005, 1101-006, 1101-007, 1101-008, 1101-009, 1101-010, 1101-011, 1101-012, 1101-013, 1101-014, 1101-015, 1101-016, 1101-017, 1101-018, 1101-019, 1101-020, 1101-021, 1101-022, 1101-023, 1101-024, 1101-025, 1101-026, 1101-027, 1101-028, 1101-029, 1101-030, 1101-031, 1101-032, 1101-033, 1101-034, 1101-035, 1101-036, 1101-037, 1101-038, 1101-039, 1101-040, 1101-041, 1101-042, 1101-043, 1101-044, 1101-045, 1101-046, 1101-047, 1101-048, 1101-049, 1101-050, 1101-051, 1101-052, 1101-053, 1101-054, 1101-055, 1101-056, 1101-057, 1101-058, 1101-059, 1101-060, 1101-061, 1101-062, 1101-063, 1101-064, 1101-065, 1101-066, 1101-067, 1101-068, 1101-069, 1101-070, 1101-071, 1101-072, 1101-073, 1101-074, 1101-075, 1101-076, 1101-077, 1101-078, 1101-079, 1101-080, 1101-081, 1101-082, 1101-083, 1101-084, 1101-085, 1101-086, 1101-087, 1101-088, 1101-089, 1101-090, 1101-091, 1101-092, 1101-093, 1101-094, 1101-095, 1101-096, 1101-097, 1101-098, 1101-099, 1101-100, 1101-101, 1101-102, 1101-103, 1101-104, 1101-105, 1101-106, 1101-107, 1101-108, 1101-109, 1101-110, 1101-111, 1101-112, 1101-113, 1101-114, 1101-115, 1101-116, 1101-117, 1101-118, 1101-119, 1101-120, 1101-121, 1101-122, 1101-123, 1101-124, 1101-125, 1101-126, 1101-127, 1101-128, 1101-129, 1101-130, 1101-131, 1101-132, 1101-133, 1101-134, 1101-135, 1101-136, 1101-137, 1101-138, 1101-139, 1101-140, 1101-141, 1101-142, 1101-143, 1101-144, 1101-145, 1101-146, 1101-147, 1101-148, 1101-149, 1101-150 | 2161, 2162, 2163, 2164, 2165, 2166, 2167, 2168, 2169, 2170, 2171, 2172, 2173, 2174, 2175, 2176, 2177, 2178, 2179, 2180, 2181, 2182, 2183, 2184, 2185, 2186, 2187, 2188, 2189, 2190, 2191, 2192, 2193, 2194, 2195, 2196, 2197, 2198, 2199, 2200, 2201, 2202, 2203, 2204, 2205, 2206, 2207, 2208, 2209, 2210, 2211, 2212, 2213, 2214, 2215, 2216, 2217, 2218, 2219, 2220, 2221, 2222, 2223, 2224, 2225, 2226, 2227, 2228, 2229, 2230, 2231, 2232, 2233, 2234, 2235, 2236, 2237, 2238, 2239, 2240, 2241, 2242, 2243, 2244, 2245, 2246, 2247, 2248, 2249, 225, 2250, 2251, 2252, 2253, 2254, 2255, 2256, 2257, 2258, 2260, 2261, 2262, 2263, 2264, 2265, 2266, 2267, 2268, 2269, 2270, 2271, 2272, 2273, 2274, 2275, 2276, 2277, 2278, 2279, 2280, 2281, 2282, 2283, 2284, 2285, 2286, 2287, 2288, 2289, 2290, 2291, 2292, 2293, 2294, 2295, 2296, 2297, 2298, 2299, 2300, 2301, 2302, 2303, 2304, 2305, 2306, 2307, 2308, 2309, 2310
1102 | 3 | 25 Tiller Drive, Seaford res 1 | 25 | Tiller Drive | Seaford | 1102-01, 1102-02, 1102-03 | 2311, 2312, 2313
1103 | 3 | 247 Main South Road, Hackham West Res 1 | 247 | Main South Road | Hackham West | 1103-01, 1103-02, 1103-03 | 2314, 2315, 2316
1104 | 7 | 3 & 5 Wootton Street, Davoren Park Res 1 | 3&5 | Wootton Street | Davoren Park | 1104-01, 1104-02, 1104-03, 1104-04, 1104-05, 1104-06, 1104-07 | 2317, 2318, 2319, 2320, 2321, 2322, 2323
1105 | 3 | 48 Streeters Road, North Plympton Res 1 | 48 | Streeters Road | North Plympton | 1105-01, 1105-02, 1105-03 | 2324, 2325, 2326
1106 | 3 | 10 Friar Street, Enfield Res 1 | 10 | Friar Street | Enfield | 1106-01, 1106-02, 1106-03 | 2327, 2328, 2329
1107 | 4 | 10 Copernicus Road, Christies Beach | 10 | Copernicus Road | Christies Beach | 1107-01, 1107-02, 1107-03, 1107-04 | 2330, 2331, 2332, 2333
1108 | 4 | 3 Patella Street, Seaford rise | 3 | Patella Street | Seaford rise | 1108-01, 1108-02, 1108-03, 1108-04 | 2334, 2335, 2336, 2337
1109 | 3 | 21 Mirrimar Crescent, Reynella | 21 | Mirrimar Crescent | Reynella | 1109-01, 1109-02, 1109-03 | 2338, 2339, 2340
1110 | 3 | 10 Pope Cres, Hope Valley Res 1 | 10 | Pope Cres | Hope Valley | 1110-01, 1110-02, 1110-03 | 2341, 2342, 2343
1111 | 3 | 26 Davenport Terrace, Seacliff Park Res 1 | 26 | Davenport Terrace | Seacliff Park | 1111-01, 1111-02, 1111-03 | 2344, 2345, 2346
1112 | 3 | 3 Ross Street, Brighton Res 1 | 3 | Ross Street | Brighton | 1112-01, 1112-02, 1112-03 | 2347, 2348, 2349
1113 | 3 | 120 Clairville Road, Newton Res 1 | 120 | Clairville Road | Newton | 1113-01, 1113-02, 1113-03 | 2350, 2351, 2352
1114 | 3 | 8 Breckenridge Road, Reynella Res 1 | 8 | Breckenridge Road | Reynella | 1114-01, 1114-02, 1114-03 | 2353, 2354, 2355
1115 | 3 | 24 Homington Road, Elizabeth North Res 1 | 24 | Homington Road | Elizabeth North | 1115-01, 1115-02, 1115-03 | 2356, 2357, 2358
1116 | 3 | 24 Brodie Road, Reynella Res 1 | 24 | Brodie Road | Reynella | 1116-01, 1116-02, 1116-03 | 2359, 2360, 2361
1117 | 30 | 83A Awoonga Road, Hope Valley Res 1 | 83 | A Awoonga Road | Hope Valley | 1117-01, 1117-02, 1117-03, 1117-04, 1117-05, 1117-06, 1117-07, 1117-08, 1117-09, 1117-10, 1117-11, 1117-12, 1117-13, 1117-14, 1117-15, 1117-16, 1117-17, 1117-18, 1117-19, 1117-20, 1117-21, 1117-22, 1117-23, 1117-24, 1117-25, 1117-26, 1117-27, 1117-28, 1117-29, 1117-30 | 2362, 2363, 2364, 2365, 2366, 2367, 2368, 2369, 2370, 2371, 2372, 2373, 2374, 2375, 2376, 2377, 2378, 2379, 2380, 2381, 2382, 2383, 2384, 2385, 2386, 2387, 2388, 2389, 2390, 2391
1118 | 3 | 9 Riders Street, Seacombe Gardens Res 1 | 9 | Riders Street | Seacombe Gardens | 1118-01, 1118-02, 1118-03 | 2392, 2393, 2394
1119 | 4 | 27 Howard Street, Windsor Gardens Res 1 | 27 | Howard Street | Windsor Gardens | 1119-01, 1119-02, 1119-03, 1119-04 | 2395, 2396, 2397, 2398
1120 | 3 | 14 Brodie Road, Reynella Res 1 | 14 | Brodie Road | Reynella | 1120-01, 1120-02, 1120-03 | 2399, 2400, 2401
1121 | 3 | 2A Launceston Ave, Warradale Res 1 | 2 | A Launceston Ave | Warradale | 1121-01, 1121-02, 1121-03 | 2402, 2403, 2404

## Review
Flag | Source row (CERTIFICATION) | Project Number | Job Number | Site Address | What to check
Blank site address | 149 | 1027 | 1027-01 | (blank) | No address in the source, so this row could not be matched to any other job. It has been given its own project number. Fix the address in CERTIFICATION and re-run to merge it.
Blank site address | 150 | 1028 | 1028-01 | (blank) | No address in the source, so this row could not be matched to any other job. It has been given its own project number. Fix the address in CERTIFICATION and re-run to merge it.
Blank site address | 151 | 1029 | 1029-01 | (blank) | No address in the source, so this row could not be matched to any other job. It has been given its own project number. Fix the address in CERTIFICATION and re-run to merge it.
Blank site address | 440 | 1078 | 1078-01 | (blank) | No address in the source, so this row could not be matched to any other job. It has been given its own project number. Fix the address in CERTIFICATION and re-run to merge it.
Blank site address | 558 | 1100 | 1100-01 | (blank) | No address in the source, so this row could not be matched to any other job. It has been given its own project number. Fix the address in CERTIFICATION and re-run to merge it.
Grouped on a descriptor, not a lot |  | 1007 | 1007-13 | #13 Hunt Crescent, Christies Beach (CA) | Same address as the other jobs in this project, but the job is identified by a descriptor (Single/Double Storey, CA, Community, Torrens) rather than a lot or res number. Confirm it belongs in this project.
Grouped on a descriptor, not a lot |  | 1019 | 1019-01 | 3 Cannes Avenue, Grange - Single Storey | Same address as the other jobs in this project, but the job is identified by a descriptor (Single/Double Storey, CA, Community, Torrens) rather than a lot or res number. Confirm it belongs in this project.
Grouped on a descriptor, not a lot |  | 1019 | 1019-02 | 3 Cannes Avenue, Grange - Double Storey | Same address as the other jobs in this project, but the job is identified by a descriptor (Single/Double Storey, CA, Community, Torrens) rather than a lot or res number. Confirm it belongs in this project.
Possible duplicate address |  | 1020 vs 1079 | 1020-01 / 1079-01 | 84 -88 Greentree Blvd Paralowie - Lot 10 ¦¦ 90 Greentree BVD, Paralowie RES 1 | These two addresses are 90% similar but were kept as separate projects because the street numbers differ. Confirm they are genuinely different sites.
Possible duplicate address |  | 1045 vs 1052 | 1045-01 / 1052-01 | 31 Raggatt Cres, Mitchell Park Lot 1 ¦¦ 20 Raggatt Cres, Mitchel Park | These two addresses are 92% similar but were kept as separate projects because the street numbers differ. Confirm they are genuinely different sites.
Possible duplicate address |  | 1045 vs 1080 | 1045-01 / 1080-01 | 31 Raggatt Cres, Mitchell Park Lot 1 ¦¦ 16 Egan Cres, Mitchell Park Res 1 | These two addresses are 86% similar but were kept as separate projects because the street numbers differ. Confirm they are genuinely different sites.
Possible duplicate address |  | 1116 vs 1120 | 1116-01 / 1120-01 | 24 Brodie Road, Reynella Res 1 ¦¦ 14 Brodie Road, Reynella Res 1 | These two addresses are 96% similar but were kept as separate projects because the street numbers differ. Confirm they are genuinely different sites.

## Method
How this workbook was built
Source | CERTIFICATION tab of test_import.xlsx, 801 data rows
Layout | Columns 1 to 191 match test_import.csv exactly, same order and headers. Columns 192 to 194 are extra CERTIFICATION columns kept so nothing is lost.
Grouping rule | Jobs share a project when they sit at the same site address and differ only by lot or residence.
Address normalising | Before comparing, the following are stripped: (Lot n), Lot n, (Res n), Res n, a bare trailing dwelling number, (CA), (Community), (Torrens), Single/Double Storey, SA, and postcodes. Case, punctuation and extra spaces are ignored. Street type abbreviations are expanded (Rd/Road, Ave/Avenue, Tce/Terrace, Blvd and Bvd/Boulevard, Cres/Crescent, Dr/Drive, Ct/Court, Pde/Parade, Pl/Place, Gr/Grove, Hwy/Highway, Ln/Lane, Sq/Square, St/Street).
Typo matching | Two addresses also group when they are 90% or more similar AND their street numbers match exactly. Requiring the street number to match prevents 13 Opal Road merging with 17 Opal Road. After normalising, no extra pairs met this test, so no fuzzy merges were applied. Near misses between 85% and 100% are listed on the Review tab instead of being merged.
Project Number | Starts at 1001 and increases in the order projects first appear in the CERTIFICATION tab.
Job Sequence | 01, 02, 03 within a project, in CERTIFICATION row order. Held as text so the leading zero is kept.
Job Number | Project Number, hyphen, Job Sequence. For example 1004-02.
Old Job Number | The Job Number as it appears in CERTIFICATION, unchanged.
Address split | Street Number, Street and Suburb are parsed from Site Address. Where an address has no comma, the suburb is recognised against the list of suburbs found elsewhere in the sheet.
City column | Matches your template: this column carries the lot or residence identifier, not a city. Say the word and it can be renamed Lot / Res.
Extra columns | Three CERTIFICATION columns have no place in your CSV template: the unnamed column K (between Notes and CMA), Estimator, and Link. Rather than lose them they are appended after the 191 template columns, headed in gold. Delete columns GJ to GL before importing if your import expects exactly 191 columns.
Hidden columns | CERTIFICATION hides 104 of its columns in Excel. Every one of them is included here, values intact. Hiding affects the view only, never the data.
Hidden and filtered rows | Checked directly in the file: CERTIFICATION has no hidden rows and no saved filter. All 801 populated rows are present. The other tabs (project import, Sheet1, Sheet2, Sheet3) hold stage lookups and your nine sample template rows, not job records.
Not verified | No data was altered, invented or corrected. Everything outside the four new key columns and the address split is copied straight from CERTIFICATION.