## Lifecycle Stages
Stage ID | Stage Name | Order | Notes
LCStage_AD | Aquistion & Development | 1
LCstage_PreCon | Pre-Constructions | 2
LCStage_Con | Construction | 3
LCStage_Maint | Maintenance | 4
LCstage_Complete | Completed | 5
LCStage_Closed | Closed | 6
LCStage_Cancelled | Cancelled | 7

## Properties
# | Lifecycle Stage | Stage | Process block |  | Property | Type | job or project | Department (process map) | SLA sheet (days) | Predecessors | Successors
1 | Aquisition and Development | Aquisition and Development | New Project | New Project Agreement type | Agreement type | Enum | Job | Acquisition & Development, Design
13 | Aquisition and Development | Aquisition and Development | New Project | New Project Sales Consultant | Sales Consultant | User | Project | Acquisition & Development, Design
14 | Aquisition and Development | Aquisition and Development | New Job | New Job Site Supervisor | Site Supervisor | User | Project | Acquisition & Development, Design
15 | Aquisition and Development | Aquisition and Development | New Job | New Job Estimator | Estimator | User | Project | Acquisition & Development, Design
16 | Aquisition and Development | Aquisition and Development | New Job | New Job Link | Link | URL | Job | Acquisition & Development, Design
18 | Aquisition and Development | Aquisition and Development | New Job | New Job Number of Single Stories Dwellings | Number of Single Stories Dwellings | number | Project | Acquisition & Development, Design
19 | Aquisition and Development | Aquisition and Development | New Job | New Job Number of Double Stories Dwellings | Number of Double Stories Dwellings | number | Project | Acquisition & Development, Design
20 | Aquisition and Development | Aquisition and Development | New Project | New Project Number of Total Dwellings | Number of Total Dwellings | number | Project | Acquisition & Development, Design
21 | Pre-Constructions |  | PWA & Invoice | PWA & Invoice Contract Issued | Contract Issued | Date | Job | Acquisition & Development, Design | 3 |  | 3 Concept Plans; 5 Soil (Bore Logs); 4 Site Survey; 2 PWA Deposit
22 | Pre-Constructions |  | PWA & Invoice | PWA & Invoice Contract Signed | Contract Signed | Date | Job | Acquisition & Development, Design
23 | Pre-Constructions | Stage 1 | PWA & Invoice | PWA & Invoice Deposit 1 Paid | Deposit 1 Paid | Date | Job | Acquisition & Development, Design | 7
24 | Pre-Constructions | Stage 1 | PWA & Invoice | PWA & Invoice $ Amount Paid | $ Amount Paid | text | Job | Acquisition & Development, Design
25 | Pre-Constructions | Stage 1 | (1 Day) | (1 Day) Sales Documents (Incl. Site Inspection) Complete | Sales Documents (Incl. Site Inspection) Complete | yes/no | Job | Acquisition & Development, Design
26 | Pre-Constructions | Stage 1 | Added to Trello | Added to Trello Trello | Trello | yes/no | Job | Acquisition & Development, Design | 7
27 | Pre-Constructions | Stage 1 | Concept Plan | Concept Plan Ordered | Ordered | date | Project | Acquisition & Development, Design | 7 | 1 PWA Issued; 2 PWA Deposit | 14 Prelim FCR Ordered; 12 Civil Plan Ordered; 6 Planning Drawings Ordered; 7 Planning Drawings Completed
28 | Pre-Constructions | Stage 1 | Concept Plan | Concept Plan Received | Received | date | Project | Acquisition & Development, Design | 7 | 1 PWA Issued; 2 PWA Deposit | 14 Prelim FCR Ordered; 12 Civil Plan Ordered; 6 Planning Drawings Ordered; 7 Planning Drawings Completed
29 | Pre-Constructions | Stage 1 | Concept Plan | Concept Plan Amendment Ordered | Amendment Ordered | date | Project | Acquisition & Development | 7 | 1 PWA Issued; 2 PWA Deposit | 14 Prelim FCR Ordered; 12 Civil Plan Ordered; 6 Planning Drawings Ordered; 7 Planning Drawings Completed
30 | Pre-Constructions | Stage 1 | Concept Plan | Concept Plan Amendment Received | Amendment Received | date | Project |  | 7 | 1 PWA Issued; 2 PWA Deposit | 14 Prelim FCR Ordered; 12 Civil Plan Ordered; 6 Planning Drawings Ordered; 7 Planning Drawings Completed
31 | Pre-Constructions | Stage 1 | Concept Plan | Concept Plan Signed Off (7 Days) | Signed Off (7 Days) | date | Project | Acquisition & Development | 7 | 1 PWA Issued; 2 PWA Deposit | 14 Prelim FCR Ordered; 12 Civil Plan Ordered; 6 Planning Drawings Ordered; 7 Planning Drawings Completed
32 | Pre-Constructions | Stage 1 | Site Survey | Site Survey Ordered | Ordered | date | Project |  | 7 | 2 PWA Deposit; 1 PWA Issued | 7 Planning Drawings Completed
33 | Pre-Constructions | Stage 1 | Site Survey | Site Survey Received | Received | date | Project |  | 14 | 2 PWA Deposit; 1 PWA Issued | 7 Planning Drawings Completed
34 | Pre-Constructions | Stage 1 | Soil - Bore Logs | Soil - Bore Logs Ordered | Ordered | date | Project |  | 10 | 2 PWA Deposit; 1 PWA Issued
35 | Pre-Constructions | Stage 1 | Soil - Bore Logs | Soil - Bore Logs Received (14 Days) | Received (14 Days) | date | Project |  | 14 | 2 PWA Deposit; 1 PWA Issued
36 | Pre-Constructions | Stage 1 | Planning Drawings | Planning Drawings Ordered | Ordered | date | Project |  | 1 | 3 Concept Plans
37 | Pre-Constructions | Stage 1 | Planning Drawings | Planning Drawings Received | Received | date | Project | Acquisition & Development, Design | 7 | 4 Site Survey; 3 Concept Plans | 15 Planning Approval; 8 Quote Steel Framing; 9 Prelim EER
38 | Pre-Constructions | Stage 1 | Planning Drawings | Planning Drawings Amendment Ordered | Amendment Ordered | date | Project |  | 1 | 3 Concept Plans
39 | Pre-Constructions | Stage 1 | Planning Drawings | Planning Drawings Amendment Received | Amendment Received | date | Project |  | 1 | 3 Concept Plans
40 | Pre-Constructions | Stage 1 | Planning Drawings | Planning Drawings Signed off (14 Days) | Signed off (14 Days) | date | Project | Acquisition & Development | 14 | 3 Concept Plans
41 | Pre-Constructions | Stage 1 | Prelim EER | Prelim EER Ordered | Ordered | date | Job |  | 14 | 3 Concept Plans
42 | Pre-Constructions | Stage 1 | Prelim EER | Prelim EER Received (2 Days) | Received (2 Days) | date | Job | Acquisition & Development | 2 | 9 Prelim EER
43 | Pre-Constructions | Stage 1 | Prelim EER | Prelim EER Confirm EER option with Scheduling | Confirm EER option with Scheduling | date | Job |  | 2 | 7 Planning Drawings Completed | 17 Contract Check; 11 Prelim EER Pricing; 10 Prelim EER Review
44 | Pre-Constructions | Stage 1 | Prelim EER | Prelim EER Log on Sales Estimating Trello | Log on Sales Estimating Trello | date | Job |  | 2 | 7 Planning Drawings Completed | 17 Contract Check; 11 Prelim EER Pricing; 10 Prelim EER Review
45 | Pre-Constructions | Stage 1 | Prelim EER | Prelim EER Confirm EER Option with Scheduling | Confirm EER Option with Scheduling | date | Job |  | 2 | 7 Planning Drawings Completed | 17 Contract Check; 11 Prelim EER Pricing; 10 Prelim EER Review
46 | Pre-Constructions | Stage 1 | Prelim EER | Prelim EER Received back from Estimating | Received back from Estimating | date | Job | Acquisition & Development, Estimating | 2 | 7 Planning Drawings Completed | 17 Contract Check; 11 Prelim EER Pricing; 10 Prelim EER Review
47 | Pre-Constructions | Stage 1 | Civil Plan | Civil Plan Ordered | Ordered | date | Project |  | 10 | 3 Concept Plans | 13 Civil Plan Checked & Received
48 | Pre-Constructions | Stage 1 | Civil Plan | Civil Plan Received (10 Days) | Received (10 Days) | date | Project | Acquisition & Development | 10 | 12 Civil Plan Ordered | 15 Planning Approval; 42 Fencing/Retaining Checks
49 | Pre-Constructions | Stage 1 | Civil Plan | Civil Plan Gavin Check Ordered | Gavin Check Ordered | text | Project
50 | Pre-Constructions | Stage 1 | Civil Plan | Civil Plan Gavin Check Returned (2 Days) | Gavin Check Returned (2 Days) | text | Project |  | 2
51 | Pre-Constructions | Stage 1 | Civil Plan | Civil Plan Amended Ordered | Amended Ordered | date | Project |  | 10 | 3 Concept Plans | 13 Civil Plan Checked & Received
52 | Pre-Constructions | Stage 1 | Civil Plan | Civil Plan Amended Received (10 Days) | Amended Received (10 Days) | date | Project |  | 10 | 12 Civil Plan Ordered | 15 Planning Approval; 42 Fencing/Retaining Checks
53 | Pre-Constructions | Stage 1 | Prelim Footings | Prelim Footings Ordered | Ordered | date | Job
54 | Pre-Constructions | Stage 1 | Prelim Footings | Prelim Footings Received (2 Days) | Received (2 Days) | date | Job |  | 2
55 | Pre-Constructions | Stage 1 | Lodged for Planning Approval | Lodged for Planning Approval Lodged | Lodged | date | Project |  | 21 | 7 Planning Drawings Completed; 13 Civil Plan Checked & Received | 20 Working Drawings Ordered; 16 Final Quote Check; 34 Selections Commence Schemes; 42 Fencing/Retaining Checks
56 | Pre-Constructions | Stage 1 | Lodged for Planning Approval | Lodged for Planning Approval Approved (28 Days) | Approved (28 Days) | date | Project |  | 28 | 7 Planning Drawings Completed; 13 Civil Plan Checked & Received | 20 Working Drawings Ordered; 16 Final Quote Check; 34 Selections Commence Schemes; 42 Fencing/Retaining Checks
57 | Pre-Constructions | Stage 1 | Lodged for Planning Approval | Lodged for Planning Approval RFI Received | RFI Received | date | Project |  | 21 | 7 Planning Drawings Completed; 13 Civil Plan Checked & Received | 20 Working Drawings Ordered; 16 Final Quote Check; 34 Selections Commence Schemes; 42 Fencing/Retaining Checks
58 | Pre-Constructions | Stage 1 | Lodged for Planning Approval | Lodged for Planning Approval RFI Responded (14 Days) | RFI Responded (14 Days) | date | Project |  | 14 | 7 Planning Drawings Completed; 13 Civil Plan Checked & Received | 20 Working Drawings Ordered; 16 Final Quote Check; 34 Selections Commence Schemes; 42 Fencing/Retaining Checks
59 | Pre-Constructions | Stage 1 | Final Quote Check | Final Quote Check Issued to Estimator | Issued to Estimator | date | Job |  | 10 | 15 Planning Approval | 17 Contract Check
60 | Pre-Constructions | Stage 1 | Final Quote Check | Final Quote Check Sent to S/C | Sent to S/C | date | Job |  | 10 | 15 Planning Approval | 17 Contract Check
61 | Pre-Constructions | Stage 1 | Final Quote Check | Final Quote Check Contract Sent to Ryan | Contract Sent to Ryan | date | Job |  | 10 | 15 Planning Approval | 17 Contract Check
62 | Pre-Constructions | Stage 1 | Final Quote Check | Final Quote Check Contract Approved by Ryan | Contract Approved by Ryan | date | Job |  | 10 | 15 Planning Approval | 17 Contract Check
63 | Pre-Constructions | Stage 1 | Contracts/Send Finalised Quote | Contracts/Send Finalised Quote Issued | Issued | date | Job |  | 3 |  | 3 Concept Plans; 5 Soil (Bore Logs); 4 Site Survey; 2 PWA Deposit
64 | Pre-Constructions | Stage 1 | Contracts/Send Finalised Quote | Contracts/Send Finalised Quote Received (7 Days) | Received (7 Days) | date | Job |  | 7
65 | Pre-Constructions | Stage 1 | Contracts/Send Finalised Quote | Contracts/Send Finalised Quote Sale Contact Client to Confirm No more Changes | Sale Contact Client to Confirm No more Changes | unknown (no data) | Job
66 | Pre-Constructions | Stage 1 | 2nd Deposit - contract deposit | 2nd Deposit - contract deposit Issued | Issued | date | Job |  | 3 |  | 3 Concept Plans; 5 Soil (Bore Logs); 4 Site Survey; 2 PWA Deposit
67 | Pre-Constructions | Stage 1 | 2nd Deposit - contract deposit | 2nd Deposit - contract deposit Received (7 Days) | Received (7 Days) | yes/no | Job | Finance | 7
68 | Pre-Constructions | Stage 1 | Contract value | Contract value Contract Value $ | Contract Value $ | currency | Job
69 | Pre-Constructions | Stage 1 | Stage gate | Stage gate Stage 1 Complete | Stage 1 Complete | yes/no | Job
70 | Pre-Constructions | Stage 2 | DNF Conditions Check | DNF Conditions Check Completed | Completed | date | Job
71 | Pre-Constructions | Stage 2 | Working Drawings | Working Drawings Ordered | Ordered | date | Job | Acquisition & Development, Design | 14 | 15 Planning Approval; 19 Contract Deposit Paid | 21 Working Drawings Completed & Checked
72 | Pre-Constructions | Stage 2 | Working Drawings | Working Drawings Received (14 Days) | Received (14 Days) | date | Job |  | 14 | 21 Working Drawings Completed & Checked | 31 Framing Drawings and Layouts; 24 Final EER Ordered; 27 Final FCR Ordered; 32 Framing Supporting Docs (windows , windspeed); 40 1st Site Inspection; 26 Lightweight Verandah Engineering; 50 BRC/KBS Lodged; 47 Production Estimate (CPC)
73 | Pre-Constructions | Stage 2 | Working Drawings | Working Drawings Plan Check complete | Plan Check complete | date | Job |  | 3 | 21 Working Drawings Completed & Checked | 31 Framing Drawings and Layouts; 24 Final EER Ordered; 27 Final FCR Ordered; 32 Framing Supporting Docs (windows , windspeed); 40 1st Site Inspection; 26 Lightweight Verandah Engineering; 50 BRC/KBS Lodged; 47 Production Estimate (CPC)
74 | Pre-Constructions | Stage 2 | Working Drawings | Working Drawings Logged for Amends | Logged for Amends | unknown (no data) | Job |  | 3 | 21 Working Drawings Completed & Checked | 31 Framing Drawings and Layouts; 24 Final EER Ordered; 27 Final FCR Ordered; 32 Framing Supporting Docs (windows , windspeed); 40 1st Site Inspection; 26 Lightweight Verandah Engineering; 50 BRC/KBS Lodged; 47 Production Estimate (CPC)
75 | Pre-Constructions | Stage 2 | Working Drawings | Working Drawings Amends received | Amends received | unknown (no data) | Job |  | 3 | 21 Working Drawings Completed & Checked | 31 Framing Drawings and Layouts; 24 Final EER Ordered; 27 Final FCR Ordered; 32 Framing Supporting Docs (windows , windspeed); 40 1st Site Inspection; 26 Lightweight Verandah Engineering; 50 BRC/KBS Lodged; 47 Production Estimate (CPC)
76 | Pre-Constructions | Stage 2 | Working Drawings | Working Drawings Amended Plans Checked | Amended Plans Checked | unknown (no data) | Job |  | 3 | 21 Working Drawings Completed & Checked | 31 Framing Drawings and Layouts; 24 Final EER Ordered; 27 Final FCR Ordered; 32 Framing Supporting Docs (windows , windspeed); 40 1st Site Inspection; 26 Lightweight Verandah Engineering; 50 BRC/KBS Lodged; 47 Production Estimate (CPC)
77 | Pre-Constructions | Stage 2 | Working Drawings | Working Drawings Finalised and signed (10 Days) | Finalised and signed (10 Days) | unknown (no data) | Job |  | 10 | 21 Working Drawings Completed & Checked | 31 Framing Drawings and Layouts; 24 Final EER Ordered; 27 Final FCR Ordered; 32 Framing Supporting Docs (windows , windspeed); 40 1st Site Inspection; 26 Lightweight Verandah Engineering; 50 BRC/KBS Lodged; 47 Production Estimate (CPC)
78 | Pre-Constructions | Stage 2 | Pegging Plan/Encroachment Plan | Pegging Plan/Encroachment Plan Ordered | Ordered | unknown (no data) | Project
79 | Pre-Constructions | Stage 2 | Pegging Plan/Encroachment Plan | Pegging Plan/Encroachment Plan Received (7 Days) | Received (7 Days) | unknown (no data) | Project | Acquisition & Development | 7
80 | Pre-Constructions | Stage 2 | Finalised EER | Finalised EER Ordered | Ordered | date | Job | Acquisition & Development | 5 | 19 Contract Deposit Paid; 22 Working Drawings Signed | 25 Final EER Checked; 50 BRC/KBS Lodged
81 | Pre-Constructions | Stage 2 | Finalised EER | Finalised EER Received (7 Days) | Received (7 Days) | date | Job | Scheduling | 7
82 | Pre-Constructions | Stage 2 | Finalised EER | Finalised EER Sent to Scheduling | Sent to Scheduling | unknown (no data) | Job | Scheduling
83 | Pre-Constructions | Stage 2 | Finalised EER | Finalised EER Received back from Scheduling (1 Day) | Received back from Scheduling (1 Day) | unknown (no data) | Job | Acquisition & Development | 1
84 | Pre-Constructions | Stage 2 | Stage gate | Stage gate Stage 2 Complete | Stage 2 Complete | yes/no | Job
85 | Pre-Constructions | Stage 3 | Stage gate | Stage gate Added to Pre-construction Trello + Move to Stage 3 on LMWF | Added to Pre-construction Trello + Move to Stage 3 on LMWF | unknown (no data) | Job
86 | Pre-Constructions | Stage 3 | Attached lightweight Verandah Engineering | Attached lightweight Verandah Engineering Ordered | Ordered | unknown (no data) | Job |  | 14 | 19 Contract Deposit Paid; 22 Working Drawings Signed
87 | Pre-Constructions | Stage 3 | Attached lightweight Verandah Engineering | Attached lightweight Verandah Engineering Received (14 Days) | Received (14 Days) | unknown (no data) | Job | Finance | 14 | 19 Contract Deposit Paid; 22 Working Drawings Signed
88 | Pre-Constructions | Stage 3 | FCR | FCR Ordered | Ordered | date | Job |  | 14 | 19 Contract Deposit Paid; 22 Working Drawings Signed | 28 FCR Check
89 | Pre-Constructions | Stage 3 | FCR | FCR Received (14 Days) | Received (14 Days) | date | Job | Finance | 14
90 | Pre-Constructions | Stage 3 | FCR | FCR Amendment Ordered | Amendment Ordered | unknown (no data) | Job
91 | Pre-Constructions | Stage 3 | FCR | FCR Amendment Received | Amendment Received | unknown (no data) | Job
92 | Pre-Constructions | Stage 3 | FCR | FCR Sent to Gavin | Sent to Gavin | unknown (no data) | Job
93 | Pre-Constructions | Stage 3 | FCR | FCR Received back from Gavin (7 Days) | Received back from Gavin (7 Days) | unknown (no data) | Job |  | 7
94 | Pre-Constructions | Stage 3 | Electrical/NBN Undergrounds | Electrical/NBN Undergrounds Plan Ordered | Plan Ordered | unknown (no data) | Project |  | 10 | 3 Concept Plans | 13 Civil Plan Checked & Received
95 | Pre-Constructions | Stage 3 | Electrical/NBN Undergrounds | Electrical/NBN Undergrounds Plan Received (10 Days) | Plan Received (10 Days) | unknown (no data) | Project |  | 10 | 28 FCR Check
96 | Pre-Constructions | Stage 3 | Electrical/NBN Undergrounds | Electrical/NBN Undergrounds Permit Application Lodged to Council | Permit Application Lodged to Council | unknown (no data) | Project |  | 10 | 28 FCR Check
97 | Pre-Constructions | Stage 3 | Electrical/NBN Undergrounds | Electrical/NBN Undergrounds Permit received | Permit received | unknown (no data) | Project |  | 10 | 28 FCR Check
98 | Pre-Constructions | Stage 3 | Electrical/NBN Undergrounds | Electrical/NBN Undergrounds NBN layout sent to CMA's | NBN layout sent to CMA's | unknown (no data) | Project |  | 10 | 28 FCR Check
99 | Pre-Constructions | Stage 3 | Section 221 - Stormwater/Crossover Permits | Section 221 - Stormwater/Crossover Permits Ordered | Ordered | unknown (no data) | Project |  | 14 | 28 FCR Check
100 | Pre-Constructions | Stage 3 | Section 221 - Stormwater/Crossover Permits | Section 221 - Stormwater/Crossover Permits Received (14 Days) | Received (14 Days) | unknown (no data) | Project | Finance | 14 | 28 FCR Check
101 | Pre-Constructions | Stage 3 | Framing and Trusses | Framing and Trusses Timber Frame / Steel Frame | Timber Frame / Steel Frame | text | Job
102 | Pre-Constructions | Stage 3 | Framing and Trusses | Framing and Trusses Ordererd | Ordererd | unknown (no data) | Job
103 | Pre-Constructions | Stage 3 | Framing and Trusses | Framing and Trusses Received (21 Days) | Received (21 Days) | unknown (no data) | Job | Finance | 21
104 | Pre-Constructions | Stage 3 | Framing and Trusses | Framing and Trusses Amendment Ordered | Amendment Ordered | unknown (no data) | Job
105 | Pre-Constructions | Stage 3 | Framing and Trusses | Framing and Trusses Amendment Received | Amendment Received | unknown (no data) | Job
106 | Pre-Constructions | Stage 3 | Beam Design | Beam Design Ordered | Ordered | text | Job |  | 7 | 32 Framing Supporting Docs (windows , windspeed) | 50 BRC/KBS Lodged
107 | Pre-Constructions | Stage 3 | Beam Design | Beam Design Receieved (21 Days) | Receieved (21 Days) | yes/no | Job |  | 21 | 32 Framing Supporting Docs (windows , windspeed) | 50 BRC/KBS Lodged
108 | Pre-Constructions | Stage 3 | Beam Design | Beam Design Amendment Ordered | Amendment Ordered | yes/no | Job |  | 7 | 32 Framing Supporting Docs (windows , windspeed) | 50 BRC/KBS Lodged
109 | Pre-Constructions | Stage 3 | Beam Design | Beam Design Amendment Received | Amendment Received | yes/no | Job |  | 7 | 32 Framing Supporting Docs (windows , windspeed) | 50 BRC/KBS Lodged
110 | Pre-Constructions | Stage 3 | Construction/Timber/Beam Jordan Check | Construction/Timber/Beam Jordan Check Sent to Management | Sent to Management | yes/no | Job
111 | Pre-Constructions | Stage 3 | Construction/Timber/Beam Jordan Check | Construction/Timber/Beam Jordan Check Approved (7 Days) | Approved (7 Days) | yes/no | Job |  | 7
112 | Pre-Constructions | Stage 3 | Selections | Selections Selections Consultant | Selections Consultant | text | Job
113 | Pre-Constructions | Stage 3 | Selections | Selections Selection Type Scheme / Client | Selection Type Scheme / Client | text | Job
114 | Pre-Constructions | Stage 3 | Selections | Selections Email Request to selections to contact client | Email Request to selections to contact client | unknown (no data) | Job | Selections
115 | Pre-Constructions | Stage 3 | Selections | Selections Gallery Appointment Date (21 Days) | Gallery Appointment Date (21 Days) | unknown (no data) | Job |  | 21
116 | Pre-Constructions | Stage 3 | Selections | Selections Selection Variation signed | Selection Variation signed | unknown (no data) | Job
117 | Pre-Constructions | Stage 3 | Selections | Selections Selections booklet signed (10 Days) | Selections booklet signed (10 Days) | unknown (no data) | Job |  | 10 | 37 Estimating Check of Contract/Selections; 38 Selections Drafting Amendments | 47 Production Estimate (CPC)
118 | Pre-Constructions | Stage 3 | 1st Site Inspection | 1st Site Inspection Ordered | Ordered | unknown (no data) | Project |  | 10 | 23 Pegging Plan Received; 22 Working Drawings Signed; 19 Contract Deposit Paid | 41 1st Site Inspection Actioned
119 | Pre-Constructions | Stage 3 | 1st Site Inspection | 1st Site Inspection Back (14 Days) | Back (14 Days) | unknown (no data) | Project |  | 14 | 23 Pegging Plan Received; 22 Working Drawings Signed; 19 Contract Deposit Paid | 41 1st Site Inspection Actioned
120 | Pre-Constructions | Stage 3 | 1st Site Inspection | 1st Site Inspection Items Actioned (5 Days) | Items Actioned (5 Days) | unknown (no data) | Project |  | 5 | 40 1st Site Inspection
121 | Pre-Constructions | Stage 3 | Retaining, Fencing & BOB | Retaining, Fencing & BOB Retaining In Contract? | Retaining In Contract? | unknown (no data) | Project
122 | Pre-Constructions | Stage 3 | Retaining, Fencing & BOB | Retaining, Fencing & BOB Retaining Required Before Or During Build | Retaining Required Before Or During Build | unknown (no data) | Project
123 | Pre-Constructions | Stage 3 | Retaining, Fencing & BOB | Retaining, Fencing & BOB Fencing In Contract? | Fencing In Contract? | yes/no | Project
124 | Pre-Constructions | Stage 3 | Retaining, Fencing & BOB | Retaining, Fencing & BOB BOB Sent | BOB Sent | unknown (no data) | Project
125 | Pre-Constructions | Stage 3 | Retaining, Fencing & BOB | Retaining, Fencing & BOB BOB Signed + Contact Details (30 Days) | BOB Signed + Contact Details (30 Days) | unknown (no data) | Project |  | 30
126 | Pre-Constructions | Stage 3 | Retaining, Fencing & BOB | Retaining, Fencing & BOB Fencing Notices Issued to client | Fencing Notices Issued to client | unknown (no data) | Project |  | 7 | 42 Fencing/Retaining Checks
127 | Pre-Constructions | Stage 3 | Retaining, Fencing & BOB | Retaining, Fencing & BOB Fencing Sent Via Registered Mail | Fencing Sent Via Registered Mail | unknown (no data) | Project
128 | Pre-Constructions | Stage 3 | Retaining, Fencing & BOB | Retaining, Fencing & BOB Registered Mail Collected | Registered Mail Collected | unknown (no data) | Project
129 | Pre-Constructions | Stage 3 | Retaining, Fencing & BOB | Retaining, Fencing & BOB 30 day overdue letter | 30 day overdue letter | unknown (no data) | Project
130 | Pre-Constructions | Stage 3 | Retaining, Fencing & BOB | Retaining, Fencing & BOB Cross Notice Received / Notes | Cross Notice Received / Notes | unknown (no data) | Project
131 | Pre-Constructions | Stage 3 | Retaining, Fencing & BOB | Retaining, Fencing & BOB Cross notice responded to (7 Days) | Cross notice responded to (7 Days) | unknown (no data) | Project |  | 7
132 | Pre-Constructions | Stage 3 | Retaining, Fencing & BOB | Retaining, Fencing & BOB Fencing Notices Completed + Saved in folder (14 Days) | Fencing Notices Completed + Saved in folder (14 Days) | unknown (no data) | Project |  | 14
133 | Pre-Constructions | Stage 3 | SA Water | SA Water SA Water Docs proposed location Plan ordered | SA Water Docs proposed location Plan ordered | unknown (no data) | Project
134 | Pre-Constructions | Stage 3 | SA Water | SA Water Received (7 Days) | Received (7 Days) | unknown (no data) | Project | Finance | 7
135 | Pre-Constructions | Stage 3 | SA Water | SA Water Cross check SA Water Locations against Working Drawings | Cross check SA Water Locations against Working Drawings | unknown (no data) | Project
136 | Pre-Constructions | Stage 3 | SA Water | SA Water Invoice Received | Invoice Received | unknown (no data) | Project
137 | Pre-Constructions | Stage 3 | SA Water | SA Water Invoice paid (2 Days) | Invoice paid (2 Days) | unknown (no data) | Project |  | 2 | 45 SA Water Docs
138 | Pre-Constructions | Stage 3 | SA Water | SA Water Confirmation of SA Water Meters & Sewer Connection on Site | Confirmation of SA Water Meters & Sewer Connection on Site | unknown (no data) | Project
139 | Pre-Constructions | Stage 3 | Construction Price Check (CPC) Sheet requested | Construction Price Check (CPC) Sheet requested Log on trello | Log on trello | unknown (no data) | Job
140 | Pre-Constructions | Stage 3 | Construction Price Check (CPC) Sheet requested | Construction Price Check (CPC) Sheet requested received (14 Days) | received (14 Days) | unknown (no data) | Job | Finance | 14
141 | Pre-Constructions | Stage 3 | Construction Price Check (CPC) Sheet requested | Construction Price Check (CPC) Sheet requested sent to Gary | sent to Gary | unknown (no data) | Job
142 | Pre-Constructions | Stage 3 | Construction Price Check (CPC) Sheet requested | Construction Price Check (CPC) Sheet requested Gary communicate to client /meeting (3 Days) | Gary communicate to client /meeting (3 Days) | unknown (no data) | Job |  | 3
143 | Pre-Constructions | Stage 3 | Construction Price Check (CPC) Sheet requested | Construction Price Check (CPC) Sheet requested Variation issued? | Variation issued? | unknown (no data) | Job
144 | Pre-Constructions | Stage 3 | Construction Price Check (CPC) Sheet requested | Construction Price Check (CPC) Sheet requested Variation Signed / Approved (14 Days) | Variation Signed / Approved (14 Days) | unknown (no data) | Job |  | 14
145 | Pre-Constructions | Variation | Variation | Variation Check contract Vegetation Site Scrape | Check contract Vegetation Site Scrape | unknown (no data) | Project
146 | Pre-Constructions | Variation | Variation | Variation Required Yes/No | Required Yes/No | unknown (no data) | Job
147 | Pre-Constructions | Variation | Variation | Variation Issued | Issued | unknown (no data) | Job |  | 3 |  | 3 Concept Plans; 5 Soil (Bore Logs); 4 Site Survey; 2 PWA Deposit
148 | Pre-Constructions | Variation | Variation | Variation Received (5 Days) | Received (5 Days) | unknown (no data) | Job | Finance | 5
149 | Pre-Constructions | Variation | BRC/KBS | BRC/KBS Lodged | Lodged | unknown (no data) | Job |  | 21 | 31 Framing Drawings and Layouts; 24 Final EER Ordered; 22 Working Drawings Signed; 19 Contract Deposit Paid; 33 Beam Design | 52 Footing Quotes Release; 51 Development Approval; 56 Finance Approval; 53 Final Construction Check
150 | Pre-Constructions | Stage 3 | BRC/KBS | BRC/KBS Approved (28 Days) | Approved (28 Days) | unknown (no data) | Job |  | 28
151 | Pre-Constructions | Stage 3 | BRC/KBS | BRC/KBS RFI Received | RFI Received | unknown (no data) | Job | Acquisition & Development
152 | Pre-Constructions | Stage 3 | BRC/KBS | BRC/KBS RFI Responded (14 Days) | RFI Responded (14 Days) | unknown (no data) | Job | Acquisition & Development | 14
153 | Pre-Constructions | Stage 3 | CITB | CITB Paid (Admin - CC) | Paid (Admin - CC) | unknown (no data) | Job
154 | Pre-Constructions | Stage 3 | DA | DA DA Requested | DA Requested | yes/no | Project
155 | Pre-Constructions | Stage 3 | DA | DA DA Approved (7 Days) | DA Approved (7 Days) | unknown (no data) | Project |  | 7
156 | Pre-Constructions | Stage 3 | Final Site Inspection, confirmation of Services | Final Site Inspection, confirmation of Services Ordered | Ordered | unknown (no data) | Project
157 | Pre-Constructions | Stage 3 | Final Site Inspection, confirmation of Services | Final Site Inspection, confirmation of Services Back (7 Days) | Back (7 Days) | unknown (no data) | Project |  | 7
158 | Pre-Constructions | Stage 3 | Final Site Inspection, confirmation of Services | Final Site Inspection, confirmation of Services Actioned | Actioned | unknown (no data) | Project
159 | Pre-Constructions | Stage 3 | Finance | Finance Updated Progress Payment Schedule issued for VO's over $40K | Updated Progress Payment Schedule issued for VO's over $40K | unknown (no data) | Job
160 | Pre-Constructions | Stage 3 | Finance | Finance Total of Variations Incl. CPC | Total of Variations Incl. CPC | unknown (no data) | Job
161 | Pre-Constructions | Stage 3 | Finance | Finance Revised Progress Claim amount/Total Build Amount - Approved by Accounts | Revised Progress Claim amount/Total Build Amount - Approved by Accounts | unknown (no data) | Job
162 | Pre-Constructions | Stage 3 | Finance | Finance Loan Approval Requested | Loan Approval Requested | yes/no | Job
163 | Pre-Constructions | Stage 3 | Finance | Finance Loan Approval Received (14 Days) | Loan Approval Received (14 Days) | unknown (no data) | Job |  | 14
164 | Pre-Constructions | Stage 3 | Finance | Finance Further Proof of Finance | Further Proof of Finance | unknown (no data) | Job
165 | Pre-Constructions | Stage 3 | Finance | Finance Commencement Letter requested | Commencement Letter requested | unknown (no data) | Job
166 | Pre-Constructions | Stage 3 | Finance | Finance Commencement Letter received | Commencement Letter received | unknown (no data) | Job
167 | Pre-Constructions | Stage 3 | Finance | Finance Settlement on Land - Titles | Settlement on Land - Titles | unknown (no data) | Job
168 | Pre-Constructions | Stage 3 | HOW Insurance | HOW Insurance Discuss amount with Craig | Discuss amount with Craig | unknown (no data) | Job
169 | Pre-Constructions | Stage 3 | HOW Insurance | HOW Insurance Requested | Requested | yes/no | Job | Finance
170 | Pre-Constructions | Stage 3 | HOW Insurance | HOW Insurance Received | Received | yes/no | Job | Finance
171 | Pre-Constructions | Stage 3 | HOW Insurance | HOW Insurance Invoiced Paid | Invoiced Paid | yes/no | Job | Finance
172 | Pre-Constructions | Stage 3 | Released to Construction | Released to Construction Request Released to Construction Template CRAIG | Request Released to Construction Template CRAIG | yes/no | Job
173 | Pre-Constructions | Stage 3 | Released to Construction | Released to Construction Pre Release to Scheduling and PO's | Pre Release to Scheduling and PO's | yes/no | Job | Scheduling, Finance
174 | Pre-Constructions | Stage 3 | Released to Construction | Released to Construction released to construction (HOW Complete) | released to construction (HOW Complete) | yes/no | Job |  | 3 | 56 Finance Approval; 55 2nd Site Inspection Actioned; 53 Final Construction Check; 52 Footing Quotes Release; 51 Development Approval
175 | Cancelled | PWA Cancellation | PWA Cancellation | PWA Cancellation Letter Issued (also update col B to 'cancelling') | Letter Issued (also update col B to 'cancelling') | text | Job
176 | Cancelled | PWA Cancellation | PWA Cancellation | PWA Cancellation Signed Returned | Signed Returned | unknown (no data) | Job
177 | Cancelled | PWA Cancellation | PWA Cancellation | PWA Cancellation Followed Up (Unsigned) | Followed Up (Unsigned) | unknown (no data) | Job
178 | Cancelled | PWA Cancellation | PWA Cancellation | PWA Cancellation Advised Departments Job Closed | Advised Departments Job Closed | unknown (no data) | Job
179 | Cancelled | Contract Cancellation | Contract Cancellation | Contract Cancellation Refund Y/N | Refund Y/N | yes/no | Job
180 | Cancelled | Contract Cancellation | Contract Cancellation | Contract Cancellation Agreed Amount $ | Agreed Amount $ | yes/no | Job
181 | Cancelled | Contract Cancellation | Contract Cancellation | Contract Cancellation Release of Documents Y/N | Release of Documents Y/N | yes/no | Job
182 | Cancelled | Contract Cancellation | Contract Cancellation | Contract Cancellation Letter Issued | Letter Issued | date | Job
183 | Cancelled | Contract Cancellation | Contract Cancellation | Contract Cancellation Followed up Unsigned | Followed up Unsigned | unknown (no data) | Job
184 | Cancelled | Contract Cancellation | Contract Cancellation | Contract Cancellation Signed Returned | Signed Returned | unknown (no data) | Job
185 | Cancelled | Contract Cancellation | Contract Cancellation | Contract Cancellation Payment Made | Payment Made | unknown (no data) | Job
186 | Cancelled | Contract Cancellation | Contract Cancellation | Contract Cancellation Documents Released | Documents Released | unknown (no data) | Job
187 | Cancelled | Contract Cancellation | Contract Cancellation | Contract Cancellation Advised Departments Job Closed | Advised Departments Job Closed | unknown (no data) | Job
ID | Construction | Process | Task Name | Task Name Forecast Start | Forecast Start | Date |  | team | Days | Predecessors
1 | Construction | 1 - Footings | 1 - Footings | 1 - Footings FOOTINGS | FOOTINGS | Date | Job | Scheduling | 18
2 | Construction | 1 - Footings | 1 - Footings | 1 - Footings COMMENCE CONSTRUCTION | COMMENCE CONSTRUCTION | Date | Job | Construction Admin | 1 |  | 2003-04-05
3 | Construction | 1 - Footings | 1 - Footings | 1 - Footings Council Notification - Commence Construction | Council Notification - Commence Construction | Date | Job | Construction Admin | 1 | 2
4 | Construction | 1 - Footings | 1 - Footings | 1 - Footings TEMPORARY FENCE INSTALL | TEMPORARY FENCE INSTALL | Date | Job | Scheduling | 1 | 2 | 2026-08-06
5 | Construction | 1 - Footings | 1 - Footings | 1 - Footings SITE TOILET DELIVERY | SITE TOILET DELIVERY | Date | Job | Scheduling | 1 | 2 | 2026-06-08
6 | Construction | 1 - Footings | 1 - Footings | 1 - Footings RETAINING | RETAINING | Date | Job | Scheduling | 5 | 2026-05-04 | 2026-11-12
7 | Construction | 1 - Footings | 1 - Footings | 1 - Footings Council Notification - Steel Inspection | Council Notification - Steel Inspection | Date | Job | Construction Admin | 1 | 2026-10-08
8 | Construction | 1 - Footings | 1 - Footings | 1 - Footings SLAB POUR | SLAB POUR | Date | Job | Scheduling | 14 | 2026-04-05 | 11, 7, 10, 12, 13, 17, 9
9 | Construction | 1 - Footings | 1 - Footings | 1 - Footings Customer Notification - Footings Complete | Customer Notification - Footings Complete | Date | Job | Construction Admin | 1 | 8
10 | Construction | 1 - Footings | 1 - Footings | 1 - Footings Claim - Footings Stage - Completed | Claim - Footings Stage - Completed | Date | Job | Construction Admin | 0 | 8
11 | Construction | 1 - Footings | 1 - Footings | 1 - Footings UNDERGROUND ELEC | UNDERGROUND ELEC | Date | Job | Scheduling | 1 | 2026-06-08
12 | Construction | 1 - Footings | 1 - Footings | 1 - Footings STORMWATER | STORMWATER | Date | Job | Scheduling | 1 | 2026-08-06
13 | Construction | 1 - Footings | 1 - Footings | 1 - Footings FINAL TRIM | FINAL TRIM | Date | Job | Scheduling | 1 | 8 | 15, 14
14 | Construction | 1 - Footings | 1 - Footings | 1 - Footings BIN DELIVERY | BIN DELIVERY | Date | Job | Scheduling | 1 | 13
15 | Construction | 1 - Footings | 1 - Footings | 1 - Footings BRICKS DELIVERY | BRICKS DELIVERY | Date | Job | Scheduling | 1 | 13
16 | Construction | 2 - Frame | 2 - Frame | 2 - Frame FRAMING | FRAMING | Date | Job |  | 25
17 | Construction | 2 - Frame | 2 - Frame | 2 - Frame WALL FRAME DELIVERY | WALL FRAME DELIVERY | Date | Job | Scheduling | 1 | 8 | 18
18 | Construction | 2 - Frame | 2 - Frame | 2 - Frame TRUSSES DELIVERY | TRUSSES DELIVERY | Date | Job | Scheduling | 1 | 17 | 19
19 | Construction | 2 - Frame | 2 - Frame | 2 - Frame WINDOW DELIVERY | WINDOW DELIVERY | Date | Job | Scheduling | 1 | 18 | 20
20 | Construction | 2 - Frame | 2 - Frame | 2 - Frame 1ST FIX CARPENTER LABOUR | 1ST FIX CARPENTER LABOUR | Date | Job | Scheduling | 5 | 19 | 21, 28, 24, 22, 33, 23
21 | Construction | 2 - Frame | 2 - Frame | 2 - Frame Council Notification - Wall & Roof Frame | Council Notification - Wall & Roof Frame | Date | Job | Construction Admin | 1 | 20
22 | Construction | 2 - Frame | 2 - Frame | 2 - Frame Customer Notification - Wall & Roof Frame Complete | Customer Notification - Wall & Roof Frame Complete | Date | Job | Construction Admin | 1 | 20
23 | Construction | 2 - Frame | 2 - Frame | 2 - Frame Claim - Wall & Roof Frame Stage | Claim - Wall & Roof Frame Stage | Date | Job | Construction Admin | 0 | 20
24 | Construction | 2 - Frame | 2 - Frame | 2 - Frame FRAME CHECK (3RD PARTY) | FRAME CHECK (3RD PARTY) | Date | Job | Construction (Site Supervisor) | 1 | 20 | 26, 25, 27
25 | Construction | 2 - Frame | 2 - Frame | 2 - Frame 1ST FIX PLUMBING | 1ST FIX PLUMBING | Date | Job | Construction (Site Supervisor) | 1 | 24
26 | Construction | 2 - Frame | 2 - Frame | 2 - Frame 1ST FIX GAS | 1ST FIX GAS | Date | Job | Construction (Site Supervisor) | 1 | 24
27 | Construction | 2 - Frame | 2 - Frame | 2 - Frame CABINETRY MEASURE | CABINETRY MEASURE | Date | Job | Construction (Site Supervisor) | 1 | 24
28 | Construction | 4 - Roof Cover | 4 - Roof Cover | 4 - Roof Cover ROOFING INSTALL | ROOFING INSTALL | Date | Job | Construction (Site Supervisor) | 5 | 20 | 29, 32, 30, 34, 31
29 | Construction | 4 - Roof Cover | 4 - Roof Cover | 4 - Roof Cover Customer Notification - Roof Cover Complete | Customer Notification - Roof Cover Complete | Date | Job | Construction Admin | 1 | 28
30 | Construction | 4 - Roof Cover | 4 - Roof Cover | 4 - Roof Cover Claim - Roof Cover Stage | Claim - Roof Cover Stage | Date | Job | Construction Admin | 0 | 28
31 | Construction | 4 - Roof Cover | 4 - Roof Cover | 4 - Roof Cover VELUXE / SKYLIGHT INSTALL | VELUXE / SKYLIGHT INSTALL | Date | Job | Construction (Site Supervisor) | 1 | 28 | 32
32 | Construction | 4 - Roof Cover | 4 - Roof Cover | 4 - Roof Cover SOLAR INSTALL (1) | SOLAR INSTALL (1) | Date | Job | Construction (Site Supervisor) | 1 | 31, 28
33 | Construction | 4 - Roof Cover | 4 - Roof Cover | 4 - Roof Cover TERMITE TREATMENT | TERMITE TREATMENT | Date | Job | Construction (Site Supervisor) | 1 | 20
34 | Construction | 3 - External Cladding | 3 - External Cladding | 3 - External Cladding SAND / CEMENT / HWS BOX DELIVERY | SAND / CEMENT / HWS BOX DELIVERY | Date | Job | Construction (Site Supervisor) | 1 | 28 | 37, 35, 36
35 | Construction | 3 - External Cladding | 3 - External Cladding | 3 - External Cladding LOWER CLADDING | LOWER CLADDING | Date | Job | Construction (Site Supervisor) | 10 | 34 | 40, 38, 51, 39, 42
36 | Construction | 3 - External Cladding | 3 - External Cladding | 3 - External Cladding GAS BOX DELIVERY | GAS BOX DELIVERY | Date | Job | Construction (Site Supervisor) | 1 | 34
37 | Construction | 3 - External Cladding | 3 - External Cladding | 3 - External Cladding GAS BOX INSTALL | GAS BOX INSTALL | Date | Job | Construction (Site Supervisor) | 1 | 34
38 | Construction | 3 - External Cladding | 3 - External Cladding | 3 - External Cladding Council Notification - External Cladding | Council Notification - External Cladding | Date | Job | Construction Admin | 1 | 35
39 | Construction | 3 - External Cladding | 3 - External Cladding | 3 - External Cladding Customer Notification - External Cladding Complete | Customer Notification - External Cladding Complete | Date | Job | Construction Admin | 1 | 35
40 | Construction | 3 - External Cladding | 3 - External Cladding | 3 - External Cladding Claim - External Cladding Stage | Claim - External Cladding Stage | Date | Job | Construction Admin | 0 | 35
41 | Construction | 3 - External Cladding | 3 - External Cladding | 3 - External Cladding POST CLADDING ITEMS | POST CLADDING ITEMS | Date | Job |  | 12
42 | Construction | 3 - External Cladding | 3 - External Cladding | 3 - External Cladding LOWER EAVES DELIVERY | LOWER EAVES DELIVERY | Date | Job | Construction (Site Supervisor) | 1 | 35 | 43
43 | Construction | 3 - External Cladding | 3 - External Cladding | 3 - External Cladding LOWER EAVES INSTALL | LOWER EAVES INSTALL | Date | Job | Construction (Site Supervisor) | 3 | 42 | 44
44 | Construction | 3 - External Cladding | 3 - External Cladding | 3 - External Cladding RENDER | RENDER | Date | Job | Construction (Site Supervisor) | 3 | 43 | 45
45 | Construction | 3 - External Cladding | 3 - External Cladding | 3 - External Cladding BRICK CLEAN | BRICK CLEAN | Date | Job | Construction (Site Supervisor) | 1 | 44 | 46
46 | Construction | 3 - External Cladding | 3 - External Cladding | 3 - External Cladding GARAGE DOOR MEASURE | GARAGE DOOR MEASURE | Date | Job | Construction (Site Supervisor) | 1 | 45 | 47
47 | Construction | 3 - External Cladding | 3 - External Cladding | 3 - External Cladding LOWER DOWNPIPE INSTALL | LOWER DOWNPIPE INSTALL | Date | Job | Construction (Site Supervisor) | 1 | 46 | 48
48 | Construction | 3 - External Cladding | 3 - External Cladding | 3 - External Cladding STORMWATER CONNECTION | STORMWATER CONNECTION | Date | Job | Construction (Site Supervisor) | 1 | 47 | 49
49 | Construction | 3 - External Cladding | 3 - External Cladding | 3 - External Cladding CALL UP GAS RUN IN | CALL UP GAS RUN IN | Date | Job | Construction (Site Supervisor) | 1 | 48
50 | Construction | 5 - 2nd Fix | 5 - 2nd Fix | 5 - 2nd Fix 1ST FIX | 1ST FIX | Date | Job |  | 25
51 | Construction | 5 - 2nd Fix | 5 - 2nd Fix | 5 - 2nd Fix STUD CHECK / FRAME OUT VELUXE | STUD CHECK / FRAME OUT VELUXE | Date | Job | Construction (Site Supervisor) | 1 | 35 | 54, 52, 55, 56, 57, 53
52 | Construction | 5 - 2nd Fix | 5 - 2nd Fix | 5 - 2nd Fix 1ST FIX ELECTRICAL | 1ST FIX ELECTRICAL | Date | Job | Construction (Site Supervisor) | 2 | 51 | 58
53 | Construction | 5 - 2nd Fix | 5 - 2nd Fix | 5 - 2nd Fix SOLAR INSTALL (2) | SOLAR INSTALL (2) | Date | Job | Construction (Site Supervisor) | 1 | 51 | 58
54 | Construction | 5 - 2nd Fix | 5 - 2nd Fix | 5 - 2nd Fix 1ST FIX ALARM / SECURITY | 1ST FIX ALARM / SECURITY | Date | Job | Construction (Site Supervisor) | 1 | 51 | 58
55 | Construction | 5 - 2nd Fix | 5 - 2nd Fix | 5 - 2nd Fix 1ST FIX AIRCON | 1ST FIX AIRCON | Date | Job | Construction (Site Supervisor) | 1 | 51 | 58
56 | Construction | 5 - 2nd Fix | 5 - 2nd Fix | 5 - 2nd Fix TILES DELIVERY | TILES DELIVERY | Date | Job | Construction (Site Supervisor) | 1 | 51
57 | Construction | 5 - 2nd Fix | 5 - 2nd Fix | 5 - 2nd Fix 2ND FIX DELIVERY | 2ND FIX DELIVERY | Date | Job | Construction (Site Supervisor) | 1 | 51 | 63
58 | Construction | 5 - 2nd Fix | 5 - 2nd Fix | 5 - 2nd Fix GYPROCK INSTALL | GYPROCK INSTALL | Date | Job | Construction (Site Supervisor) | 14 | 52, 53, 54, 55 | 59
59 | Construction | 5 - 2nd Fix | 5 - 2nd Fix | 5 - 2nd Fix ELECTRICAL CUTOUTS | ELECTRICAL CUTOUTS | Date | Job | Construction (Site Supervisor) | 1 | 58 | 60
60 | Construction | 5 - 2nd Fix | 5 - 2nd Fix | 5 - 2nd Fix WATERPROOFING | WATERPROOFING | Date | Job | Construction (Site Supervisor) | 1 | 59 | 62, 61
61 | Construction | 5 - 2nd Fix | 5 - 2nd Fix | 5 - 2nd Fix Council Notification - Waterproofing | Council Notification - Waterproofing | Date | Job | Construction Admin | 1 | 60
62 | Construction | 5 - 2nd Fix | 5 - 2nd Fix | 5 - 2nd Fix SCREEDING (TILER) | SCREEDING (TILER) | Date | Job | Construction (Site Supervisor) | 1 | 60 | 63
63 | Construction | 5 - 2nd Fix | 5 - 2nd Fix | 5 - 2nd Fix 2ND FIX CARPENTRY LABOUR | 2ND FIX CARPENTRY LABOUR | Date | Job | Construction (Site Supervisor) | 4 | 57, 62 | 65, 67, 64
64 | Construction | 5 - 2nd Fix | 5 - 2nd Fix | 5 - 2nd Fix Customer Notification - 2nd Fix Complete | Customer Notification - 2nd Fix Complete | Date | Job | Construction Admin | 1 | 63
65 | Construction | 5 - 2nd Fix | 5 - 2nd Fix | 5 - 2nd Fix Claim - 2nd Fix Stage | Claim - 2nd Fix Stage | Date | Job | Construction Admin | 0 | 63
66 | Construction | 6 - Practical Completion | 6 - Practical Completion | 6 - Practical Completion INTERNAL FITOUT | INTERNAL FITOUT | Date | Job |  | 15
67 | Construction | 6 - Practical Completion | 6 - Practical Completion | 6 - Practical Completion 1ST COAT PAINTING | 1ST COAT PAINTING | Date | Job | Construction (Site Supervisor) | 5 | 63 | 68
68 | Construction | 6 - Practical Completion | 6 - Practical Completion | 6 - Practical Completion CABINETRY INSTALL | CABINETRY INSTALL | Date | Job | Construction (Site Supervisor) | 3 | 67 | 69, 70
69 | Construction | 6 - Practical Completion | 6 - Practical Completion | 6 - Practical Completion STONE MEASURE | STONE MEASURE | Date | Job | Construction (Site Supervisor) | 1 | 68 | 73
70 | Construction | 6 - Practical Completion | 6 - Practical Completion | 6 - Practical Completion TILING LABOUR | TILING LABOUR | Date | Job | Construction (Site Supervisor) | 5 | 68 | 78, 72, 74, 79, 81, 71, 83, 75, 82, 80
71 | Construction | 6 - Practical Completion | 6 - Practical Completion | 6 - Practical Completion SANITARY INSTALL | SANITARY INSTALL | Date | Job | Construction (Site Supervisor) | 1 | 70
72 | Construction | 6 - Practical Completion | 6 - Practical Completion | 6 - Practical Completion GARAGE DOOR INSTALL | GARAGE DOOR INSTALL | Date | Job | Construction (Site Supervisor) | 1 | 70
73 | Construction | 6 - Practical Completion | 6 - Practical Completion | 6 - Practical Completion STONE INSTALL | STONE INSTALL | Date | Job | Construction (Site Supervisor) | 1 | 69 | 82, 80, 83, 81, 78, 79
74 | Construction | 6 - Practical Completion | 6 - Practical Completion | 6 - Practical Completion SCREEN / ROBE MEASURE | SCREEN / ROBE MEASURE | Date | Job | Construction (Site Supervisor) | 1 | 70
75 | Construction | 6 - Practical Completion | 6 - Practical Completion | 6 - Practical Completion ACCESSORIES - DELIVERY | ACCESSORIES - DELIVERY | Date | Job | Construction (Site Supervisor) | 1 | 70 | 76
76 | Construction | 6 - Practical Completion | 6 - Practical Completion | 6 - Practical Completion ACCESSORIES - INSTALL | ACCESSORIES - INSTALL | Date | Job | Construction (Site Supervisor) | 1 | 75
77 | Construction | 6 - Practical Completion | 6 - Practical Completion | 6 - Practical Completion 2ND FIX SERVICES | 2ND FIX SERVICES | Date | Job |  | 13
78 | Construction | 6 - Practical Completion | 6 - Practical Completion | 6 - Practical Completion 2ND FIX PLUMBING | 2ND FIX PLUMBING | Date | Job | Construction (Site Supervisor) | 2 | 70, 73
79 | Construction | 6 - Practical Completion | 6 - Practical Completion | 6 - Practical Completion 2ND FIX GAS | 2ND FIX GAS | Date | Job | Construction (Site Supervisor) | 1 | 70, 73
80 | Construction | 6 - Practical Completion | 6 - Practical Completion | 6 - Practical Completion 2ND FIX ELECTRICAL | 2ND FIX ELECTRICAL | Date | Job | Construction (Site Supervisor) | 2 | 73, 70
81 | Construction | 6 - Practical Completion | 6 - Practical Completion | 6 - Practical Completion 2ND FIX AIRCON | 2ND FIX AIRCON | Date | Job | Construction (Site Supervisor) | 2 | 73, 70
82 | Construction | 6 - Practical Completion | 6 - Practical Completion | 6 - Practical Completion 2ND FIX ALARM / SECURITY | 2ND FIX ALARM / SECURITY | Date | Job | Construction (Site Supervisor) | 1 | 73, 70
83 | Construction | 6 - Practical Completion | 6 - Practical Completion | 6 - Practical Completion TILING (SPLASHBACKS) | TILING (SPLASHBACKS) | Date | Job | Construction (Site Supervisor) | 2 | 73, 70 | 84
84 | Construction | 6 - Practical Completion | 6 - Practical Completion | 6 - Practical Completion FINAL COAT PAINT | FINAL COAT PAINT | Date | Job | Construction (Site Supervisor) | 5 | 83 | 85
85 | Construction | 6 - Practical Completion | 6 - Practical Completion | 6 - Practical Completion FLOORING INSTALL | FLOORING INSTALL | Date | Job | Construction (Site Supervisor) | 5 | 84 | 86
86 | Construction | 6 - Practical Completion | 6 - Practical Completion | 6 - Practical Completion SKIRTINGS / HANDLES INSTALL | SKIRTINGS / HANDLES INSTALL | Date | Job | Construction (Site Supervisor) | 1 | 85 | 89
87 | Construction | 6 - Practical Completion | 6 - Practical Completion | 6 - Practical Completion PRACTICLE COMPLETION (PCI) | PRACTICLE COMPLETION (PCI) | Date | Job |  | 19
88 | Construction | 6 - Practical Completion | 6 - Practical Completion | 6 - Practical Completion Claim - Practical Completion | Claim - Practical Completion | Date | Job | Construction Admin | 0 | 93
89 | Construction | 6 - Practical Completion | 6 - Practical Completion | 6 - Practical Completion 1ST HOUSE CLEAN | 1ST HOUSE CLEAN | Date | Job | Construction (Site Supervisor) | 1 | 86 | 90
90 | Construction | 6 - Practical Completion | 6 - Practical Completion | 6 - Practical Completion CONSTRUCTION WALK | CONSTRUCTION WALK | Date | Job | Construction (Site Supervisor) | 1 | 89 | 92, 91
91 | Construction | 6 - Practical Completion | 6 - Practical Completion | 6 - Practical Completion Customer Care - Book PCI | Customer Care - Book PCI | Date | Job | Construction Admin | 1 | 90 | 93
92 | Construction | 6 - Practical Completion | 6 - Practical Completion | 6 - Practical Completion TOUCH UPS | TOUCH UPS | Date | Job | Construction (Site Supervisor) | 5 | 90 | 93
93 | Construction | 6 - Practical Completion | 6 - Practical Completion | 6 - Practical Completion PCI WALKTHROUGH | PCI WALKTHROUGH | Date | Job | Construction (Site Supervisor) | 1 | 91, 92 | 88, 99, 94, 95
94 | Construction | 7 - Handover | 7 - Handover | 7 - Handover Customer Care - Book Handover Appointment | Customer Care - Book Handover Appointment | Date | Job | Construction Admin | 1 | 93
95 | Construction | 7 - Handover | 7 - Handover | 7 - Handover APPLIANCES - DELIVERY | APPLIANCES - DELIVERY | Date | Job | Construction (Site Supervisor) | 1 | 93 | 98, 96, 97
96 | Construction | 7 - Handover | 7 - Handover | 7 - Handover PLUMBER APPLIANCES - INSTALL | PLUMBER APPLIANCES - INSTALL | Date | Job | Construction (Site Supervisor) | 1 | 95
97 | Construction | 7 - Handover | 7 - Handover | 7 - Handover ELECTRICIAN APPLIANCES - INSTALL | ELECTRICIAN APPLIANCES - INSTALL | Date | Job | Construction (Site Supervisor) | 1 | 95
98 | Construction | 7 - Handover | 7 - Handover | 7 - Handover GAS APPLIANCES - INSTALL | GAS APPLIANCES - INSTALL | Date | Job | Construction (Site Supervisor) | 1 | 95
99 | Construction | 7 - Handover | 7 - Handover | 7 - Handover HANDOVER | HANDOVER | Date | Job | Construction (Site Supervisor) | 1 | 93+10
100 | Construction | 7 - Handover | 7 - Handover | 7 - Handover FENCING | FENCING | Date | Job | Construction (Site Supervisor) | 1
101 | Construction | 7 - Handover | 7 - Handover | 7 - Handover BASE PREP | BASE PREP | Date | Job | Construction (Site Supervisor) | 1
102 | Construction | 7 - Handover | 7 - Handover | 7 - Handover SEWER CHECK | SEWER CHECK | Date | Job | Construction (Site Supervisor) | 1
103 | Construction | 7 - Handover | 7 - Handover | 7 - Handover PAVING / CONCRETE | PAVING / CONCRETE | Date | Job | Construction (Site Supervisor) | 1
104 | Construction | 7 - Handover | 7 - Handover | 7 - Handover RAINWATWATER TANK | RAINWATWATER TANK | Date | Job | Construction (Site Supervisor) | 1
105 | Construction | 7 - Handover | 7 - Handover | 7 - Handover LANDSCAPING | LANDSCAPING | Date | Job | Construction (Site Supervisor) | 1
106 | Construction | 7 - Handover | 7 - Handover | 7 - Handover LETTER BOX | LETTER BOX | Date | Job | Construction (Site Supervisor) | 1
107 | Construction | 7 - Handover | 7 - Handover | 7 - Handover CLOTHSLINE | CLOTHSLINE | Date | Job | Construction (Site Supervisor) | 1
[6 empty] | Date | Job

## Processes
# | Lifecycle Stage | Process | Type | Department (process map) | SLA sheet (days) | SLA schedule (days) | Predecessors | Successors
| Aquistions & Development | Project Creation | Project
| Aquistions & Development | Job Creation | Project
| Aquistions & Development | PWA | Job
| Pre-Construction | Invoice | Job
| Pre-Construction | Concept Plan | Project
| Pre-Construction | Site Survey | Project
| Pre-Construction | Soil - Bore Logs | Project
| Pre-Construction | Planning Drawings | Project
| Pre-Construction | Preliminary EER | Job
| Pre-Construction | Civil Plan | Project
| Pre-Construction | Preliminary Footings | Job
| Pre-Construction | Planning Approval | Project
| Pre-Construction | Final Quote Check | Job
| Pre-Construction | Contract Signing | Job
| Pre-Construction | 2nd Deposit (contract depost) | Job
| Pre-Construction | DNF Conditions Check | Job
| Pre-Construction | Working Drawings | Job
| Pre-Construction | Pegging Plan/Encroachment Plan | Project
| Pre-Construction | Finalised EER | Job
| Pre-Construction | Attached lightweight Verandah Engineering | Job
| Pre-Construction | Footings Construciton Report (FCR) | Job
| Pre-Construction | Electrical/NBN Undergrounds | Project
| Pre-Construction | Section 221 - Stormwater/Crossover Permits | Project
| Pre-Construction | Framing and Trusses | Job
| Pre-Construction | Beam Design | Job
| Pre-Construction | Construction/Timber/Beam Jordan Check | Job
| Pre-Construction | Selections | Job
| Pre-Construction | 1st Site Inspection | Project
| Pre-Construction | Retaining, Fencing & BOB | Project
| Pre-Construction | SA Water | Project
| Pre-Construction | Construction Price Check (CPC) Sheet | Job
| Pre-Construction | Variation | Job
Building Rules Consent (BRC)
| Pre-Construction | KBS | Job
| Pre-Construction | CITB | Job
| Pre-Construction | Development Approval (DA) | Project
| Pre-Construction | Final Site Inspection | Project
| Pre-Construction | Finance | Job
| Pre-Construction | HOW Insurance | Job
| Pre-Construction | Construction Release | Job
| Cancelled | PWA Cancellation | Job
| Cancelled | Contract Cancellation | Job
| Construction | 1 - Footings | Job
| Construction | 2 - Frame | Job
| Construction | 4 - Roof Cover | Job
| Pre-Construction | 3 - External Cladding | Job
| Construction | 5 - 2nd Fix | Job
| Construction | 6 - Practical Completion | Job
| Construction | 7 - Handover | Job
Job